## QA Folder Structure
QA Folder Structure |  | Date: |  | checklists
Site QA
ADMINISTRATION BUILDING
GROUND
|  |  | Ductwork Installation | ITC-001 DUCT ROUGH IN
|  |  | Ductwork insulation | ITC-001 DUCT ROUGH IN
|  |  | Grille Installation | ITC-003 Floor Fit Off
|  |  | Refrigeration Pipe Work | ITC-002 PIPE ROUGH IN
|  |  | Mech elec installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Controls Installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | FCU Installation | ITC-001 DUCT ROUGH IN
LEVEL 1
|  |  | Ductwork Installation | ITC-001 DUCT ROUGH IN
|  |  | Ductwork insulation | ITC-001 DUCT ROUGH IN
|  |  | Grille Installation | ITC-003 Floor Fit Off
|  |  | Refrigeration Pipe Work | ITC-002 PIPE ROUGH IN
|  |  | Mech elec installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Controls Installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | FCU Installation | ITC-001 DUCT ROUGH IN
ROOF PLANT
|  |  | Ductwork Installation | ITC-001 DUCT ROUGH IN
|  |  | HHW Pipe work installation | ITC-002 PIPE ROUGH IN
|  |  | Refrigeration Pipe Work | ITC-002 PIPE ROUGH IN
|  |  | Pipe Insulation/Cladding | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Mech elec installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Controls Installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Equipment Installation | ITC-005 Equipment Installation Level 4 Plant Room
SMA BUILDING
GROUND
|  |  | Ductwork Installation | ITC-001 DUCT ROUGH IN
|  |  | Ductwork insulation | ITC-001 DUCT ROUGH IN
|  |  | Grille Installation | ITC-003 Floor Fit Off
|  |  | Refrigeration Pipe Work | ITC-002 PIPE ROUGH IN
|  |  | Mech elec installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | Controls Installation | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
|  |  | FCU Installation | ITC-001 DUCT ROUGH IN

## MECH ITCs
type | name | values
checklist | ITC-001 DUCT ROUGH IN
checkpoint | Installed to Entire standard (ENT-STD-3.1) and to latest drawings
checkpoint | Cleats installed
checkpoint | Insulated as required
checkpoint | No visible damage
checkpoint | Flex Supported to Entire standard (ENT-STD-1.1)
checkpoint | Seismic restraints installed as per Seismic design
checkpoint | Fan Coil Units installed as per the latest drawing
checklist | ITC-002 PIPE ROUGH IN
checkpoint | Pipes installed to Entire standards and latest drawings
checkpoint | Hydrostatically tested as per (ITC-010 & ITC-011)
checkpoint | Pipes insulated as required
checkpoint | Seismic restraints installed as per Seismic design
checkpoint | Drains installed to standard & on correct grade
checkpoint | Refrigeration pressure test as per (ITC-013)
checklist | ITC-003 Floor Fit Off
section | Grilles
checkpoint | Installed to latest drawing
checkpoint | Balancing dampers open
checkpoint | No visible damage
section | Filters
checkpoint | Installed to latest drawing
checkpoint | Accessible
section | Equipment
checkpoint | Access panels in correct location
checkpoint | Equipment clearly labelled
checklist | ITC-004 Penetration Treatment (sign off by relevant sub contractor)
section | Penetrations
checkpoint | Acoustic penetrations correctly sealed
checkpoint | Fire Penetrations correctly sealed
checkpoint | Photos and documentation captured by contractor
checkpoint | Penetrations labeled as required
checklist | ITC-005 Equipment Installation ADMIN ROOF Plant Room
section | Fans
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Vibration isolations installed
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Labelled
section | Energy Recovery Systems
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Vibration isolations installed
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Unit clearly labelled
section | DX Split Systems Condensing Units
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Vibration isolations installed
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Units clearly labelled
section | HEAT PUMPS
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Vibration isolations installed
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Units clearly labelled
section | Pumps
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Vibration isolations installed
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Units clearly labelled
section | Buffer Tanks
checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint | Seismic restraints Installed as per Seismic design
checkpoint | Units clearly labelled
section | Expansion and Auto Fill Systems
checkpoint | Installed to latest drawing
checkpoint | Units clearly labelled
checklist | ITC-006 Subcontractor Rough In (sign off by relevant contractor)
section | Mechanical Electrical
checkpoint | Mech elec wires installed as per design
checkpoint | MSSB Installed as per design
checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
section | Controls
checkpoint | Control wire installed as per design
checkpoint | Control Panel Installed as per design
checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
checkpoint | Devices fit off as required
section | Insulation
checkpoint | Pipe Insulation installed as required
checkpoint | Pipe Cladding Installed as required
checklist | ITC-07 Fire/smoke damper checklist
section | Fire/smoke dampers
checkpoint | Access panel in duct / ceiling for damper access, installed
checkpoint | Fire/Smoke dampers labelled
checkpoint | Installed to manufacturers requirements