## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | ce89e2c3-92c3-4532-b5c5-8bea55f7b656 |  | checklist | Commissioning Document |  |  |  |  | Yes | Commissioning Document | 481adb5e-6303-4166-ad8a-7959ba996935
checkpoint-status | b152ee0e-78f6-4d21-b800-3748af9cb859 |  | checkpoint | Please attached commissioning document and pictures
checklist-sectioned |  |  | checklist | ITC-002 PIPE ROUGH IN |  |  |  |  | Yes | ITC-002 PIPE ROUGH IN | 63b89e8c-5f22-4b32-acb6-444577d7a0ee
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Pipes installed to Entire standards and latest drawings
checkpoint-status |  |  | checkpoint | Hydrostatically tested as per (ITC-010 & ITC-011)
checkpoint-status |  |  | checkpoint | Pipes insulated as required
checkpoint-status |  |  | checkpoint | Seismic restraints installed as per Seismic design
checkpoint-status |  |  | checkpoint | Drains installed to standard & on correct grade
checkpoint-status |  |  | checkpoint | Refrigeration pressure test as per (ITC-013)
checklist-sectioned |  |  | checklist | ITC-001 DUCT ROUGH IN |  |  |  |  | Yes | ITC-001 DUCT ROUGH IN | 6ca2b634-86d9-41e8-94cd-3439bc5239b8
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Installed to Entire standard (ENT-STD-3.1) and to latest drawings
checkpoint-status |  |  | checkpoint | Cleats installed
checkpoint-status |  |  | checkpoint | Insulated as required
checkpoint-status |  |  | checkpoint | No visible damage
checkpoint-status |  |  | checkpoint | Flex Supported to Entire standard (ENT-STD-1.1)
checkpoint-status |  |  | checkpoint | Seismic restraints installed as per Seismic design
checkpoint-status |  |  | checkpoint | Fan Coil Units installed as per the latest drawing
checklist-sectioned |  |  | checklist | ITC-006 Subcontractor Rough In (sign off by relevant contractor) |  |  |  |  | Yes | ITC-006 Subcontractor Rough In (sign off by relevant contractor) | 6ed70a93-b0f3-4814-bc27-6b0de3769429
checkpoint-group |  |  | section | Mechanical Electrical
checkpoint-status |  |  | checkpoint | Mech elec wires installed as per design
checkpoint-status |  |  | checkpoint | MSSB Installed as per design
checkpoint-status |  |  | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
checkpoint-group |  |  | section | Controls
checkpoint-status |  |  | checkpoint | Control wire installed as per design
checkpoint-status |  |  | checkpoint | Control Panel Installed as per design
checkpoint-status |  |  | checkpoint | Wall and or Ceiling rough in complete (If required) ready for closing up by ceiling/wall contractor
checkpoint-status |  |  | checkpoint | Devices fit off as required
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Pipe Insulation installed as required
checkpoint-status |  |  | checkpoint | Pipe Cladding Installed as required
checklist-sectioned |  |  | checklist | ITC-005 Equipment Installation ADMIN ROOF Plant Room |  |  |  |  | Yes | ITC-005 Equipment Installation ADMIN ROOF Plant Room | 9c232e4e-f6a9-4a20-aa25-8f67291918cb
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Labelled
checkpoint-group |  |  | section | Energy Recovery Systems
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Unit clearly labelled
checkpoint-group |  |  | section | DX Split Systems Condensing Units
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | HEAT PUMPS
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Pumps
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Vibration isolations installed
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Buffer Tanks
checkpoint-status |  |  | checkpoint | Installed to latest drawing in the correct positions and egress access clearances checked
checkpoint-status |  |  | checkpoint | Seismic restraints Installed as per Seismic design
checkpoint-status |  |  | checkpoint | Units clearly labelled
checkpoint-group |  |  | section | Expansion and Auto Fill Systems
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Units clearly labelled
checklist-sectioned |  |  | checklist | ITC-003 Floor Fit Off |  |  |  |  | Yes | ITC-003 Floor Fit Off | a38572d3-0959-4d51-9043-b1b7cf101e32
checkpoint-group |  |  | section | Grilles
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Balancing dampers open
checkpoint-status |  |  | checkpoint | No visible damage
checkpoint-group |  |  | section | Filters
checkpoint-status |  |  | checkpoint | Installed to latest drawing
checkpoint-status |  |  | checkpoint | Accessible
checkpoint-group |  |  | section | Equipment
checkpoint-status |  |  | checkpoint | Access panels in correct location
checkpoint-status |  |  | checkpoint | Equipment clearly labelled
checklist-sectioned |  |  | checklist | ITC-07 Fire/smoke damper checklist |  |  |  |  | Yes | ITC-07 Fire/smoke damper checklist | aac826aa-6191-42dd-8efa-bf0e4e4d5621
checkpoint-group |  |  | section | Fire/smoke dampers
checkpoint-status |  |  | checkpoint | Access panel in duct / ceiling for damper access, installed
checkpoint-status |  |  | checkpoint | Fire/Smoke dampers labelled
checkpoint-status |  |  | checkpoint | Installed to manufacturers requirements
checklist-sectioned |  |  | checklist | ITC-004 Penetration Treatment (sign off by relevant sub contractor) |  |  |  |  | Yes | ITC-004 Penetration Treatment (sign off by relevant sub contractor) | e679ea8f-f6f9-42d6-b66c-1b7e95e8d60e
checkpoint-group |  |  | section | Penetrations
checkpoint-status |  |  | checkpoint | Acoustic penetrations correctly sealed
checkpoint-status |  |  | checkpoint | Fire Penetrations correctly sealed
checkpoint-status |  |  | checkpoint | Photos and documentation captured by contractor
checkpoint-status |  |  | checkpoint | Penetrations labeled as required