## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-NWPA-XXXX TMF - Mechanical Services RevA | itp |  |  |  |  | ITP-NWPA-XXXX TMF - Mechanical Services RevA
section | Details
checkpoint-no-status | Details:
textbox | AMS Number:
textbox | AMS Title:
textbox | Work Lot Number:
textbox | Work Lot Description:
textbox | Design Package:
textbox | Associated Design Packages:
checkpoint | Author (Mandatory)
textbox | Name:
label | Position: Site Engineer
date | Date:
holdpoint | Signature
checkpoint | Reviewer & Approver (Mandatory)
textbox | Name:
label | Position: Project Engineer
date | Date:
holdpoint | Signature
checkpoint | Additional Reviewer (If Applicable)
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature
checkpoint | Authorisation (Mandatory)
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature
section | 1.0 PRELIMINARIES - Prior To Commencement of Work – Master Worklot Records (if applicable)
checkpoint | 1.1 - Preliminary activities completed
label | Specification Reference - JH-MPR-SQE-006 Managing SQE Risks
label | Acceptance Criteria - All ‘pre-construction’ authorisations and checks completed and recorded in Pre-Commencement Checklist in PPW as part of the AMS establishment
label | Test / Inspection Method & Frequency - Prior to works commencing
label | Inspection: Project Team - PE (H)
label | Records & Comments -
bool | Pre-Commencement Checklist completed in PPW
textbox | PPW Record No.: |  | AMS/NWPA/00
holdpoint | HOLD POINT
checkpoint | 1.2 - Work Lot Map
label | Specification Reference - NWP-000-NWA-PRO-XQA-0003 - Work Lot Management Procedure
label | Acceptance Criteria - Work Lot Map attached to Work Lot
label | Test / Inspection Method & Frequency - Per work lot
label | Inspection: Project Team - SE (H)
label | Records & Comments -
bool | Work Lot Map
holdpoint | HOLD POINT
section | 2.0 MATERIAL COMPLIANCE - Prior To Commencement of Work – Master Worklot Records (if applicable)
checkpoint | 2.1 - Calibration Certificates
label | Specification Reference - JH-MPR-QUA-010
label | ○ Process Control
label | Acceptance Criteria - Confirm that external equipment calibration and testing facilities are registered in PPW.
label | ○ External equipment calibration meets contract requirements for each item of test equipment.
label | Test / Inspection Method & Frequency - Visual check with certificates, ITP, checklist or inspection report
label | Inspection: Project Team - SE (H), QA (R)
label | Records & Comments -
bool | Record of visual inspection
bool | Calibration Certificates
holdpoint | HOLD POINT
checkpoint | 2.2 - Shop Drawing Approval
label | Specification Reference - IFC Drawings
label | Acceptance Criteria - Mechanical shop drawings have been reviewed and approved by NWPA
label | Test / Inspection Method & Frequency - Prior to works commencing
label | Inspection: Project Team - PE (H)
label | Records & Comments -
bool | Approved Shop drawings
holdpoint | HOLD POINT
section | All preliminary records have been reviewed and approved. ITP signed at sections 1 to 3 and uploaded to Master lot with all preliminary records. Works may proceed onsite.
checkpoint | Site Engineer
textbox | Site Engineer Name:
date | Date:
holdpoint | Site Engineer Signature:
checkpoint | Project Engineer
textbox | Project Engineer Name:
date | Date:
holdpoint | Project Engineer Signature:
section | 4.0 CONSTRUCTION ACTIVITIES - Prior To Commencement and During Works – Sub-lot Records (if applicable)
checkpoint | 4.1 - Inspection of incoming materials:
label | ○ All mechanical Units – ERV, AC, DX, IEC, fans etc.
label | ○ Grilles
label | ○ Pipework
label | ○ Ductwork
label | Specification Reference - NWP-000-NWA-PLN-XPM-0022
label | ○ JH-MPR-PMA-007 - Material Control
label | ○ Project Requirement Specification
label | Acceptance Criteria - Materials conform to IFC drawings and Specifications
label | ○ Qty conform to purchase order requirements
label | ○ Free of defects, transportation damage and/or imperfections
label | Test / Inspection Method & Frequency - Visual check with written notes in Delivery docket, ITP, checklist or inspection report.
label | ○ Upon Delivery
label | Inspection: Subcontractor - SF (H)
label | Inspection: Project Team - SE (H)
label | Records & Comments -
bool | Ductwork Installation Checklists
bool | Ductwork Insulation Checklists
bool | Grille Installation Checklists
bool | Mech Electrical Installation Checklists
bool | Controls Installation Checklists
bool | FCU Installation Checklists
holdpoint | HOLD POINT
checkpoint | 4.2 - Mechanical Equipment Installation
label | Specification Reference - IFC Drawings
label | ○ AS 1668
label | ○ AS 3000
label | ○ Manufacturer Requirements
label | Acceptance Criteria - All pipe work and duct work has been installed as per design specifications and relevant standards
label | Test / Inspection Method & Frequency - As per each equipment
label | Inspection: Subcontractor - SF (W)
label | Inspection: Project Team - SE (S)
label | Records & Comments -
bool | Ductwork Installation Checklists
bool | Ductwork Insulation Checklists
bool | Grille Installation Checklists
bool | Mech Electrical Installation Checklists
bool | Controls Installation Checklists
bool | FCU Installation Checklists
section | 5.0 TESTING AND COMMISSIONING REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
checkpoint | 5.1 - Refrigeration Pressure Testing
label | Specification Reference - IFC Drawings
label | ○ AS 1668
label | ○ AS 3000
label | ○ Manufacturer Requirements
label | Acceptance Criteria - Pressure testing should be in accordance with the design specifications and relevant standards
label | Test / Inspection Method & Frequency - As per each air conduiting unit
label | Inspection: Subcontractor - SF (R)
label | Inspection: Project Team - SE (R)
label | Records & Comments -
bool | HHW Pipework Install Checklist
bool | Refrigeration Pipework Install Checklist
checkpoint | 5.2 - System Commissioning
label | Specification Reference - IFC Drawings
label | ○ AS 1668
label | ○ AS 3000
label | ○ Manufacturer Requirements
label | Acceptance Criteria - Mechanical systems are tested to perform in accordance with the design specifications and relevant standards
label | Test / Inspection Method & Frequency - As per each equipment
label | Inspection: Subcontractor - SF (R)
label | Inspection: Project Team - SE (R)
label | Records & Comments -
bool | Mechanical Commissioning Checklists
section | 6.0 COMPLETION REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
checkpoint | 6.1 - Works Completion Inspection (with Subcontractor)
label | Specification Reference - NWP-000-NWA-PRO-XDC-0002 – Outstanding Works, Works Completion and Defect Management Procedure
label | Acceptance Criteria - Works completed in accordance with IFC Dwg and Specifications
label | ○ Inspection completed & recorded prior to releasing activity
label | Test / Inspection Method & Frequency - Visual Inspection with Subcontractor at the end of work activity prior to signing off ITP
label | Inspection: Project Team - PE (H)
label | Inspection: Project Team Sign Date - Refer to CHK241
label | Records & Comments -
bool | NWPA Completion Checklist – CHK/NWPA/00241
holdpoint | HOLD POINT
checkpoint | 6.2 - Close out NCR(s)
label | Specification Reference - NWP-000-NWA-PLN-XPM-0022 Quality Management Plan
label | Acceptance Criteria - All out of tolerances notified via NCR reporting system
label | ○ All NCR’s applicable to the works to be raised in a timely manner and, if applicable, designer confirmation to be obtained.
label | Test / Inspection Method & Frequency - Prior to closing and signing ITP
label | Inspection: Project Team - PE (H), QM (H)
label | Inspection: Project Team Sign Date - Refer to CHK241
label | Records & Comments -
bool | NWPA Completion Checklist – CHK/NWPA/00241
holdpoint | HOLD POINT
checkpoint | 6.3 - Relevant DCN(s) and RFI(s):
label | Specification Reference - NWP-000-NWA-PLN-XPM-0006 Design and Engineering Management Plan
label | Acceptance Criteria - Design/Construction Queries or clarifications relating to this ITP are addressed and closed.
label | ○ All ‘parts’ of RFI are included
label | ○ All ‘supporting evidence’ is included
label | Test / Inspection Method & Frequency - DCNs and RFIs closed and linked to NCRs where applicable
label | Inspection: Project Team - PE (H)
label | Inspection: Project Team Sign Date - Refer to CHK241
label | Records & Comments -
bool | NWPA Completion Checklist – CHK/NWPA/00241
holdpoint | HOLD POINT
checkpoint | 6.4 - Redline Marked-up Drawings
label | Specification Reference - NWP-000-NWA-GUD-XDM-0002 Red Line Guidelines
label | Acceptance Criteria - Redline drawing to be produced & maintained by engineers to include all changes made during construction
label | ○ Redline to use latest IFC version of the design drawings and be marked- up in red pen, to identify any variations
label | ○ RFI, DCR, ECW and Client Wavers to be referenced in redlines (as required)
label | Test / Inspection Method & Frequency - Completion of Works
label | Inspection: Project Team - PE (H)
label | Inspection: Project Team Sign Date - Refer to CHK241
label | Records & Comments -
bool | NWPA Completion Checklist – CHK/NWPA/00241
holdpoint | HOLD POINT