## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 5c7f43c0-e70b-4e17-b219-4a40a4b0037e |  | checklist | Mirror/Splashbacks |  |  |  |  | Yes | QA - Mirror/Splashbacks | a82c151e-269d-4f5c-85a8-8d0dc9ecbfdc
checkpoint-status | 2161f328-1541-40a9-8c68-7af931d809af |  | checkpoint | Surface prep
checkpoint-status | 1b437a9b-1767-44ad-9262-9c9647f8ef1d |  | checkpoint | Glass installed
checkpoint-status | 846fe988-b244-42ef-9c3e-571416481031 |  | checkpoint | Trade clean
checklist-flat | 792d3a74-0ba7-49a5-8590-fc1d7446d7f8 |  | checklist | Captive Skylight |  |  |  |  | Yes | QA - Captive Skylight | e9b5a563-7cf4-4124-959b-63b824a39668
checkpoint-status | f5fe5b16-56ba-430c-9e5a-7eef1a13d0d8 |  | checkpoint | Frame prep
label | 3ecdd06f-32a9-56bd-8351-16d33178236e |  | note | Ensure setting blocks @ quarter points
checkpoint-status | 0550e3c8-7c90-4ddf-81c2-31ddc188b403 |  | checkpoint | Check feet are installed
checkpoint-status | 82d23771-08d3-4ecc-b947-9d071dcb7233 |  | checkpoint | Glass installed
checkpoint-status | 4622ef1d-7353-41f3-91f5-6967474f0cb3 |  | checkpoint | Beads installed
checkpoint-status | da0ddde5-06fa-483b-8bed-bb836013c95c |  | checkpoint | Correct wedge installed
checkpoint-status | 9dc728d7-8d17-4594-8710-9dbce537a9b9 |  | checkpoint | Silicone joints
checkpoint-status | 1ad1d5a9-a061-44d6-b8c3-c87da1436671 |  | checkpoint | Trade clean
checklist-flat | c727103b-4c3c-4c36-bbfd-82a8a5cc7e1d |  | checklist | QA - Frameless Manual Sliding Doors |  |  |  |  | Yes | QA - Frameless Manual Sliding Doors | 971cb6da-45de-4fab-ac44-52bd0dc06468
checkpoint-status | c4c1c162-1ff6-4047-90f7-8445423af99c |  | checkpoint | Top Tracks installed correctly
label | 911ba1a5-31d8-5e9a-b7a1-e2c8d72a447e |  | note | Check screws installed correctly
checkpoint-status | ddf98eb1-ad31-4196-9f73-376f5f7c93f1 |  | checkpoint | Bottom tracks installed correctly
label | 8745cd73-25ba-5123-9c3e-a0b0d72003ab |  | note | Check plastic insert is installed
checkpoint-status | c8f42486-167f-4fc8-a2c8-daa1a1968593 |  | checkpoint | H Packers cut back and painted
checkpoint-status | d73ed5f4-9d82-41e5-870e-fb2f331cb2fb |  | checkpoint | Door rails installed correctly to the glass
checkpoint-status | 53140f9d-3e2f-4ab1-ac44-fbad5c012295 |  | checkpoint | Covers, end caps and pick ups installed
checkpoint-status | b800f5e8-f925-4489-b1f4-073396e5437b |  | checkpoint | Handles installed
checkpoint-status | 767b3931-80e7-4e13-aa22-17e1702bdc77 |  | checkpoint | Channel for fixed panel installed correctly
label | 5001eb1c-c91c-53d3-85f8-10ebbe92868f |  | note | Check screws installed correctly
label | 305af284-4cc2-595f-9c50-0689308cf628 |  | note | Check for damage
checkpoint-status | 5737d599-4d50-45ad-84e7-3ed1c2916f46 |  | checkpoint | Glass installed correct way around
label | 5a465e78-88b3-5710-b916-4ed93e4b68b4 |  | note | Ensure setting blocks @ quarter points
label | d28c7252-4e8a-5e41-9587-6a558061c353 |  | note | Check edge-work & unit marking
checkpoint-status | 2e0dea59-78fa-43db-beb9-5e50bc6b4e5a |  | checkpoint | Correct wedge installed
label | 7a329cc2-0d8b-5388-8398-60d93ac4d30f |  | note | Check tight fitment
checkpoint-status | 30967a8a-ae60-4567-a32d-e06c1d44c2f1 |  | checkpoint | Silicone joints completed
checkpoint-status | 4eb72556-4398-458c-8369-fc7e5a08a084 |  | checkpoint | Trade clean
checklist-flat | 19fa7750-dbe5-4ccf-8e58-2409fb730a48 |  | checklist | QA - Framed Fixed Glazing |  |  |  |  | Yes | QA - Framed Fixed Glazing | 7a453494-4d53-4e52-a104-c02588f2a233
checkpoint-status | af9f978a-f269-4230-b2a3-4e9dad106745 |  | checkpoint | Channel for fixed panel installed correctly
label | 629aa2da-fd80-5f23-8701-ff4b1b35d9cc |  | note | Check screws installed correctly
label | 26c68614-a94a-571c-b6ec-75ed9ee112a3 |  | note | Check for damage
checkpoint-status | d8c42e92-5686-4f36-a8d1-9ff6fb8d540d |  | checkpoint | Backing wedge installed
checkpoint-status | 4412073a-e2c7-433a-b4cc-cbe6fee68d3b |  | checkpoint | Glass installed correct way around
label | d8758292-682c-5ca2-8e95-4e588a94ca6d |  | note | Ensure setting blocks @ quarter points
label | 51608391-5c6d-5f5b-89e9-8bcded6a54c6 |  | note | Check edge-work & unit marking
checkpoint-status | 05a7a6ee-7f8f-4373-a3a1-50e2204a8e97 |  | checkpoint | Beads installed
checkpoint-status | 56f1b9a0-b23e-48e0-9ad1-6ea9dc4dedbd |  | checkpoint | Wedge installed
label | a3c5f313-c0f0-5a02-a62d-c14953583ab7 |  | note | Correct wedge per specification
checkpoint-status | 187d1a22-93ce-4908-a16f-2df19ba87878 |  | checkpoint | Silicone joints completed
checkpoint-status | bb56350f-5ca8-4d7c-a4a2-1f38ee3c5da6 |  | checkpoint | Trade clean
checklist-flat | 02b55767-ef07-4814-b9f8-e83764693490 |  | checklist | QA - Ballustrades |  |  |  |  | Yes | QA - Ballustrades | 99c7b6ca-2109-49a8-83e1-99ed01e34e2d
checkpoint-status | ebe581be-79e1-4de6-9a56-66fbeb1c6121 |  | checkpoint | Fixings drilled & chem-set
label | 7f2af103-acf3-5808-bb32-1900c955c262 |  | note | timber: coach screwed with sika-fix
checkpoint-status | 38895f8a-6270-42cb-abd7-0e0dd69ae148 |  | checkpoint | Hardware installed per PS1
label | 11ce906b-65e1-56fe-a3b8-921d81dadb27 |  | note | Re-tension fixings & check hardware for damage
checkpoint-status | c1be2f10-556c-48f2-b5fa-0d102b23369c |  | checkpoint | Glass installed & plumbed per PS1
label | e4d778ed-3dc6-55d4-91f2-b8e51167d393 |  | note | Pre-check edgework & ensure gaps are even
checkpoint-status | dc8b873d-359c-4224-a23a-7b473826456b |  | checkpoint | Hand-rail / link-rail installed
checkpoint-status | 6529ce9f-9b63-40ea-bad3-0e5a0692d122 |  | checkpoint | Cover Caps and end caps Installed
checkpoint-status | d86b850d-4d6b-4385-93d1-d0b80d3232ce |  | checkpoint | Trade clean
checklist-flat | f083fb0b-6704-4252-afcd-9417f9ef629d |  | checklist | Frameless Doors |  |  |  |  | Yes | QA - Frameless Doors | 46f6d34b-482d-494e-ad91-43faed54c34d
checkpoint-status | ef308dcd-31df-433b-b9be-1831902bb7cc |  | checkpoint | Channel installed
label | fbcc1f25-70bc-540d-ad49-8fe8c7287b63 |  | note | Check alignment per plans & check for damage
checkpoint-status | a0307595-04c2-41f2-95ed-61113e60154b |  | checkpoint | Hardware installed
label | 68dd3294-0126-59fd-b983-20e59987d909 |  | note | Check for marking
checkpoint-status | ca20ef54-1340-4273-9478-4bca62a142a8 |  | checkpoint | Check gaps are even
checkpoint-status | 6308ba30-75e8-4564-aa66-3d0be45f0117 |  | checkpoint | Glass installed
checkpoint-status | a1ff8970-2b25-4deb-b32d-ecd570eb4218 |  | checkpoint | Silicone joints
checkpoint-status | 4f547536-39b2-47e1-bb08-3e17f97a5118 |  | checkpoint | Trade clean
checklist-flat | 23e5626d-4f50-4768-a3db-da41adb7e117 |  | checklist | Captive Glazing |  |  |  |  | Yes | QA - Captive Glazing | 942746ba-95f7-45dd-858b-ac1ad321afea
checkpoint-status | 16d79d94-3903-4038-b569-681b1aa533c8 |  | checkpoint | Frame prep
label | cf6f8214-e641-5026-be55-ec28d6505a9e |  | note | Ensure setting blocks @ quarter points
checkpoint-status | bd66ad66-d603-4c52-beed-c84870eae882 |  | checkpoint | Glass installed correct way around
label | bd3c2621-1838-583f-9e02-d4614abab3e4 |  | note | Check edge-work & unit marking
checkpoint-status | 53fa4fa2-e24d-45b7-8e0d-4b8fd9427bc0 |  | checkpoint | Beads installed
checkpoint-status | 69a3e5c9-41c1-4024-a97d-8cff1942b8c5 |  | checkpoint | Wedge installed
label | be048a3e-435f-58f1-a25c-8dca34139c60 |  | note | Correct wedge per specification
checkpoint-status | a04e665a-9719-4048-a145-8df078e69d25 |  | checkpoint | Trade clean
checklist-flat | 3444a99a-69b8-474e-862f-1a279dc00d1a |  | checklist | Canopies |  |  |  |  | Yes | QA - Canopies | 55ad9884-30cd-4fb5-92bb-db90fd20916b
checkpoint-status | 1672347e-0010-4277-aade-76ca231058a9 |  | checkpoint | Install hardware per PS1
label | 9b5d2520-7154-597f-ae90-075f1ea7e5fd |  | note | Ensure fittings & swivel heads bolted tight
checkpoint-status | e5cb80c7-75fe-4983-b794-c98b50d3e4b8 |  | checkpoint | Glass installed & aligned per PS1
label | b42c3e08-32d1-5644-9798-7a0e5f648494 |  | note | Check edge-work & unit marking
checkpoint-status | 666c2a11-93b7-43ad-8bee-88b78acba2da |  | checkpoint | Silicone joints
checkpoint-status | cf66d7e5-9a90-44d5-94a4-4a5588c94e79 |  | checkpoint | Trade clean
checklist-flat | 43ab5d0f-1054-4aad-b505-0f5552a97ea3 |  | checklist | Showers |  |  |  |  | Yes | QA - Showers | 0fdd5db8-ddae-4ae7-b642-70a203cb46a2
checkpoint-status | 6beade9b-4400-44b4-9909-4bece929102d |  | checkpoint | Channel installed
label | 45959ffb-c1c8-59da-9c61-4b4d8b647adf |  | note | Check alignment per plans & check for damage
checkpoint-status | 7f85092a-b3a7-4a5d-806e-833e153293a4 |  | checkpoint | Hardware installed
label | 66d30591-4d81-54e2-9aa6-138e7ce833a9 |  | note | Check for marking
checkpoint-status | 6ccfd93c-8c01-43f8-999f-2ace185df305 |  | checkpoint | Glass installed
label | 9b8e7677-4968-530c-9b92-6926c3259ea5 |  | note | Check quality, safety stamps & gaps are even
checkpoint-status | faf40a78-94d4-41e6-8680-ed3aaa8deb09 |  | checkpoint | Silicone joints
checkpoint-status | 055092f6-f484-4176-95a2-4532ce058e0a |  | checkpoint | Trade clean
checklist-flat | 33f71324-f3d0-4986-8098-a7c07c701411 |  | checklist | Frameless Auto Doors |  |  |  |  | Yes | QA - Frameless Auto Doors | c4435fcd-b015-40d3-b85e-a11b19869616
checkpoint-status | f63f9707-bde9-4307-85a4-45cbe1a76e90 |  | checkpoint | Hardware installed
checkpoint-status | 54b77993-eee4-499b-bdfe-3daebfcf614d |  | checkpoint | Glass installed level & plumb
checkpoint-status | df484dd4-d049-44ca-b9b1-cc5c652179eb |  | checkpoint | Check gaps are even
checkpoint-status | 5b523103-f950-4da9-9e87-e654bd9d3d5f |  | checkpoint | Trade clean
checklist-flat | 9ba0620f-3600-43e0-ba33-6f340eb77671 |  | checklist | 2 Sided Structural |  |  |  |  | Yes | QA - 2 Sided Structural | ce0ce856-d5b7-4614-a806-2a329c70dcaa
checkpoint-status | a10dfc54-a85a-4fd8-8f12-b9dc5030dc95 |  | checkpoint | Frame prep
checkpoint-status | af6861d8-9c7b-4aaf-9ce4-3406cb410bb4 |  | checkpoint | Structural taping
checkpoint-status | 15b3771d-277d-448b-b99f-0f8e57a9ab85 |  | checkpoint | Glass installed per structural submission
label | 4ae5e6e0-7efd-5e63-91e6-53997539c447 |  | note | Pre-check edgework & any markings on glass
checkpoint-status | 45ae458e-1140-48fe-9a7b-ad00cc8a2c9d |  | checkpoint | Beads installed
checkpoint-status | fd239154-f923-48a3-baa5-f1cd2b6e5969 |  | checkpoint | Ties installed
checkpoint-status | 51c0a933-b454-46a3-81db-951f886ea188 |  | checkpoint | Structural silicone
checkpoint-status | 6643abad-01d7-42bf-9549-c1185014bfe9 |  | checkpoint | Trade clean
checkpoint-status | 4eeb0133-679f-4029-8f8f-3f41971c5594 |  | checkpoint | Ties removed
checklist-flat | a55bd02b-99f5-44bb-ab41-4f246e92e70c |  | checklist | Internal Glazing |  |  |  |  | Yes | QA - Internal Glazing | a4be6dd7-f990-4531-9409-f8611e23c6a5
checkpoint-status | a28059c0-7c37-41cd-a759-b02ab08f3ed2 |  | checkpoint | Frame prep
label | 58d8e2e6-25ab-519d-8000-091272880ee0 |  | note | Ensure setting blocks @ quarter points
checkpoint-status | 57fd627a-6447-4e46-b14e-4fea3309a4ab |  | checkpoint | Glass installed
checkpoint-status | 9603afcc-72ee-4743-9252-720ff8085e68 |  | checkpoint | Beads installed
checkpoint-status | c68e1c91-d0f1-49d4-8468-1aecc949b4ec |  | checkpoint | Correct wedge installed
checkpoint-status | cf9b77b2-4d2f-46b0-9d8d-ef9457128a73 |  | checkpoint | Silicone joints
checkpoint-status | 245e6fcd-9622-4739-ae39-0bcc836623f9 |  | checkpoint | Trade clean
checklist-flat | e1fe79cb-99dd-40ee-8ba4-1a752f2427b2 |  | checklist | Spider Walls |  |  |  |  | Yes | QA - Spider Walls | 45a6b104-ddd6-4df3-bcf5-c665d539b68b
checkpoint-status | ff1ea9d5-9c58-4a02-8c13-4d388a979f50 |  | checkpoint | Install hardware per PS1
label | 2cc3d4e5-e192-57b9-843e-99accbff44ff |  | note | Ensure fittings & swivel heads bolted tight
checkpoint-status | bffaed8d-3c8c-46fb-8c12-568da7f00443 |  | checkpoint | Glass installed & aligned per PS1
label | af078006-19a5-536b-8c01-ef68562ba257 |  | note | Check edge-work & unit marking
checkpoint-status | f25ac75f-c199-4cae-a58e-36b9c5dbd48c |  | checkpoint | Silicone joints
checkpoint-status | 44400ef3-1aeb-4563-ba7d-69a161f8c32b |  | checkpoint | Trade clean