## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev B | itp |  |  |  |  | INF-HSEQ CC0398-ITP-003 Base Pavement Construction Rev B
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs - 235929-000-CV-SP-002
label | Acceptance criteria - What is the lot size?
textbox | Acceptance |  |  | m2
label | Maximum lot size = 4000m2
label | Key - S
label | VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot Mark-Up
checkpoint | 1.2 - Survey set-out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Is the work area clearly pegged out for line and level?
button | Acceptance | Yes,No,N/A
label | Key - W
label | VIVA - S
checkpoint | 1.3 - Material classification and source
label | Ref docs - 235929-000-CV-SP-002
label | Acceptance criteria - Has the nominated materials been approved for use on the project?
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | iDocs Approval Document
textbox | iDocs Number
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Conformance of previous layer
checkpoint | 2.1 - Conformance of previous layer
label | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | ITP Number
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | Type of Pavement:
label | ○ For Crushed Rock Placement Below Concrete Pavement Refer to Section 3.0
label | ○ For Crushed Rock Placement for Gravel Pavement Refer to Section 4.0
label | ○ If multiple pavement types exist please complete as applicable
label | ○ Please strikeout not applicable sections
section | 3.0 Crushed Rock Placement Below Concrete Paving
checkpoint | 3.1 - Placement
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has Class 2 Crushed Rock been placed to be a minimum of 250mm Thick as per IFC Drawings?
label | ○ Crushed Rock Layers must not exceed 250mm thick lifts if additional Crushed Rock is required.
button | Acceptance | Yes,No,N/A
label | Key - S
label | VIVA - S
checkpoint | 3.2 - Moisture
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Key - S
label | VIVA - S
checkpoint | 3.3 - Compaction
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Compaction Testing is to be completed at 3 tests per lot to the below requirements:
label | ○ 98% MDD
label | ○ +-3% of Modified Moisture Content
label | – If testing of the first 3 consecutive lots have achieved the above requirements testing is to be reduced to testing per 2 lots until such time that a lot fails to meet the specified requirements.
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Compaction test reports
checkpoint | 3.5 - Test rolling
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation?
textbox | List attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’ please see below
label | If ‘yes’ please proceed
label | Key - H
label | VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Proof Roll Sheet
checkpoint | 3.6 - Identification of soft wet or unstable material
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
button | Acceptance | Yes,No,N/A
textbox
label | Key - H
label | VIVA - W
checkpoint | 3.7 - Treatment of unsuitable material
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the nominated soft/wet spot been rectified by a remove and replace method?
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - W
checkpoint | 3.8 - Placement of Polythene Membrane
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the Polythene Membrane been installed above the completed Crushed Rock layer?
button | Acceptance | Yes,No,N/A
label | Key - S
label | VIVA - S
section | 4.0 Crushed Rock Paving
checkpoint | 4.1 - Placement of Geogrid
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has Geogrid been installed where non-paved areas have been excavated?
button | Acceptance | Yes,No,N/A
label | Key - W
label | VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material Approval
checkpoint | 4.2 - Placement of Crushed Rock
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has 20mm Class 3 Crushed Rock been placed to be 400mm thick?
label | ○ Crushed Rock Layers must not exceed 250mm thick
button | Acceptance | Yes,No,N/A
label | Key - S
label | VIVA - S
checkpoint | 4.3 - Moisture
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
button | Acceptance | Yes,No,N/A
label | Key - S
label | VIVA - S
checkpoint | 4.4 - Compaction
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Compaction Testing is to be completed at 3 tests per lot to the below requirements:
label | ○ 100% Standard Compaction
label | ○ +-3% of Modified Moisture Content
label | If testing of the first 3 consecutive lots have achieved the above requirements testing is to be reduced to testing per 2 lots until such time that a lot fails to meet the specified requirements.
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Compaction test reports
checkpoint | 4.5 - Test rolling
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Does the layer withstand test rolling without visible deformation?
textbox | List attendees:
button | Acceptance | Yes,No,N/A
label | If ‘no’ please see below
label | If ‘yes’ please proceed
label | Key - H
label | VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Proof Roll Sheet
checkpoint | 4.6 - Identification of soft wet or unstable material
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - What quantity of soft, wet or unstable material is present?
textbox | Acceptance |  |  | m2
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Photos
checkpoint | 4.7 - Treatment of unsuitable material
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the nominated soft/wet spot been rectified by a remove and replace method?
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Proof Roll Sheet
section | 5.0 Conformance check
checkpoint | 5.1 - Pavement finish
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the crushed rock layer been finished to a smooth and uniform surface?
button | Acceptance | Yes,No,N/A
label | Key - W
checkpoint | 5.2 - Surface level of pavement courses
label | Ref docs - IFC Drawings 235929-000-CV-SP-002
label | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
label | ○ Tolerance: +-15mm
button | Acceptance | Yes,No,N/A
label | Key - H
label | VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | As built reports
holdpoint | AUTHORITY HOLDPOINT