## Curtain Wall Breakdown (hidden)
CHECKLISTS
North Elevation
Ground level
|  | Wight Opening/Area Acceptance |  | Wight Opening/Area Accrptance Checklist
|  | Curtain Wall External |  | Curtain Wall External Checklist
|  | Curtain Wall Internal |  | Curtain Wall Internal Checklist
|  | Subsill Installation |  | Subsill Installation Checklist
|  | Wight Area Completion Checkist |  | Wight Area Completion Checkist
Level 1
Batch 1.1
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Batch 1.2
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Batch 1.3
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Level 2
Batch 4
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Batch 3
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Level 3
Batch 8
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Batch 7A
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
......
East Elevation
Ground
Level 1
Level 2
Level 3
Level 4
Level 5
Level 6
Level 7
Level 8
South Elevation
Ground
Batch 2
|  |  | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
|  |  | Curtain Wall External | Curtain Wall External Checklist
|  |  | Curtain Wall Internal | Curtain Wall Internal Checklist
|  |  | Subsill Installation | Subsill Installation Checklist
|  |  | Webfordge Checklist | Webfordge Checklist
|  |  | Wight Area Completion Checkist | Wight Area Completion Checkist
Batch 9
Wight Opening/Area Acceptance
Curtain Wall External
Curtain Wall Internal
Subsill Installation
Wight Area Completion Checkist
Level 1
Batch 2
Wight Opening/Area Acceptance
Curtain Wall External
Curtain Wall Internal
Subsill Installation
Wight Area Completion Checkist
Batch 9
Wight Opening/Area Acceptance
Curtain Wall External
Curtain Wall Internal
Subsill Installation
Wight Area Completion Checkist
Level 2
Batch 2
Wight Opening/Area Acceptance
Curtain Wall External
Curtain Wall Internal
Subsill Installation
Wight Area Completion Checkist
Batch 10
Wight Opening/Area Acceptance
Curtain Wall External
Curtain Wall Internal
Subsill Installation
Wight Area Completion Checkist
Level 3

## Curtain Wall Breakdown Format (hidden)
Batches | a | b | CHECKLISTS
Batch 1
Ground level
NORTH ELEVATION
| B1-GL-P1-N | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B1-GL-P2-N | Curtain Wall External | Curtain Wall External Checklist
| B1-GL-P3-N | Curtain Wall Internal | Curtain Wall Internal Checklist
| B1-GL-P4-N | Subsill Installation | Subsill Installation Checklist
| B1-GL-P5-N | Wight Area Completion Checkist | Wight Area Completion Checkist
B1-GL-P14-N
EAST ELEVATION
| B1-GL-P14-E | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B1-GL-P6-E | Curtain Wall External | Curtain Wall External Checklist
| B1-GL-P7-E | Curtain Wall Internal | Curtain Wall Internal Checklist
| B1-GL-P8-E | Subsill Installation | Subsill Installation Checklist
| B1-GL-P9-E | Wight Area Completion Checkist | Wight Area Completion Checkist
B1-GL-P10-E
B1-GL-P11-E
B1-GL-P12-E
B1-GL-P13-E
Level 1
EAST ELEVATION
| B1-L1-P27-E | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B1-L1-P28-E | Curtain Wall External | Curtain Wall External Checklist
| B1-L1-P29-E | Curtain Wall Internal | Curtain Wall Internal Checklist
| B1-L1-P30-E | Subsill Installation | Subsill Installation Checklist
| B1-L1-P31-E | Wight Area Completion Checkist | Wight Area Completion Checkist
B1-L1-P32-E
B1-L1-P33-E
B1-L1-P34-E
B1-L1-P35-E
B1-L1-P36-E
NORTH ELEVATION
| B1-L1-P21-N | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B1-L1-P22-N | Curtain Wall External | Curtain Wall External Checklist
| B1-L1-P23-N | Curtain Wall Internal | Curtain Wall Internal Checklist
| B1-L1-P24-N | Subsill Installation | Subsill Installation Checklist
| B1-L1-P25-N | Wight Area Completion Checkist | Wight Area Completion Checkist
B1-L1-P26-N
B1-L1-P13-N
B1-L1-P14-N
B1-L1-P15-N
B1-L1-P16-N
B1-L1-P17-N
B1-L1-P18-N
B1-L1-P19-N
B1-L1-P37-N
B1-L1-P5-N
B1-L1-P6-N
B1-L1-P7-N
B1-L1-P8-N
B1-L1-P9-N
B1-L1-P10-N
B1-L1-P11-N
B1-L1-P12-N
WEST ELEVATION
| B1-L1-P1-W | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B1-L1-P2-W | Curtain Wall External | Curtain Wall External Checklist
| B1-L1-P3-W | Curtain Wall Internal | Curtain Wall Internal Checklist
| B1-L1-P4-W | Subsill Installation | Subsill Installation Checklist
| B1-L1-P37-W | Wight Area Completion Checkist | Wight Area Completion Checkist
B1-L1-P20-W
Batch 2
Ground level
SOUTH ELEVATION
| B2-GL-P1-S | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B2-GL-P2-S | Curtain Wall External | Curtain Wall External Checklist
| B2-GL-P3-S | Curtain Wall Internal | Curtain Wall Internal Checklist
| B2-GL-P4-S | Subsill Installation | Subsill Installation Checklist
| B2-GL-P5-S | Wight Area Completion Checkist | Wight Area Completion Checkist
B2-GL-P6-S
B2-GL-P7-S
Level 1
SOUTH ELEVATION
| B2-L1-P1-S | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B2-L1-P2-S | Curtain Wall External | Curtain Wall External Checklist
| B2-L1-P3-S | Curtain Wall Internal | Curtain Wall Internal Checklist
| B2-L1-P4-S | Subsill Installation | Subsill Installation Checklist
| B2-L1-P5-S | Wight Area Completion Checkist | Wight Area Completion Checkist
B2-L1-P6-S
B2-L1-P7-S
WEST ELEVATION
| B2-L1-P8-S | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B2-L1-P9-S | Curtain Wall External | Curtain Wall External Checklist
| B2-L1-P10-S | Curtain Wall Internal | Curtain Wall Internal Checklist
| B2-L1-P11-S | Subsill Installation | Subsill Installation Checklist
| B2-L1-P12-S | Wight Area Completion Checkist | Wight Area Completion Checkist
B2-L1-P13-S
B2-L1-P14-S
B2-L1-P15-S
B2-L1-P16-S
B2-L1-P17-S
B2-L1-P18-S
B2-L1-P19-S
B2-L1-P20-S
B2-L1-P21-S
B2-L1-P22-S
B2-L1-P23-S
B2-L1-P24-S
B2-L1-P25-S
Level 2
SOUTH ELEVATION
| B2-L2-P1-S | Wight Opening/Area Acceptance | Wight Opening/Area Accrptance Checklist
| B2-L2-P2-S | Curtain Wall External | Curtain Wall External Checklist
| B2-L2-P3-S | Curtain Wall Internal | Curtain Wall Internal Checklist
| B2-L2-P4-S | Subsill Installation | Subsill Installation Checklist
| B2-L2-P5-S | Wight Area Completion Checkist | Wight Area Completion Checkist
B2-L2-P6-S
B2-L2-P7-S
Batch 3

## Breakdown Form
ConQA - Breakdown
Folder | Elevation / Type | Detail | Checklist
Job Details |  |  | Job Details
Safety |  |  | Safety
Quality
CW 1
|  | Ability to Add | Ability to Add
CW 2
|  | Ability to Add | Ability to Add
CW 3
|  | Ability to Add | Ability to Add
CW 4
|  | Ability to Add | Ability to Add
CW 5
|  | Ability to Add | Ability to Add
CW 6
|  | Ability to Add | Ability to Add
CW 7
|  | Ability to Add | Ability to Add
Punch Windows
|  | Ability to Add | Ability to Add
Skylight
|  | Ability to Add | Ability to Add
Variations |  |  | Ability to Add

## Summary checklist (hidden)
type | name | values
checklist | Wight Opening/Area Acceptance Checklist |  | SUMMARY W/ SUBSILL
checkpoint | Area Acceptable, All elements approved |  | Wight Opening/Area Acceptance Checklist
bool | Check the height & Level |  | Curtain Wall External Checklist
bool | Check the structure within the tolerance accetable (Slab edge +-25mm/Slab level +-10mm) PHOTO REQUIRED |  | Curtain Wall Internal Checklist
bool | Waterproofing ( Check if there unadeque application) PHOTO REQUIRED |  | Subsill Installation Checklist
holdpoint | Raise Remedial / Request Signoff |  | Wight Area Completion Checkist
type | name | values | SUMMARY W/0 SUBSILL
checklist | Curtain Wall External Checklist |  | Wight Opening/Area Acceptance Checklist
checkpoint | Setout / grids/ datum lines (refer to Survey mark/Setting out) |  | Curtain Wall External Checklist
checkpoint | Secondary Bracket Installed, Bolt torque (refer to SD)PHOTO REQUIRED PER BATCHES |  | Curtain Wall Internal Checklist
checkpoint | Subsill installed (refer to subsill QA)
checkpoint | Curtain Wall Panel Check ( Primary Brackets, support bracket for Symonith, Glass, Neolith)
checkpoint | Panel locked off position as per module
checkpoint | Spigot & soakers sealed - PHOTO REQUIRED
checkpoint | External flashings / weather seals installed - PHOTO REQUIRED
checkpoint | Horizontal & Vertical Fins Installed
type | name | values
checklist | Curtain Wall Internal Checklist
checkpoint | Airseal and internal flashings
checkpoint | PGI Galv. Z support clips installed
checkpoint | PGI fire insulation installed - PHOTO REQUIRED
checkpoint | Trims and closers (smoke seal) - PHOTO REQUIRED
checkpoint | Blind Box installed - PHOTEO REQUIRED
checkpoint | Sill Trunking Installed - PHOTO REQUIRED
checkpoint | Vertical Trunking Installed - PHOTO REQUIRED
checkpoint | Trade clean / protected
type | name | values
checklist | Subsill Installation Checklist
checkpoint | Setout / grids/ datum lines
checkpoint | Inspection of membrane / sign off from builder
checkpoint | Markout and drill holes - check edge distance (As per Survey mark setting out)
checkpoint | Install subsill / Deadload blocks/ splicers / soakers
checkpoint | Install backer rod - PHOTO REQUIRED
checkpoint | Complete airseal within application time allowed - PHOTO REQUIRED
checkpoint | Splices,Top Angle fitted & soakers sealed - PHOTO REQUIRED
type | name | values
checklist | Wight Area Completion Checkist
checkpoint | All elements completed correctly as per specification, reviewed and approved
holdpoint | Raise Remedial / Request Signoff
type | name | values
checklist | Skylights Installation Checklist
checkpoint | Steel structure acceptance
checkpoint | Install glazing channels
checkpoint | Install glazing bars (seal splice joint)
checkpoint | Install transom (seal joint to top of bar / end of transom)
checkpoint | Transom end fixings + washers
checkpoint | Fit head and sill angle for glazing support
checkpoint | Flashing and airseals
checkpoint | Check backing rubber correctly positioned
checkpoint | Caps fitted (by glazer)
checkpoint | Cover caps fitted (by glazer)
checkpoint | Trade clean
type | name | values
checklist | Webfordge Checklist - Symonite
checkpoint | PRE-START. Checks to be by both Symonite and main contractor. If necessary give details on separate sheet.
checkpoint | Check framing is sound and secure and is suitable for purpose.
checkpoint | Check framing layout provides adequate fixing points to be able to meet the required fixing centres.
checkpoint | Check joinery for alignent
checkpoint | Check joinery flashing (sill, head etc)
checkpoint | Check building wrap/RAB for defects
checkpoint | Check presence and correct fitment of all other flashings
ALUMINIUM SPANDREL FRAME. Initial checks to be by Symonite Installer. If necessary give details on separate sheet.
checkpoint | Frame installation
checkpoint | frame fixed to curtain wall using M10 304 bolts
checkpoint | Cross braces installed as required
checkpoint | all bolts tightened to required torque specs
checkpoint | frame aligns with curtain wall mullions
checkpoint | frame aligns with curtain wall head and sill above
checkpoint | webforge fixed at correct centres
checkpoint | Fixing/mounting brackets fitted as detailed.
checkpoint | Window head closer/fixing bracket fitted.
checkpoint | Flashing tapes applied as necessary/screws sealed over.
checkpoint | Jamb flashings and fixing brackets fitted.
checkpoint | PANEL INSTALLATION. Initial checks to be by Symonite Installer. If necessary give details on separate sheet.
checkpoint | Primary fixing details. ie fixings through "A" brackets.
checkpoint | Primary fixings are of the approved type (304/316 SS) .
checkpoint | Primary fixings achieve 35mm min. embedment.
checkpoint | Primary fixings do not exceed fixing centres specified.
checkpoint | Plastic H packers do not exceed 30mm total.
checkpoint | Plastic H packers fitted with open end pointing down.
checkpoint | Plastic H packers secured by screw or sealant as necessary
checkpoint | Solid packing (exterior grade) installed where required.
checkpoint | Secondary Fixing details. ie fixings through "B" brackets.
checkpoint | Secondary fixings are of the approved type (S/S Tec screw).
checkpoint | Secondary fixings do not exceed fixing centres specified.
checkpoint | Secondary fixings adjusted to give a flush panel face
checkpoint | Abutment fixings.ie fixings where panels meet surfaces other than panel.
checkpoint | At joinery.
checkpoint | Installation follows detailing given in shop drawings.
checkpoint | At least 15mm sill(tray) to upstand cover.
checkpoint | Fall at sill exceeds minimum (5 degrees).
checkpoint | Flat soakers installed behind all upstand joints.
checkpoint | At least 15mm cover at jambs.
checkpoint | Jambs fixed at specified centres.
checkpoint | Head fixed at specified centres.
checkpoint | At soffits.
checkpoint | Fixing angle fitted to correct inset line where possible.
checkpoint | Specify centres if using covered screws.
checkpoint | At vertical abutments (walls/precast/etc.).
checkpoint | Installation follows detailing given in shop drawings.
checkpoint | Fixing angle fitted to correct inset line where possible.
checkpoint | Specify centres if using covered screws.
checkpoint | At parapets
checkpoint | Installation follows detailing given in shop drawings.
checkpoint | Fall at parapet exceeds minimum (5 degrees).
checkpoint | Fixings at vertical joints are solidly packed.
checkpoint | Opening at rear of parapet is not excessive.
checkpoint | Back edge closer/support bracket fitted.
checkpoint | At bottom edge.
checkpoint | Installation follows detailing given in shop drawings.
checkpoint | Bottom edge closer installed.
checkpoint | Opening at bottom edge is not excessive.
checkpoint | At a deck or roof surface, clearance exceeds 35mm.
checkpoint | At a timber framed wall, cover exceeds 50mm below FFL.
checkpoint | Minimum groaund clearance achieved (100mm above paved surfaces or 175mm above unpaved surfaces).
checkpoint | SEALANT. Initial checks to be by Symonite Installer. If necessary give details on separate sheet.
checkpoint | Panels joints correctly proportioned (width/depth ratio).
checkpoint | Panel joints are have been cleaned with SikaCleaner 205 and allowed to flash off for more than 15mins but no more than 6 hrs.
checkpoint | Abutment joints to porous materials have been primed with SikaPrimer-3N and allowed to flash off for more than 30 mins but not more than 8 hrs.
checkpoint | PEF backing rod installed.
checkpoint | Backing rod fully pushed back in the joint
checkpoint | All joints masked.
checkpoint | Sealant applied in accordance with manufacturers spec.
checkpoint | Ambient and substrate temperature is 5-40 degrees
checkpoint | Sealant tooled off to given a flat or slightly concave finish.
checkpoint | Visual inspection 24hrs after application.
checkpoint | Sealant type applied -
checkpoint | Sealant colour -
checkpoint | CLEAN UP. Initial checks to be by Symonite Installer. If necessary give details on separate sheet.
checkpoint | All masking removed and panels peeled of protective film.
checkpoint | All excess sealant and other residue removed.
checkpoint | All drainage holes unobstructed.
checkpoint | Grommets installed in drain holes as required.
checkpoint | All rubbish removed from working area.
checkpoint | All rubbish disposed of as site instructions.
checkpoint | FINAL. Checks to be by Symonite PM and MC. If necessary give details on separate sheet.
checkpoint | Panel layout corresponds with Symonite shop drawings.
checkpoint | Panel colours correspond with Symonite shop drawings.
checkpoint | Check panels for visible defects.
checkpoint | Check panel alignment (stepping etc.).
checkpoint | Check detailing at window/door heads.
checkpoint | Check detailing at window/door sills.
checkpoint | Check detailing at parapet.
checkpoint | Check detailing at bottom edge.
checkpoint | Visually inspect seals.
checkpoint | Check all areas for unfinished clean-up.
checkpoint | SIGN OFF. Checks to be by Symonite PM and MC. If necessary give details on separate sheet.
checkpoint | All quality assurance issues resolved in this area.
checkpoint | This area is deemed to be complete and satisfactory.
type | name
checklist | Reynodual - Symonite
checkpoint | TBC
checkpoint | TBC
checkpoint | TBC
checkpoint | TBC
checkpoint | TBC
type | name | values
checklist | Perforated & Louvres- Symonite
checkpoint | TBC
type | name | values
checklist | Canopy
checkpoint | TBC

## Checklists
type | name | values
checklist | Job Details
checkpoint | Site Info
label | Site Name & Address
input
label | Main Contractor Details
input
label | Project Manager
input
label | Site Manager
input
checkpoint | Latest Drawings
checkpoint | Scope of Works Attached
checkpoint | Additional Pre-Start Docs
type | name | values
checklist | Safety
checkpoint | Site Info
label | Site Name & Address
input
label | Main Contractor - Safety Contact
input
label | Site Specific Safety Requirements
input
checkpoint | SSSP / JSEA Docs
checkpoint | Additional Pre-Start Docs
type | name | values
checklist | Site Observations
label | Observation Details
input
checkpoint | Site Observation Closed
type | name | values
checklist | Structural Curtain Walls
sections | Curtain Wall External Checklist
checkpoint | Setout / grids/ datum lines (refer to Survey mark/Setting out) MUST ATTACHED SURVEY DRAWING SHOWING LEVELS AND SLAB EDGES
checkpoint | Opening acceptance as per drawings MUST ADD SURVEY DRAWING
checkpoint | Secondary Bracket Installed, Bolt torque Mark with paint marker when toqued(refer to SD)
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Install subsill /Jamb/ Deadload blocks/ splicers / soakers
checkpoint | Splices,Top Angle fitted & soakers sealed - PHOTO REQUIRED
checkpoint | All Fixings over sealed PHOTO REQUIRED
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Install backer rod - PHOTO REQUIRED
checkpoint | Complete airseal within application time allowed
checkpoint | Install panels as per drawings -PHOTO REQUIRED
checkpoint | Install glazing rubber with correct orientation/ no breaks and full height between panel and frame
checkpoint | External flashings / weather seals installed and SEALED if drawing indicates
sections | Curtain Wall Internal Checklist
checkpoint | Airseal and internal flashings
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Panel locked off position as per module
checkpoint | Crusifix sealing done on panel to panel cross joints?
sections | Internal fire seal and trunking
checkpoint | PGI Galv. Z support clips installed
checkpoint | PGI fire insulation installed
checkpoint | Trims and closers (smoke seal)
checkpoint | Blind Box installed
checkpoint | Sill Trunking Installed
checkpoint | Vertical Trunking Installed
sections | Fins
checkpoint | Horizontal & Vertical Fins Installed
checkpoint | Fin bolts tight and locked off as per drawings
sections | Glass
Checkpoint | Glass installed and no damaged glass
sections | Wight Aluminium sign off
checkpoint | Trade clean / protected
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Skylight & Canopy Installation Checklist
checkpoint | Steel structure acceptance
checkpoint | Install glazing channels
checkpoint | Install glazing bars (seal splice joint)
checkpoint | Install transom (seal joint to top of bar / end of transom)
checkpoint | Transom end fixings + washers
checkpoint | Fit head and sill angle for glazing support
checkpoint | Flashing and air seals
checkpoint | Check backing rubber correctly positioned
checkpoint | Caps fitted (by glazer)
checkpoint | Cover caps fitted (by glazer)
checkpoint | Trade clean
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Frameless Glass Spider fitting Checklist
checkpoint | Survey Setout Marking on the floor as per plan reference
checkpoint | Check datum points
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be)
checkpoint | Install U-channel Perimeter
checkpoint | Check the packer (shims) must be in accurate level.
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Install Glass and the Spider fitting - tighten spider bolt
checkpoint | Check the reference line top of the panel
checkpoint | Sealant application
checkpoint | Trade clean
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Louvre's
checkpoint | Area Acceptable, All elements approved
checkpoint | Check survey of heights
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there is any damage
checkpoint | Fixing is accordance with the Shop drawing
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Frames installed in correct position & level
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Airseal is accordance to the shop drawing LIST SIZE in mm PHOTO REQUIRED
label | Enter airseal size in mm here
sections
checkpoint | All visable fixings touched up with dabstick/paint
checkpoint | Trade clean / protected
Check point | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Architectural Slider / Hinge Door
sections | Joinery Install
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Check the dimentions & Level (ADD survey drawings in here if not as per drawings)
checkpoint | Check rebate is correct as per drawings PHOTO REQUIRED
label | Insert rebate dimentions here (Depth x width)
input
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there any damage
checkpoint | Installed into the position with approved fixing
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Application of the Airseal Sealant w/ PE rod complete PHOTO'S REQUIRED
label | Enter average airseal size in mm here
input
sections | Sliders
checkpoint | Slider & fixed panels to install and slide smothly.
checkpoint | Ensure All Hardware installed and working
checkpoint | Ensure all Mohair, seals, infills & plastic caps installed.
checkpoint | Trade clean / protected
checkpoint | All infils installed and corners closed and tight/ no damage or scratched
checkpoint | All glazing beads installed and meeting at corners
checkpoint | Rain shield and flashings installed and sealed as per drawings
checkpoint | All visable fixings touched up with dabstick/paint
sections | Hinge Doors
checkpoint | Install the door into the position also the thresholds
checkpoint | All Door seals installed and complete
checkpoint | All Harware installed and in working order
checkpoint | Door to floor clearance as per drawings
checkpoint | Rain shield and flashings installed and sealed as per drawings
checkpoint | All visable fixings touched up with dabstick/paint
checkpoint | Trade clean / protected
sections | Glass
checkpoint | Glass installed and rubbered off correctly no glass damage PHOTO REQUIRED
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Punch Windows (site glazed)
sections | Joinery Install
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Check the dimentions & Level (ADD survey drawings in here if not as per drawings)
checkpoint | Fixing angle fitted and level as per drawings (check that fixings are as specified) PHOTO REQUIRED
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there is any damage
checkpoint | Fixing in accordance with the Shop drawing
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Frames installed in correct position & level
checkpoint | Ensure no packers visible out of line where airseal is to be installed.
checkpoint | Airseal is accordance to the shop drawing LIST SIZE in mm PHOTO REQUIRED
label | Enter airseal size in mm here
input
checkpoint | All infils installed and corners closed and tight/ no damage or scratched PHOTO REQUIRED
checkpoint | All glazing beads installed and meeting at corners PHOTO REQUIRED
checkpoint | Rain shield and flashings installed and sealed as per drawings PHOTO REQUIRED
checkpoint | All visable fixings touched up with dabstick/paint PHOTO REQUIRED
checkpoint | Ensure all Hardware, seals installed and in working order.
checkpoint | Trade clean / protected
sections | Glass
checkpoint | Glass installed and rubbered off correctly no glass damage PHOTO REQUIRED
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Punch Windows (pre-glazed)
sections | Joinery Install
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Check the dimentions & Level (ADD survey drawings in here if not as per drawings)
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there is any damage
checkpoint | Fixing is accordance with the Shop drawing
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Frames installed in correct position & level
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Airseal is accordance to the shop drawing LIST SIZE in mm PHOTO REQUIRED
label | Enter airseal size in mm here
input
checkpoint | All infils installed and corners closed and tight/ no damage or scratched PHOTO REQUIRED
checkpoint | Rain shield and flashings installed and sealed as per drawings PHOTO REQUIRED
checkpoint | All visable fixings touched up with dabstick/paint PHOTO REQUIRED
checkpoint | Ensure all Hardware, seals installed and in working order.
checkpoint | Trade clean / protected
sections | Glass
checkpoint | Glass installed and rubbered off correctly no glass damage PHOTO REQUIRED
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Flush Glaze Shopfront Frame Installation
sections | Joinery Install
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Check the dimentions & Level (ADD survey drawings in here if not as per drawings)
checkpoint | Check rebate is correct as per drawings PHOTO REQUIRED
label | Insert rebate dimentions here (Depth x width)
input
checkpoint | Fixing angle fitted and level as per drawings (check that fixings are as specified) PHOTO REQUIRED
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there is any damage
checkpoint | Install the frame perimeter into the position with approved fixing
checkpoint | Install subsill / Deadload blocks/ splicers / soakers
checkpoint | Splices,Top Angle fitted & soakers sealed
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Ensure no packers visable out of line where airseal is to be installed.
checkpoint | Application of the Airseal Sealant w/ PE rod complete PHOTO'S REQUIRED
label | Enter average airseal size in mm here
input
checkpoint | Install frames
checkpoint | Glazing rubber installed around frame and Unit. PHOTO REQUIRED
checkpoint | Install fixings to fixoff frames as per drawings PHOTO REQUIRED
checkpoint | Rain shield and flashings installed and sealed as per drawings PHOTO REQUIRED
checkpoint | All Glazing beads installed and meeting correctly at corners
sections | Manual Doors
checkpoint | Install the door into the position also the thresholds
checkpoint | All Door seals installed and complete
checkpoint | All Harware installed and in working order
sections | Glass
checkpoint | Glass installed and rubbered off correctly no glass damage PHOTO REQUIRED
sections | Auto Doors
checkpoint | Supplier Install the door into the position
checkpoint | All Door seals installed and complete
checkpoint | Door to floor clearance as per drawings PHOTO REQUIRED
Hold point | Auto door commisioned
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff
type | name | values
checklist | Flush glaze curtain wall frame installation
sections | Joinery Install
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Setout / grids/ datum lines (refer to Survey mark/Set out by main contractor)
checkpoint | Check rebate is correct as per drawings
label | Insert rebate dimentions here (Depth x width) IF REQUIRED
input
checkpoint | Secondary Bracket Installed, IF REQUIRED Bolt torque Mark with paint marker when toqued(refer to SD)
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Check the joinery if there is any damage
checkpoint | Install the frame perimeter into the position with approved fixing
checkpoint | Install subsill / Deadload blocks/ splicers / soakers
checkpoint | Splices,Top Angle fitted & soakers sealed
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Ensure no packers visible out of line where airseal is to be installed.
checkpoint | Application of the Airseal Sealant w/ PE rod complete PHOTO'S REQUIRED
label | Enter average airseal size in mm here
input
checkpoint | Install frames
checkpoint | Glazing rubber installed around frame and Unit. PHOTO REQUIRED
checkpoint | Install fixings to fixoff frames as per drawings
checkpoint | Rain shield and flashings installed and sealed as per drawings PHOTO REQUIRED
checkpoint | All infils installed and corners closed and tight/ no damage or scratched PHOTO REQUIRED
checkpoint | All visible fixings touched up with dabstick/paint PHOTO REQUIRED
checkpoint | Ensure all Hardware, seals installed and in working order.
checkpoint | All Glazing beads installed and meeting correctly at corners
sections | Glass
checkpoint | Glass installed and rubbered off correctly no glass damage PHOTO REQUIRED
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff

## List
checklist | Job Details
checklist | Safety
checklist | Site Observations
checklist | Structural Curtain Walls
checklist | Skylight & Canopy Installation Checklist
checklist | Frameless Glass Spider fitting Checklist
checklist | Louvre's
checklist | Architectural Slider
checklist | Punch windows site glazed
checklist | Punch windows pre-glazed
checklist | Flush glaze Shopfront frame installation
checklist | Flush glaze curtain wall frame installation