## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 9_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 9_Inspection | 045f0dcd-229b-4cd1-9206-394e1572d40d
checkpoint-group |  |  | section | Station 9_3rd Coat Painting Plasterboard - Wall & Bathroom Ceiling_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 3rd coat internal painting as per approved plans and manufacturer specifications
text | e6050187-8d2c-54d3-93b1-a2fea635cc95 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: Contractor
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 9 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | c5da8004-d6d7-5e29-8a9b-e9fe853dccef |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 9_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 9_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 9_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 4_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 4_Inspection | 0f2b0ae8-1ca7-49e1-86f6-21c2a00caad9
checkpoint-group |  |  | section | Station 4 Inspections
checkpoint-group |  |  | section | Station 4_Electrical & Mechanical Team_First Fix Electrical & Mechanical_Module B
checkpoint-status |  |  | checkpoint | Check and review as per Electrical and Mechanical Services Plan and provide photo
checkpoint-status |  |  | checkpoint | Ostendo Station 4 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install earth and neutral wiring as per electrical plan.
checkpoint-status |  |  | checkpoint | Install ducting fitout to bulkhead area, as per mechanical plan.
checkpoint-status |  |  | checkpoint | On completion of works, an overview photo is required
text | 8ca1ffdf-990f-59da-b8c5-99befdf7020f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold Point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 4_Windows and Ranch Slider Doors_Module A
checkpoint-status |  |  | checkpoint | Check and review as per approved manufacturer plans and specifications, photo required
checkpoint-status |  |  | checkpoint | Ostendo Station 4 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install all windows as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint-status |  |  | checkpoint | Install all window backing rod & air-seal as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint-status |  |  | checkpoint | Install all Ranch-slider as per Approved Shop Drawings, fixings as per PS1 by Engineer, Approved Shop Drawings Plans & specifications.
checkpoint-status |  |  | checkpoint | On completion at each stage of installation, (PF backing rod, sealant air-seal), overview photo required for Window and Ranch Slider
text | 27ecd7db-5845-5a49-8187-0b9ba78e4673 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold Point: Team Leader
holdpoint |  |  | signoff | Hold point: photo required and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 4_Fitout Team_Internal Doors / Wardrobe Doors & Architraves/ Skirting_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved manufacturer plans and specifications
checkpoint-status |  |  | checkpoint | Ostendo Station 4 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install all internal doors and wardrobe doors, as per manufacturer plan
checkpoint-status |  |  | checkpoint | Install all architraves and skirting where required, as per manufacturer plan
text | 5f8e1590-b943-5389-8637-b7ccec55133b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 4 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | bdc713bd-6da6-5a72-b4f9-52f03601164a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 4_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 4_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 4_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
folder-progress |  | folder-progress has incorrect meta.stepType checklist-sectioned | checklist | EGM_Ver1.0_19.12.23_ Station 10_Inspection |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Station 10_Inspection | 2b288fdf-838a-420b-a862-a4535b65c01b
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Element Assembly 4_Electrical & Mechanical_Ceiling Cassette / CE _Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Element Assembly 4_Electrical & Mechanical_Ceiling Cassette / CE1_Inspection | 2b37924e-bd85-41df-9cda-cbe8da44560c
checkpoint-group |  |  | section | Element Assembly 4_Electrical & Mechanical Team_Pre-wiring and Pre-ducting_Module A or B
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing Electrical and mechanical service plan and picture required.
checkpoint-status |  |  | checkpoint | Install and secure electrical cable bundle as per electrical service plan
checkpoint-status |  |  | checkpoint | Ostendo - Element material Scan, completed.
text | 61e4a371-f0b8-5f3d-8c13-3f720dff4df7 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: overview photo required and Signoff by Lead
holdpoint |  |  | signoff | Hold point: Signoff by Electrical & Mechanical Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 4 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 23511238-4856-53b7-a210-8307dc335a0e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 4_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 4_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 4_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.4_23.11.23_Element Assembly 1_Wall Structure - EW / MW / CW / TW_Inspection |  |  |  |  | Yes | EGM_Ver1.4_23.11.23_Element Assembly 1_Wall Structure - EW / MW / CW / TW_Inspection | 2d703f0d-15bc-4328-a80c-c83f8415becb
checkpoint-group |  |  | section | Element Assembly 1_Wall Structural Framing and Preline Inspections
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per Approved Shop Drawing Plan
text | f991c2f9-4fcb-5718-ab8e-dffd8f38d70b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 4a194ad9-386c-5d9f-afcb-d876d230685d |  | textbox | Diagonal #1:
text | 5acfecaa-3e67-558f-bbe3-636dca2cb479 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted, and photo required.
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
text | 710a3263-e84a-5c88-add1-43124b80077d |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_Structural Frame
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install bracing and fixing as per Approved Shop Drawing Plan
text | 5c659c36-d425-59d9-a6b6-59f08e667acb |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals, and photo required.
text | f52857b5-419a-571c-bce4-9942b0eab41e |  | textbox | Diagonal #1:
text | 398960ea-64f9-5e35-b299-483ca3a3ee5e |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed bracing as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted
text | e5786065-0e1f-5730-8475-3b42d8b73e9c |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_Ply Bracing Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per manufacturer plan, and photo required.
text | 448b37e5-df08-5ff6-8fa7-9ed8da6e5e05 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
text | c111aa25-d7e1-54b3-a70f-76a6b1f32e51 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Overview photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per Approved Shop Drawing Plan
text | 68ebd560-4ffa-5049-a5be-557942e3127b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify Wet Area GIB plasterboard is installed as per Approved Shop Drawings and Specification, and photo required.
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
text | bdf0b88d-1abd-55d4-a90b-77bba998bead |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | f10e9a0c-ca81-536c-b421-5fde238b8adf |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.1_22.11.23_Element Assembly 2_Frame Structure_Floor Cassette / F _Inspection |  |  |  |  | Yes | EGM_Ver1.1_22.11.23_Element Assembly 2_Frame Structure_Floor Cassette / F1_Inspection | 459dc9e2-af5b-45f9-96fb-d21eef63aa47
checkpoint-group |  |  | section | Element Assembly 2_Structural Floor Cassette Frame and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install all floor framing elements and fixings as per Approved Shop Drawing Plan
text | 6ed37e2c-6330-5284-b7f4-5b49b209bedf |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | a4883143-1537-5198-b676-7a7c6a7f5297 |  | textbox | Diagonal #1:
text | 88649111-ff6c-55f7-bf88-01f52c5b6a78 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 2_Floor Ply Brace Sheeting
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install floor sheeting and fixing as per Approved Shop Drawing Plan and Specification, photo required
text | bdcd89d8-4ca0-5e62-a7a3-3cb3b2036d99 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | e4b868e7-24c4-5f01-9b70-521fb49315f7 |  | textbox | Diagonal #1:
text | 7fe4cdc1-e268-558b-8a6e-b224599b38bb |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 2 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 2f71bfbe-0c91-57d8-94c5-3ba77b06a359 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 2_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 2_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 2_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for (MV) Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_19.12.23_ Notified NCR_QA RFI |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Notified NCR_QA RFI | 4bbec9b1-107f-4acc-959e-332145bdda55
checkpoint-group |  |  | section | Notified NCR_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 13_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 13_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_19.12.23_ Station 13_Inspection |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Station 13_Inspection | 4e87ed45-cf88-47d9-954f-969c93841d0d
checkpoint-group |  |  | section | Station 13/ Yard_Packaging, Lifting & Shipment_Module A or B
checkpoint-group |  |  | section | Station 13_Fitout Team_Items to be included in Module for onsite_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawings Plans, specifications and as per list
checkpoint-status |  |  | checkpoint | Ostendo Station 13 Module material scan, completed
checkpoint-status |  |  | checkpoint | Check all items as per list included in Module
checkpoint-status |  |  | checkpoint | Check all items are secured in place
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 51c62570-aa49-599d-98ee-4a58b6b28004 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13_Fitout Team_Rothoblaas/ Coupling_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawings Plans, specifications and as per list
checkpoint-status |  |  | checkpoint | Ostendo Station 13 Module material scan, completed
checkpoint-status |  |  | checkpoint | Check all Rothoblaas/ coupling are installed in the correct location as per Module Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 0b978b30-184f-5670-bd45-dbfbb1e80b50 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13_Internal Fixtures and Fittings Packaging_Module A or B
checkpoint-status |  |  | checkpoint | Toilet: Cistern fixed by using blue 14 day tape
checkpoint-status |  |  | checkpoint | Shower: Shower head taped in place to shower rail
checkpoint-status |  |  | checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using blue 14 day tape.
checkpoint-status |  |  | checkpoint | Bathroom: Bathroom Shower curtain is supplied and protected
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | ee1a8bdb-b3b0-551a-90e9-b31da0d598d4 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13_Packaging_External Protective Cover_Module A or B
checkpoint-status |  |  | checkpoint | Use protective film to cover a module completely
checkpoint-status |  |  | checkpoint | Ostendo Station 13 Module material scan, completed
checkpoint-status |  |  | checkpoint | Use heat Gun to seal the protective film.
text | 7bd69aca-69fe-551f-a67f-fbc0a48d68e7 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure there are no gaps in the film
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13_Lifting and Loading_Module A or B
checkpoint-status |  |  | checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle
checkpoint-status |  |  | checkpoint | Tie the module to the Transport Vehicle, using strops or with the equipment attached to the Vehicle is by Specialist Transport Operator/ Driver
checkpoint-status |  |  | checkpoint | Make sure the module is correctly sitting on the Transport vehicles is by Specialist Transport Operator/ Driver
checkpoint-status |  |  | checkpoint | Make sure the Module has been secured with the correct ties is by Specialist Transport Operator/ Driver
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 7de9e608-c872-57f6-a9a9-ea507446f534 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13/ Yard_Shipment_Module A or B
checkpoint-status |  |  | checkpoint | A Specialised Transportation Vehicle will be used to transport the module to Site
text | 329b4fe2-7b8d-525a-8b63-1bdf6a9d89a4 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check if the Transport Company meet the approved transport criteria
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 64322095-cc8f-574d-8669-61079a06a66e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 13_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 13_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 13_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
folder-progress |  | folder-progress has incorrect meta.stepType checklist-sectioned | checklist | EGM_Ver1.0_19.12.23_ Station 11_Inspection |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Station 11_Inspection | 4f9aefc0-bafc-46fe-aca5-a93317c87ca0
checklist-sectioned |  |  | checklist | EGM_Ver1.0_19.12.23_ Document/ Works_Records |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Document/ Works_Records | 5f8b2363-2f34-415e-aab8-c338907e12b4
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 0dc7d2d1-3358-5853-881f-cd621699d35a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Document/ Works Record_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | abe3b47c-fb2d-5604-92c2-e0b82c019602 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Correct Record uploaded
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Element Assembly 3_Frame Structure_Ceiling Cassette / CE _Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Element Assembly 3_Frame Structure_Ceiling Cassette / CE1_Inspection | 61289543-f8a3-4180-95c2-7d27403a7270
checkpoint-group |  |  | section | Element Assembly 3_Structural Framing and Pre-line Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install all ceiling framing elements and fixings as per Approved Shop Drawing Plan
text | eb6f50d4-c156-5b19-a81b-f11f9bab973a |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 2a145af7-4e0c-5605-99da-b64374643ab1 |  | textbox | Diagonal #1:
text | 25fafe9b-6242-5489-bf3b-ed28c0dc8438 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify structural fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step
checkpoint-group |  |  | section | Element Assembly 3_Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Element material Scan, completed.
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Approved Shop Drawing Plan
text | ab17dfe0-2984-536e-9dbd-9cb5fdc48b03 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 3_Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Element material Scan, completed.
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per Approved Shop Drawing Plan
text | fac8df03-76ec-51a0-8c32-d9cdc0034d35 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 3_Ply Sheet Bracing (where applicable Level 2)
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Element material Scan, completed.
checkpoint-status |  |  | checkpoint | Install sheeting bracing and fixing as per Approved Shop Drawing Plan
text | 12a47b2a-9f22-5c00-aa74-d58df0aaf4ec |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | fe4aac64-f0dc-52cf-9032-7abb259f6ffa |  | textbox | Diagonal #1:
text | 901d7ed0-41ed-5578-9429-0ad21885ca18 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Approved Shop Drawing Plan, and photo required.
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 3 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 09102c91-a0ca-5f69-a7ea-e8d68da72cec |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 3_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 3_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 3_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.2_28.11.23_Podium Inspection |  |  |  |  | Yes | EGM_Ver1.2_28.11.23_Podium Inspection | 64989a1d-21fe-470b-97a4-8657cb4ea36e
checkpoint-group |  |  | section | Podium_ Module Assembly Team_Structure connection/ Fixing Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Podium Module material scan, completed
checkpoint-status |  |  | checkpoint | Locate and position floor cassette on the podium
text | fb04039e-902b-59cd-8029-256ab1096091 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per Approved Shop Drawing. Support/Prop necessary.
text | 13161516-69ed-5a6f-b283-9ef8677b40dc |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per Approved Shop Drawing.
checkpoint-status |  |  | checkpoint | Check and verify all structural nail fixings as per Approved Shop Drawing and photos required.
checkpoint-status |  |  | checkpoint | Check and verify all structural screw fixings as per Approved Shop Drawing and photos required.
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted.
text | 294b4a16-443f-5317-be0d-8003051c4f85 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Podium_ Module Assembly _Passive Fire Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing
checkpoint-status |  |  | checkpoint | Fire seal/acoustic sealant installed as per approved plan and manufacturer specification, all edges to wall, floor and ceiling. Part of Passive Fire System and photos required.
checkpoint-status |  |  | checkpoint | Ostendo Podium Module material scan, completed
text | da7ea39c-c9a0-593f-8d4c-c6c4ae19f2ae |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Podium_Module Assembly - Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Podium Module material scan, completed
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per manufacturer plan
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per manufacturer plan and photos required.
text | 656ff2b3-fbc2-5a99-be7f-748c18a5f10a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Podium_ GIB Stopping Contractor Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing
checkpoint-status |  |  | checkpoint | Ostendo Podium Module material scan, completed
checkpoint-status |  |  | checkpoint | Install 1st coat of stopping to ceiling and external facing internal wall, as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | a174524d-0e53-5fde-b635-0f46784b8673 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review and Signoff by Contractor Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Podium Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 1e161c7c-1570-5ec7-815f-ae50a2a810fa |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Podium Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Podium_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Podium_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Podium_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.1_22.11.23_Offsite manufacturer Weymouth Rd ITP |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Offsite manufacturer Weymouth Rd ITP | 6629f8c9-6e25-455c-8f63-9fdf4b430645
checkpoint-group |  |  | section | 1 - ITP Review and Approval Inspection
checkpoint-status |  |  | checkpoint | ITP reviewed - Consentium
checkpoint-status |  |  | checkpoint | BC Approved
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Final Signoff by Quality & Compliance Manager
checkpoint-group |  |  | section | 2 - Preparation
checkpoint-status |  |  | checkpoint | Drawings review and approval
checkpoint-status |  |  | checkpoint | Project specification review and approval
checkpoint-status |  |  | checkpoint | Equipment calibration
checkpoint-status |  |  | checkpoint | Personnel certifications & Licenses
checkpoint-status |  |  | checkpoint | Staff training
checkpoint-status |  |  | checkpoint | manufacturer record and inspection report template
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Final Review Signoff by Quality Assurance Manager
checkpoint-group |  |  | section | 3 - Material Management
checkpoint-status |  |  | checkpoint | Material list review and approval
checkpoint-status |  |  | checkpoint | Incoming material check
checkpoint-status |  |  | checkpoint | Material storage
checkpoint-status |  |  | checkpoint | Material Handling and traceability
checkpoint-status |  |  | checkpoint | Hold point: Inventory Manager
holdpoint |  |  | signoff | Hold point: Final Review Signoff by Inventory Manager
checkpoint-group |  |  | section | 4 - manufacturer
checkpoint-status |  |  | checkpoint | 4.1 - Floor Cassette
boolean | d74909fb-393b-5f9f-a870-071b7d31ab9a |  | tickbox | Structural Framing & Fixings
boolean | bdbbb468-b9e0-5397-a1f7-a8f250c4a6bf |  | tickbox | Floor sheeting
checkpoint-status |  |  | checkpoint | 4.2 - External Wall / Marriage Wall / Intertenancy Wall / Carriage Wall
boolean | 945ed89f-fc2d-5378-8c37-398d909962cf |  | tickbox | Structural Framing & Fixings
boolean | 8f429447-733d-56f5-b461-5dac04419c77 |  | tickbox | Structural Sheet Bracing
boolean | 9860cef6-155d-5799-aa05-c83206943afd |  | tickbox | Fire Lining 1st Layer
boolean | 687b16a3-49f1-5646-92c9-0b507903a45b |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.3 - Internal wall
boolean | 34efe23f-4ea9-500e-afab-62bd478f1ce5 |  | tickbox | Structural Framing & Fixings
boolean | 72e2bc3c-bc08-5654-984d-add807427657 |  | tickbox | Standard/Single Layer Gib board
checkpoint-status |  |  | checkpoint | 4.4 - Ceiling Cassette
boolean | 48764700-0f18-54c4-a994-5cfd1aa748dd |  | tickbox | Structural Framing & Fixings
boolean | 2b1b744d-3483-5360-b066-e04467bb1029 |  | tickbox | Structural Sheet Bracing as required
boolean | e3c8f5e5-c6b5-55ab-b0a7-edd1c264c9b5 |  | tickbox | Fire Lining 1st Layer
boolean | 9a100d98-dbfb-59a0-9eb8-ae696d7d6ebf |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.5 - Module Assembly
boolean | f7f4b62d-0547-55c1-ace5-419a77436146 |  | tickbox | Module Assembly
boolean | 840d96b1-58d0-5da5-be9a-492076d9a333 |  | tickbox | Structural Fixing & Services as per manufacturer plan
boolean | 7bfe6a16-921c-5e0c-99d7-393dd2463f69 |  | tickbox | GIB Fire Seal Floor & Ceiling Cassette
checkpoint-status |  |  | checkpoint | 4.6 - Document Collection
boolean | 9c701cb7-e346-57ba-8928-2d1b60e27d92 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: LBP Team Leader
checkpoint-status |  |  | checkpoint | Hold point: LBP Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by LBP Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 5 - Exterior Work
checkpoint-no-status |  |  | checkpoint | Exterior Work
boolean | 464f0443-0a46-5b8b-b42f-2d9588b5f137 |  | tickbox | Windows, Doors & Entry Doors (Note: Excluding Doors & Entry Doors due to Onsite Connection required BC3)
boolean | 786ea236-960c-52ce-a587-865008ea1749 |  | tickbox | Insulation, RAB, Flashing, and Tapes
checkpoint-status |  |  | checkpoint | 5.1 - Document Collection
boolean | 7ead2d4a-fbe4-5a97-967f-1f4358c4ddd6 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: LBP Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by LBP Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 6 - Interior Fit Out Work
checkpoint-no-status |  |  | checkpoint | Interior Fit Out Work
boolean | 760b9748-ba10-5d80-8f19-f913862bf27e |  | tickbox | Mechanical ducts and ventilation (Note: Excluding onsite connection BC3)
boolean | e67a0e1b-e793-5607-8b8c-c6b77521bc48 |  | tickbox | Ceiling (Note: Excluding onsite connection BC3)
boolean | 45c47bb7-049a-555d-a180-603db0118ad5 |  | tickbox | False ceiling and bulkheads
boolean | 8ae4fe57-7566-5e9e-bc3d-c9b8f9ac4ab7 |  | tickbox | Floor (Note: Excluding onsite connection BC3)
boolean | 3c210a79-c43a-582e-853b-1abc26e22143 |  | tickbox | Acoustic floor (Note: Excluding onsite connection BC3)
boolean | 3c19e280-3535-57d8-a475-d5107579719f |  | tickbox | Floor coverings - Vinyl only (Note: Excluding onsite carpet BC3)
boolean | 0c6525a6-1efb-52d1-9d09-7139a29b426e |  | tickbox | Gib stopping (Note: Excluding onsite connection areas BC3)
boolean | c93ac2d8-bd18-5b7b-b8a7-f07626e7c200 |  | tickbox | Internal Door and trims (Note: Excluding onsite connection areas BC3)
boolean | fc2c68a1-df4d-5a40-9831-787f6763b8bd |  | tickbox | Painting (Note: Excluding onsite connection areas BC3)
boolean | cce46dd4-99aa-5d72-82e7-9e4338696930 |  | tickbox | Kitchen and bathroom joinery install
boolean | c9e19033-4ae6-5c21-8b00-382349bf1826 |  | tickbox | Hardware (Note: Final onsite works)
checkpoint-status |  |  | checkpoint | 6.1 - Document Collection
boolean | 0678759b-71e5-5e06-91fb-0d5e8ffa3891 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: Hardware Contractor
holdpoint |  |  | signoff | Hold point: Review Signoff by Hardware Contractor
checkpoint-status |  |  | checkpoint | Hold point: LBP Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by LBP Team Leader
checkpoint-status |  |  | checkpoint | Hold point: LBP Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by LBP Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 7 - Electrical & Mechanical
checkpoint-no-status |  |  | checkpoint | Electrical & Mechanical
boolean | b5f1f239-cf72-506b-bce9-b39f39cdf16b |  | tickbox | Ceiling Cassette
boolean | 8bb10550-9dcc-59e0-9384-30ad143b402d |  | tickbox | First fix electrical and mechanical
boolean | 0ea4a0e0-483b-5c85-b7c8-7501b9ae0d9d |  | tickbox | External wall & IT wall
boolean | d454d2bd-469a-55fd-9c35-58fa9b6cbf70 |  | tickbox | Internal Wall
boolean | 6e781bc6-6510-5c34-a519-86cb3acf1a40 |  | tickbox | Module assembly
boolean | ae79e2c1-150e-5ae6-8b23-377eb2d68817 |  | tickbox | Second fix electrical and mechanical
checkpoint-status |  |  | checkpoint | Testing & Inspections
boolean | 84dbcd21-6909-5f0c-ad4c-c91c52a49457 |  | tickbox | Visual Inspection (Note: Final Testing & Connect onsite BC3)
boolean | 6d118045-6781-5873-bda3-50418a6bb3b0 |  | tickbox | Earth Resistance and Continuity Inspection (Note: Final Testing & connect onsite BC3)
boolean | 9c3f89f5-898f-5bd7-981c-d0c51c42aa2d |  | tickbox | Insulation Resistance Inspection (Note: Final Testing & connect onsite BC3)
boolean | 392e26f3-b097-52a6-b4ed-1af64620221b |  | tickbox | Polarity and Phase Inspection (Note: Final Testing & connect onsite BC3)
boolean | aec2c6ff-f867-5ef2-8d43-af43090a13e0 |  | tickbox | Correct Circuit connection (Note: Final Testing & connect onsite BC3)
boolean | 9feb6243-6f6e-5740-bf74-fa2d66ca8755 |  | tickbox | Final Functional inspection (Note: Final Testing & connect onsite BC3)
checkpoint-status |  |  | checkpoint | 7.1 - Document Collection
boolean | 985da3c3-eb2c-5443-8414-c7df63bd245a |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: Electrical Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by Electrical Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 8 - Hydraulics
checkpoint-no-status |  |  | checkpoint | Hydraulics
boolean | 82a70239-cd81-5f2e-8fe2-8a3462a36e94 |  | tickbox | Floor Cassette
boolean | 8cdcba13-b7c8-5efe-920c-d8330d881718 |  | tickbox | Floor Plumbing and Drainage
boolean | 36db5292-8716-5b95-bbff-475e901f9f7c |  | tickbox | First test - Air Drainage Test and Plumbing Water Test
boolean | 3b7a6e66-ed6d-54c3-bd3c-eb3dae27e4bb |  | tickbox | Module Assembly
boolean | 3680f5a5-09f0-580b-ba08-98f2958b5ec8 |  | tickbox | First fix plumbing and drainage
boolean | 8becec90-5573-5245-b9d7-e8257621e180 |  | tickbox | Second fix plumbing and drainage
boolean | 952d40a5-22c8-5cf9-9a3e-55ba444e7815 |  | tickbox | Second test - Plumbing Water Test
checkpoint-status |  |  | checkpoint | Testing & Inspections
boolean | 32bbbd0f-7564-50a4-b1ec-718a6aad25b0 |  | tickbox | Water test
boolean | 2db92413-50b0-58ee-bb15-c18c39e9c0a8 |  | tickbox | Air test
boolean | e0265f49-4ce1-5240-9698-4b5e48e5258b |  | tickbox | Visual Inspection
checkpoint-status |  |  | checkpoint | 8.1 - Document Collection
boolean | 392ff4cd-376e-54a0-9ac1-be3c79a4f9f7 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: Plumbing & Drainage Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by Plumbing & Drainage Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 9 - Fire Protection
checkpoint-no-status |  |  | checkpoint | Fire Protection
boolean | 04363366-1b44-5e1d-99e2-7b8a17965563 |  | tickbox | Module Assembly
boolean | 17fc2613-97a3-5833-b64f-28566e359c63 |  | tickbox | First fix passive fire
boolean | 4d69b331-01af-5083-a179-362ab54b0e66 |  | tickbox | Internal wall & Intertenancy wall & Marriage wall
boolean | 1a9bfd19-0112-50e2-9c31-5f5dbfaa1e73 |  | tickbox | External wall & Intertenancy wall & Marriage wall
boolean | 2f264298-0996-5f56-85dd-875f6a71f788 |  | tickbox | Ceiling Cassette (Note: Final fitoff BC3)
boolean | 88d20c42-f6ab-57c4-9548-4db8c1caeab5 |  | tickbox | Second fix passive fire
checkpoint-status |  |  | checkpoint | Testing & Inspections
boolean | 6f5d9caa-a82f-57a8-b926-5b956aed0286 |  | tickbox | Visual inspection and tag each penetration
checkpoint-status |  |  | checkpoint | 9.1 - Document Collection
boolean | 2ed9e221-edeb-50dd-83c7-3466e09178d5 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: Passive Fire Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by Passive Fire Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 10 - Packing, Lifting & Shipment
checkpoint-no-status |  |  | checkpoint | Packing, Lifting & Shipment
boolean | e12131e6-b654-5933-8e1b-fa8323ddaf5e |  | tickbox | Packing
boolean | f541b999-b677-5cf6-867c-f2669116af43 |  | tickbox | Internal packing
boolean | cdf88ab4-6375-5899-8d29-dc0fc852f176 |  | tickbox | External packing
boolean | 778d302a-d55d-5672-9de4-d9f146dac7b2 |  | tickbox | Lifting and Loading
boolean | 99c1a8d8-6182-5f2b-8a69-35e39ba013e5 |  | tickbox | Shipment
checkpoint-status |  |  | checkpoint | 10.1 - Document Collection
boolean | c03e0cc3-bea1-53b5-9908-2fdefc05b065 |  | tickbox | QA Handover Pack
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review Signoff by Team Leader
checkpoint-status |  |  | checkpoint | Hold point: Quality Assurance Manager
holdpoint |  |  | signoff | Hold point: Review Signoff by Quality Assurance Manager
checkpoint-status |  |  | checkpoint | Hold point: Production Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by Production Manager
checkpoint-group |  |  | section | 11 - Final Signoff
checkpoint-status |  |  | checkpoint | Final Signoff
boolean | 4ab7dd1d-1ab7-52ae-a8f5-f52d240e92be |  | tickbox | Sections 1 through to 10 have been reviewed
boolean | 2a69dacd-a927-57d4-b8ef-88139fd4dfb5 |  | tickbox | Holdpoints Signoff have all been completed
boolean | c5cdaaf5-8894-5726-99ff-97ac3056e2a1 |  | tickbox | All QA RFI are closed
checkpoint-status |  |  | checkpoint | 11.1 All Document Collected - CONQA & OSTENDO
checkpoint-status |  |  | checkpoint | Hold point: Quality and Compliance Manager
holdpoint |  |  | signoff | Hold point: Final Review Signoff by Quality and Compliance Manager
checkpoint-status |  |  | checkpoint | Hold Point: General Manager
holdpoint |  |  | signoff | Hold point: Final & Review Signoff by General Manager
checklist-sectioned |  |  | checklist | EGM_Ver1.1_22.11.23_Station 1_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_ Station 1_Inspection | 77049c9b-f85d-4349-9c7a-7c9fb83ffc24
checkpoint-group |  |  | section | Station 1_Electrical & Mechanical - First Fix_DB_Ducting_Penetrations Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Electrical Services Plan and provide photo
checkpoint-status |  |  | checkpoint | Ostendo Station 1 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install Distribution Board as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Install all electrical cabling as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Check and verify installed switchgear valves as per plan
checkpoint-status |  |  | checkpoint | All conduit, cables are noted correctly
checkpoint-status |  |  | checkpoint | Drill penetrations through timber frame from external for internal wires
checkpoint-status |  |  | checkpoint | Ensure all screws are torqued to correct specification
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
checkpoint-status |  |  | checkpoint | External mark-out and cut fireboxes through ply/GIB, and overview photo required
checkpoint-status |  |  | checkpoint | Mechanical Ducting install as per mechanical service plan, and overview photo required
text | 7932acb1-4b1b-5357-b693-3462b0b28d84 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 1_Plumber & Drainage Team_First Fix Wingbacks Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 1 Module material scan, completed
checkpoint-status |  |  | checkpoint | Ensure all plumbing pipework is secure with applied sealant where required, prior to overview photos
checkpoint-status |  |  | checkpoint | Install all required wingbacks (cylinder, water meter, toilet, washing machine, shower) as per manufacturer's specification, and overview photo required.
checkpoint-status |  |  | checkpoint | Install shower mixer and overview photo required.
text | d58eab16-85f3-5d65-882e-ff29f7b77d46 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold Point: Team Leader
holdpoint |  |  | signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 1_ Module Assembly _Bulkhead Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install bulkhead partially (leave bottom open for ducting install) as per approved plan and manufacturer specification
checkpoint-status |  |  | checkpoint | Ostendo Station 1 Module material scan, completed
text | 17c306b7-a565-523e-97e8-16adeeebf0f0 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 1 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | edf10181-2f1c-5502-b485-73114e2cae36 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 1 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 1_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 1_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 1_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 2_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 2_Inspection | 7b808138-2556-4cb9-be4c-4115b309229c
checkpoint-group |  |  | section | Station 2_Electrical & Mechanical Team - First Fix_Firebox and Penetrations Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Electrical Services Plan and provide photo
checkpoint-status |  |  | checkpoint | Ostendo Station 2 Module material scan, completed
checkpoint-status |  |  | checkpoint | Locate and cut out all firebox penetrations as per manufacturer plan
checkpoint-status |  |  | checkpoint | Drill penetrations for external wiring down frame as per manufacturer plan
checkpoint-status |  |  | checkpoint | Install and secure mechanical ducting as per mechanical service plan
checkpoint-status |  |  | checkpoint | On completion of first fix, overview photo required
text | d83c4ff9-2e80-5d16-825a-5d2adc6799b4 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 2_Electrical & Mechanical Team - First Fix_Firebox and Passive Fire Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Fix firebox with pads and fire seal as per Approved Shop Drawing, and photo required.
checkpoint-status |  |  | checkpoint | Ostendo Station 2 Module material scan, completed
checkpoint-status |  |  | checkpoint | Check and verify all penetrations and passive fire as per manufacturer plan
checkpoint-status |  |  | checkpoint | On completion of firebox with pads, and passive fire, an overview photo is required
text | 2cf72ef7-b166-564e-bfff-6d1fbfedc96e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 2_Module Assembly Team_Acoustic Floor Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 2 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install acoustic floor as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | Install acoustic flooring and fixing as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | Install Batten and cradle as per manufacturer specification, and overview photo required
checkpoint-status |  |  | checkpoint | Install underfloor acoustic insulation as per manufacturer specification, and overview photo required
checkpoint-status |  |  | checkpoint | Install Fire fire sealant to perimeter and photo required.
checkpoint-status |  |  | checkpoint | Install wet area flooring and fixing as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | On completion of Acoustic Floor, overview photo required
text | fd12083a-21ee-5706-b40e-b459a1c6a78a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 2_Module Assembly Team_Insulation_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 2 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install all insulation material as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | Attach Insulation Certificate, and overview photo required (wall and ceiling for each R-value insulation material used).
text | d9227364-9e1b-5791-84b5-c8403e16d8ad |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 2_ Air-Conditioner Contractor _Pre-wiring/pipework Inspection_Module A
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 2 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install pre-wiring and pipework from external wall to internal wall, as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | On completion of works, an overview photo is required
text | 252352d6-83ad-5e49-a099-b5bc7f5bbc0f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: Contractor
holdpoint |  |  | signoff | Hold point: Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 2 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 4ee52f3d-2466-5076-a9ca-3c1e7aa0616b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 2 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If no RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If no RFI)
checkpoint-group |  |  | section | Station 2_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 2_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 2_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 6_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 6_Inspection | 7fe9e2fe-4655-4cf9-8614-92e0427d2748
checkpoint-group |  |  | section | Station 6_Gib Stopping 3rd Coat - Wall and Ceiling_Module A or B
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per approved plans
text | 23b06076-8419-540a-b63e-1d77c36b7b06 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | on completion of work, overview photo required
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step
checkpoint-group |  |  | section | Station 5_Putty Sanding - Architraves & Skirting_Module A or B
checkpoint-status |  |  | checkpoint | Install internal putty sanding to architraves & skirting as per approved plans
text | 13f29383-ff0d-5116-af3f-fcadfaf989c7 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed putty to holes of architraves and skirting as per specifications & approved plans
holdpoint |  |  | signoff | Hold point: photo required and Signoff by Operator before going to next step
checkpoint-group |  |  | section | Station 6 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 492d2f17-ac48-5cb7-af59-aa8ca6c31d05 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If no RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If no RFI)
checkpoint-group |  |  | section | Station 6_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 6_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 6_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_20.03.23_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection |  |  |  |  | Yes | EGM_Ver1.0_20.03.23_Element Assembly 5_Plumbing & Drainage - Floor Cassette_Inspection | 9028fb35-8c6e-47a3-9cdb-4e17a08455b7
checkpoint-group |  |  | section | Element Assembly 4_Pre-plumbing and Drainage Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Plumbing and Drainage services Plan, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Element material Scan, completed.
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacturer instructions.
text | 887214f1-8661-55ca-a170-3ec61b11fbf6 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify the pipework installed as per Approved Shop Drawing and photo required.
checkpoint-status |  |  | checkpoint | Check and verify foul water pipe gradients compliant and photo required.
checkpoint-status |  |  | checkpoint | Lagging to drainage pipework, as per specifications/ manufacturer, and photo required.
checkpoint-status |  |  | checkpoint | Timber joist stiffeners where drainage pipework penetration occur, and photos required.
checkpoint-status |  |  | checkpoint | Complete air test to AS/NZS3500 and photo required.
checkpoint-status |  |  | checkpoint | Complete water test to AS/NZS3500 and photo required.
text | 9f4832ee-0567-5d02-afd3-0ba55e29ba4e |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 5 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 0f958ae3-4ef5-537b-ac0f-4f7d9df4dcc8 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 5_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 5_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 5_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.2_22.11.23_ Element Pre-Assembly 2_Pilot Holes_Inspection |  |  |  |  | Yes | EGM_Ver1.2_22.11.23_Element Pre-Assembly 2_Pilot Holes_Inspection | 9378d43f-a24a-4648-badb-f09bb6ba0432
checkpoint-group |  |  | section | Element Pre-Assembly 2_Pilot Holes Inspection
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Timber Element Assembly Line Bar Code, completed.
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per correct template, and photo required
checkpoint-status |  |  | checkpoint | Station - Pilot Holes, as per specification and tolerance and photo required.
text | 6cc9d350-9197-575e-a71d-497c2e2ae942 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Pre-Assembly 2 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | f06f7297-fd49-5324-9fd5-ef6b39312d93 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review & Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Pre-Assembly 2_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Pre-Assembly 2_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Pre-Assembly 2_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.2_22.11.23_ Component 1_Timber Cut Production_Inspection |  |  |  |  | Yes | EGM_Ver1.2_22.11.23_ Component 1_Timber Cut Production_Inspection | 9a5e96ec-9ad0-4247-b41b-8cccc1a298a8
checkpoint-group |  |  | section | Element_Component 1_Timber Cut Production Inspection
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing & Saw Cutting List Plan, and provide picture of the respective plan which clearly shows the Element Code.
checkpoint-status |  |  | checkpoint | Ostendo - Timber Component Line Bar Code, completed.
checkpoint-status |  |  | checkpoint | Station - Correct Cutting File, as per approved manufacturer plan, and photo required.
checkpoint-status |  |  | checkpoint | Ostendo - Timber Element Assembly Line Bar Code, completed.
checkpoint-status |  |  | checkpoint | Station - Cutting lot completed, checked, and as per approved element code.
text | 7cd1df20-9289-5970-a04b-8cd02173f33b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Component 1 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 98e53b3c-429f-5fc7-b7bf-eace90750a08 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Component materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Component 1_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Component 1_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Major Final by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Component 1_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 8_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 8_Inspection | ae061033-0282-492f-9f04-0412b89db218
checkpoint-group |  |  | section | Station 8_1st and 2nd Coat Painting Plasterboard - Wall & Ceiling_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacturer specifications
text | ae570ccf-a777-5f84-9466-d5401c597e2c |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 8_1st and 2nd Coat Painting - Architraves, Skirting - Doors & Window Jambs_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacturer specifications
text | 7b18ac7a-3c45-5ad1-8ff5-de0062405410 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 8 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 388d02b3-d55f-550e-8acf-b9a078d5ed1e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 8_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 8_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 8_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 7_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 7_Inspection | b185d231-a1c6-4bf8-b0c7-4deb2d8b8c1f
checkpoint-group |  |  | section | Station 7_Gib Stopping Sanding - Wall and Ceiling_Module A or B
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping sanding as per specification & approved plans
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | e8d1326a-edf3-55db-b266-fa728685dfd0 |  | textbox | Operator name:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 7_Sealer Coat_Wall, Ceiling, Architraves & Skirting_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the sealer coat internal painting as per approved plans and manufacturer specifications
text | 86a6e6a1-c3ac-5eea-85de-0728bf5365e8 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the sealer paint coat and apply dent stopping and dent sanding completed (overview photo required)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 7 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 22003826-6018-5a58-ac7a-5e7b13f6ef2b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 7_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 7_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 7_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 5_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 5_Inspection | b1c05ace-2cad-4bf1-8b8b-0c137fcdc946
checkpoint-group |  |  | section | Station 5_First Fix Plumbing and Drainage_Module B
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacturer instructions.
text | 7d232dba-b309-5d1f-8b28-ef1da24acd7c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | After installation of inner wall water pipework, complete water test to 500Kpa for 30mins (Provide Photo)
checkpoint-status |  |  | checkpoint | After plasterboard (GIB) installation, complete pressure test water pipework to 500Kpa for 30mins (Provide Photo)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold Point: Team Leader
holdpoint |  |  | signoff | Hold point: Review on digital level of all pipes' runs and Signoff by Plumbing Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 5_Gib Stopping 1st Coat - Internal Walls_Module A or B
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
text | 3c318493-5de6-5043-9a1c-addf36932160 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per approved plans
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 5_Gib Stopping 2nd Coat - Wall and Ceiling_Module A or B
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
text | 1603e444-06f8-563d-b99d-9d427b15b7a5 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per specifications & approved plans
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 5_Putty Holes - Architraves & Skirting_Module A or B
checkpoint-status |  |  | checkpoint | Install internal putty holes to architraves & skirting as per approved plans
text | 7b05d63d-25e2-58fc-ab17-ac052b884308 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed putty to holes of architraves and skirting as per specifications & approved plans
holdpoint |  |  | signoff | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 5 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | bf5a8c3e-e810-5e86-b793-37e78acec001 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 5_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 5_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 5_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_Element Pre-Assembly 1_Structural Stud_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Element Pre-Assembly 1_Structural Stud_Inspection | b7ccc3c8-3af2-4ef6-ab61-266ae2b5f1b4
checkpoint-group |  |  | section | Element Pre-Assembly 1_Structural Stud Inspection
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Timber Element Assembly Line Bar Code, completed.
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per correct template
checkpoint-status |  |  | checkpoint | Component - Pre-Stud brackets & Rothoblaas install, as per specification and tolerance
checkpoint-status |  |  | checkpoint | Component - Pre-Stud nail stitching install, as per specification and tolerance and photo required.
text | 4d910104-b76c-5b89-b5b6-2ce40354b2c9 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Pre-Assembly 1 Inspection__Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 9042cb16-f217-57e3-a6ab-1a6a314558d5 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Pre-Assembly 1_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Pre-Assembly 1_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Pre-Assembly 1_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_19.12.23_ Station 12_Inspection |  |  |  |  | Yes | EGM_Ver1.0_19.12.23_Station 12_Inspection | d9ce08fc-a231-4a39-83aa-7bf64628ec2b
checkpoint-group |  |  | section | Station 12_Final Testing Plumbing and Drainage Inspection - Module B
checkpoint-status |  |  | checkpoint | Check and review as per approved shop drawing plumbing and drainage services Plan, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | SW pipework flood test, provide photo
checkpoint-status |  |  | checkpoint | Hot and Cold Water test for 30mins at 1550KPa as per AS/NZS 3500, provide photo
checkpoint-status |  |  | checkpoint | Visual check all pipework, no leaking detected, during testing
checkpoint-status |  |  | checkpoint | Visual check all fixtures & fitting, no leaking detected, during testing
text | 604e51d0-6171-5c60-8a30-10632aa7a40f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 12_Electrical Testing (Inform electrician to carry out the required electrical testing of all installation)_Module A & B
checkpoint-status |  |  | checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | RCD Test, provide photo
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Electrical Team Leader before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 12_Hardware_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved Shop Drawing Plans and specifications
checkpoint-status |  |  | checkpoint | Complete all hardware as per approved Shop Drawing plans and specifications, overview photo required
text | 266da760-fda6-510a-b336-22030f241358 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 12 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 5e983565-162b-56f9-b7fa-9387b66e81bc |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 12_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 12_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 12_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | Station 10_Floor Covering - Vinyl Inspection_Module B |  |  |  |  | Yes | Station 10_Floor Covering - Vinyl Inspection_Module B | e07fe315-77eb-4384-9f62-ed8b6fbe9b06
checkpoint-group |  |  | section | Contractor - Floor Covering
checkpoint-status |  |  | checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all floor coverings as per specifications and approved shop drawings (overview photo required)
checkpoint-status |  |  | checkpoint | Install floor protection, completed (as required)
text | fb4e9f3c-6445-557e-811a-38b7975a39e1 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 10_Fitout Assembly _Shower Area Hydrapanel & Fitout Inspection_Module B
checkpoint-status |  |  | checkpoint | Hydrapanel installed as per specification and approved shop drawings.
checkpoint-status |  |  | checkpoint | Ostendo Module material scan, completed
checkpoint-status |  |  | checkpoint | Shower curtain, toilet roll holders, towel rail, installed as per specifications and approved shop drawings.
checkpoint-status |  |  | checkpoint | Vanity, vanity mirror cabinet, installed as per specification and approved shop drawings
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | b45ba0b4-b87a-57ba-b446-d9b70006e3e8 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 10_Fitout Assembly - Fitout Wardrobes Inspection_Module A
checkpoint-status |  |  | checkpoint | Check and review correct manufacturer plan and provide picture of the respective manufacturer plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Module material scan, completed
checkpoint-status |  |  | checkpoint | Wardrobe rail and shelves as per specification and approved shop drawings
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 81dd840d-e0e6-5820-8b40-9769d123af52 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 10 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | e346560d-23ce-5bce-857c-db5304f6bd1f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 4 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 10_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 10_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 10_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | Station 11_Kitchen Cabinets Inspection_Module B |  |  |  |  | Yes | Station 11_Kitchen Cabinets Inspection_Module B | e3ca8788-db93-4eab-989a-357c3563336d
checkpoint-group |  |  | section | Contractor - Kitchen Cabinets
checkpoint-status |  |  | checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all kitchen cabinets as per specifications and approved shop drawings
checkpoint-status |  |  | checkpoint | Install benchtop, completed (sealant as required)
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 14be51c4-46fe-5958-912a-4d07c785b87c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 11_Electrical & Mechanical Team_Second Fix Electrical & Mechanical Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Electrical and Mechanical Services Plan and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Module material scan, completed
checkpoint-status |  |  | checkpoint | Install all power points and light switches.
checkpoint-status |  |  | checkpoint | Install all lights.
checkpoint-status |  |  | checkpoint | Install heat pumps. (Onsite install)
checkpoint-status |  |  | checkpoint | Install heat towel rail. (If required)
checkpoint-status |  |  | checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint-status |  |  | checkpoint | Install HW cylinder
checkpoint-status |  |  | checkpoint | Install Kitchen oven/hob.
checkpoint-status |  |  | checkpoint | Install wall heaters.
checkpoint-status |  |  | checkpoint | Check, by contractor smoke alarm, installed - completed
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | cdae7ebb-30c3-5242-8a5c-ab80ade2097f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold Point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 11_Final Fix Plumbing and Drainage Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Plumbing and Drainage services Plan, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo Module material scan, completed
checkpoint-status |  |  | checkpoint | Install HW cylinder as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install toilet as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install kitchen sink plumbing as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install shower fittings as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install vanity plumbing as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install floor waste as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install supertub & plumbing as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | Install shower tray waste plumbing as per Approved Shop Drawing plans and manufacturer instructions.
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 4161b4dc-3ed6-5357-8f55-3ff3ce96d537 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 11 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 7e5bee83-9976-56d2-814b-c288f1b22e0a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 11 Module materials were scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 11_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 11_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 11_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_18.12.23_Element Assembly 6_Wall Frame /IW_Inspection |  |  |  |  | Yes | EGM_Ver1.0_18.12.23_Element Assembly 6_Wall Frame /IW_Inspection | ee7f13bb-8b9e-4dad-aa02-69687c74f0a8
checkpoint-group |  |  | section | Element Assembly 6_Internal Wall Frame and Preline Inspections_Module A or B
checkpoint-status |  |  | checkpoint | Check and review correct Approved Shop Drawing and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Assembly Elements Scan, completed.
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per Approved Shop Drawing Plan & Specification
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Approved Shop Drawing Plan, and photo required
checkpoint-status |  |  | checkpoint | Check and Verify correct GIB plasterboard installed as per Shop Drawing Plan, (and photo required if GIB Fyrline or Aqualine install required, and fixing)
text | acc70b92-dc6d-55e5-9afc-cf677fd5a56d |  | textbox | Internal Wall ID:
text | 5544f330-69e7-5901-9840-483f15a79f82 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 6 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | 435b19ef-c937-53e9-a07d-a6fa98bb9a07 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Assembly 1_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.2_22.11.23_Element Pre-Assembly 3_Pre-Cut Lining Materials_Inspection |  |  |  |  | Yes | EGM_Ver1.2_22.11.23_Element Pre-Assembly 3_Pre-Cut Lining Materials_Inspection | f9921698-b2ed-4ed7-b47a-ba599c9c5486
checkpoint-group |  |  | section | Element Pre-Assembly 3_ Pre-Cut Lining Inspection
checkpoint-status |  |  | checkpoint | Check and review as per Approved Shop Drawing Lining Plan Ply & Plasterboard GIB Plan, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Ostendo - Common Line Bar Code_Ply, GIB Plasterboard Line Bar Code, completed.
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per Approved Shop Drawing Plan
checkpoint-status |  |  | checkpoint | Station - lining sheet 1 (typically Ply), as per Approved Shop Drawing Lining Plan, and photo required.
checkpoint-status |  |  | checkpoint | Station - lining sheet 1 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, and photo required.
checkpoint-status |  |  | checkpoint | Station - lining sheet 2 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, and photo required.
text | 88b8f4e8-dbce-58e8-9568-00133f198c36 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Pre-Assembly 3 Inspection__Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | d98ee786-3a0a-5940-829f-98e4e75e5df3 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Element Pre-Assembly 3_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Element Pre-Assembly 3_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Element Pre-Assembly 3_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist-sectioned |  |  | checklist | EGM_Ver1.1_30.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.1_30.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE | f9ee96bd-2ab3-43b7-a5fa-07dedbf8758d
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE_Module A_B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE @2400MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE @2400MM
checkpoint-status |  |  | checkpoint | GIB 10MM STANDARD X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING @ 3100 X 350 & @ 900 X 350MM
checkpoint-status |  |  | checkpoint | INTERNAL PRE-HUNG DOOR RH or LH
checkpoint-status |  |  | checkpoint | INTERNAL PRE-HUNG DOOR STOPS
checkpoint-status |  |  | checkpoint | ARCHITRAVES LENGTHS
checkpoint-status |  |  | checkpoint | SKIRTING LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER CURTAIN
checkpoint-status |  |  | checkpoint | CEILING INSULATION
checkpoint-status |  |  | checkpoint | ITEMS SECURED IN MODULE
checkpoint-status |  |  | checkpoint | VANITY & KITCHEN DOORS, SHOWER HEAD TAPED TO AVOID OPENING/DAMAGE
checkpoint-status |  |  | checkpoint | MODULE CLEANING COMPLETED
text | 7c8fff72-7b18-5290-aae9-aba540f94683 |  | textbox | ITEMS:
text | 0bdad48c-f32f-5fb1-a5d3-f1591936555f |  | textbox | ITEMS:
text | df0fb1fc-e603-5727-9d28-2dd8acdf7b8d |  | textbox | ITEMS:
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | d9081f38-037e-530e-b2c2-5681cbd74066 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.11.23_ Station 3_Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.11.23_Station 3_Inspection | feb318e6-b68f-4990-93ab-9c90510c2c71
checkpoint-group |  |  | section | Station 3_Electrical & Mechanical - First Fix_DB Wiring and SS Shower-tray Earthing Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review as per Electrical and Mechanical Services Approved Plan and provide photo
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Distribution Board wiring placement as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Check and verify installed switchgear valves as per plan
checkpoint-status |  |  | checkpoint | All cables are noted correctly
checkpoint-status |  |  | checkpoint | Ensure all screws are torqued to correct specification
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
checkpoint-status |  |  | checkpoint | Stainless Steel shower tray earthing connection as per electrical/mechanical service approved plan,
checkpoint-status |  |  | checkpoint | Install ventilation fan in bulkhead area, as per approved electrical/ mechanical plan.
checkpoint-status |  |  | checkpoint | On completion of Distribution Board, SS shower tray earthing, and ventilation fan, an overview photo is required
text | 7a1b82e5-6817-57c5-98b2-32aa211b32d6 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ Smoke Alarm Contractor _Pre-wiring Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved manufacturer plan.
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install pre-wiring and pipework from external wall to internal wall, as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | On completion of works, overview photo is required.
text | bcb75f7a-32dc-5575-a405-2efde43c0ec9 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_Fitout Team_Wrap (RAB) Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install balance RAB and install fixings as per manufacturer specification, an overview fixing photo is required
checkpoint-status |  |  | checkpoint | Install all RAB joint tapes/Sealants to RAB joints, windows, doors, penetrations. Etc, as required.
checkpoint-status |  |  | checkpoint | On completion of RAB joint tape and penetration tapes, an overview photo is required
text | 3ec69d8c-fa4f-5959-b3e1-be6e4f1bfc15 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_Penetration_Modules A or B
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint-status |  |  | checkpoint | Install all penetrations, as required.
text | 8535fc5b-43ef-53ae-ba31-ba3afa1cc237 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Station 3_Fitout Team_Opening Flashing Tapes & Sill Support Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install opening flashing tapes to Sill, Head, Jamb, window/door etc., as required.
checkpoint-status |  |  | checkpoint | On completion of opening flashing tapes, an overview photo is required
text | 1b691c7c-af05-5a6b-94c9-1a4dcc2fd58b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install with SS screw fixing all sill supports window/door etc., as required.
checkpoint-status |  |  | checkpoint | On completion of sill support fixing, an overview photo is required
text | b107b82d-9229-5748-b36f-772ac1d65050 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_Fitout Team_Fire Door and Fire Seal/Airseal Inspection_Module B
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install Fire door as per door schedule and PF backing rod, fire seal/airseal
checkpoint-status |  |  | checkpoint | On completion of stage of installation of PF baking rod and fire seal/airseal, an overview photo is required
text | b9183c89-b6bc-5e85-899b-edd4cbfdac30 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ Module Assembly _Passive Fire Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which show page number
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install wall and ceiling fire sealant, fire dampers, collars and sealants as per approved plans and manufacturer specifications.
text | c0d93090-2d75-5a7e-b9ef-d4efbc06d56d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ Fitout Team_Stainless Steel Shower-tray Inspection_Module B
checkpoint-status |  |  | checkpoint | Install SS shower-tray as per approved plan and manufacturer specification
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | On completion of works, overview photo required
text | 7488c189-51d6-51c2-b77c-588d545c94ce |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ Fitout Team_Bulkhead bottom_Module B
checkpoint-status |  |  | checkpoint | Install balance of bulkhead bottom battens as per approved plan and manufacturer specification
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
text | 0b02c16d-7986-5372-bd07-c1b84bcd6b13 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ Fitout Team_Internal GIB Plasterboard Inspection_Module A or B
checkpoint-status |  |  | checkpoint | Install internal GIB plasterboard as per approved plan and manufacturer specification
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Check and Verify correct GIB plasterboard installed as per Shop Drawing Plan, (and photo required if GIB Fyrline or Aqualine install required, and fixing)
text | 0a8ee139-2fa8-5956-b970-cfbb1b967d42 |  | textbox | Type of GIB plasterboard:
text | 370d7acf-e74a-5326-b428-66f3c83fec82 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_ External Membrane Waterproofing Contractor Inspection_Module A
checkpoint-status |  |  | checkpoint | Check and review as per approved manufacturer plan.
checkpoint-status |  |  | checkpoint | Ostendo Station 3 Module material scan, completed
checkpoint-status |  |  | checkpoint | Install waterproof membrane to sliding door sill area including upstand as per approved plans and manufacturer specifications.
checkpoint-status |  |  | checkpoint | On completion of work, overview photo required
text | 95b768cc-19d2-577f-8227-6a547cdb96de |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold Point: Review and Signoff by Contractor before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3 Inspection_Signoff
checkpoint-no-status |  |  | checkpoint | Inspection
text | cc8c5005-7565-541c-be08-41bfc6a72d1c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Review of Station 3 Module materials where scanned
checkpoint-status |  |  | checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint-status |  |  | checkpoint | Evaluated RFI Critical issue - Photo required:
checkpoint-status |  |  | checkpoint | Hold point: Team Leader
holdpoint |  |  | signoff | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint-status |  |  | checkpoint | Hold point: QA Manager
holdpoint |  |  | signoff | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
checkpoint-group |  |  | section | Station 3_QA RFI_Minor
checkpoint-status |  |  | checkpoint | Photo required - RFI Minor issue outcome:
checkpoint-status |  |  | checkpoint | RFI Minor Review by QA Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint-status |  |  | checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
checkpoint-group |  |  | section | Station 3_QA RFI_Major
checkpoint-status |  |  | checkpoint | Photo required - RFI Major issue outcome:
checkpoint-status |  |  | checkpoint | RFI Major Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Major Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint-status |  |  | checkpoint | Hold point: Quality & Compliance Manager
holdpoint |  |  | signoff | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
checkpoint-group |  |  | section | Station 3_QA RFI_Critical
checkpoint-status |  |  | checkpoint | Photo required - RFI Critical issue:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QA Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by Production Manager comments:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint-status |  |  | checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint-status |  |  | checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint |  |  | signoff | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.