## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | EGM_Ver1.0_12.01.24_Component Pre-Assembly 1_Structural Stud_Inspection | [5 empty] | EGM_Ver1.0_12.01.24_Component Pre-Assembly 1_Structural Stud_Inspection
section | Component Pre-Assembly 1_Structural Stud Inspection
checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number
checkpoint | Ostendo - Timber Element Assembly Line Bar Code, completed.
checkpoint | Station - Mark up correct, as per correct template
checkpoint | Component - Pre-Stud brackets & Rothoblaas install, as per specification and tolerance
checkpoint | Component - Pre-Stud nail stitching install, as per specification and tolerance and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 1 Inspection__Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review and Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 1_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 1_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Pre-Assembly 1_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_12.01.24_Component Pre-Assembly 2_Pilot Holes_Inspection | [5 empty] | EGM_Ver1.0_12.01.24_Component Pre-Assembly 2_Pilot Holes_Inspection
section | Component Pre-Assembly 2_Pilot Holes Inspection
checkpoint | Check and review as per Approved Shop Drawing & template pilot hole, and provide picture of the respective plan which clearly shows page number
checkpoint | Ostendo - Timber Element Assembly Line Bar Code, completed.
checkpoint | Station - Mark up correct, as per correct template, and photo required
checkpoint | Station - Pilot Holes, as per specification and tolerance and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 2 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review & Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 2_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 2_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Pre-Assembly 2_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_12.01.24_Component Pre-Assembly 3_Pre-Cut Lining Materials_Inspection | [5 empty] | EGM_Ver1.0_12.01.24_Component Pre-Assembly 3_Pre-Cut Lining Materials_Inspection
section | Component Pre-Assembly 3_ Pre-Cut Lining Inspection
checkpoint | Check and review as per Approved Shop Drawing Lining Plan Ply & Plasterboard GIB Plan, and provide picture of the respective plan which clearly shows page number
checkpoint | Ostendo - Common Line Bar Code_Ply, GIB Plasterboard Line Bar Code, completed.
checkpoint | Station - Mark up correct, as per Approved Shop Drawing Plan
checkpoint | Station - lining sheet 1 (typically Ply), as per Approved Shop Drawing Lining Plan, and photo required.
checkpoint | Station - lining sheet 1 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, and photo required.
checkpoint | Station - lining sheet 2 (typically Gib Plasterboard), as per Approved Shop Drawing Lining Plan, and photo required.
textbox | Operator name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Pre-Assembly 3 Inspection__Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Ostendo Element Pre-Assembly materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Pre-Assembly 3_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before refering to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Pre-Assembly 3_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before refering to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Pre-Assembly 3_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critcal Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before refering QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_19.12.23_Station 10_Inspection | [5 empty] | EGM_Ver1.0_19.12.23_Station 10_Inspection
section | Station 10_Floor Covering - Vinyl Inspection_Module B
checkpoint | Contractor - Floor Covering
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan which clearly shows page number
checkpoint | Install all floor coverings as per specifications and approved shop drawings (overview photo required)
checkpoint | Install floor protection, completed (as required)
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 10_Fitout Assembly _Shower Area Hydrapanel & Fitout Inspection_Module B
checkpoint | Hydrapanel installed as per specification and approved shop drawings.
checkpoint | Ostendo Module material scan, completed
checkpoint | Shower curtain, toilet roll holders, towel rail, installed as per specifications and approved shop drawings.
checkpoint | Vanity, vanity mirror cabinet, installed as per specification and approved shop drawings
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 10_Fitout Assembly - Fitout Wardrobes Inspection_Module A
checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint | Ostendo Module material scan, completed
checkpoint | Wardrobe rail and shelfs as per specification and approved shop drawings
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 10 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 10_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 10_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 10_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_19.12.23_Station 11_Inspection | [5 empty] | EGM_Ver1.0_19.12.23_Station 11_Inspection
section | Station 11_Kitchen Cabinets Inspection_Module B
checkpoint | Contractor - Kitchen Cabinets
checkpoint | Check and review as per specifications and approved shop drawings, and provide picture of the respective plan which clearly shows page number
checkpoint | Install all kitchen cabinets as per specifications and approved shop drawings
checkpoint | Install benchtop, completed (sealant as required)
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint | Hold point: Review and Signoff by Contractor before going to next step (If No RFI)
section | Station 11_Electrical & Mechanical Team_Second Fix Electrical & Mechanical Inspection_Module A or B
checkpoint | Check and review as per Approved Shop Drawing Electrical and Mechanical Services Plan and provide picture of the respective plan which clearly shows page number
checkpoint | Ostendo Module material scan, completed
checkpoint | Install all power points and light switches.
checkpoint | Install all lights.
checkpoint | Install heat pumps. (Onsite install)
checkpoint | Install heat towel rail. (If required)
checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint | Install HW cylinder
checkpoint | Install Kitchen oven/hob.
checkpoint | Install wall heaters.
checkpoint | Check, by contractor smoke alarm, installed - completed
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold Point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint | Hold point: Signoff by Team Leader before going to next step (If No RFI)
section | Station 11_Final Fix Plumbing and Drainage Inspection_Module B
checkpoint | Check and review as per Approved Shop Drawing Plumbing and Drainage services Plan, and provide picture of the respective plan which clearly shows page number
checkpoint | Ostendo Module material scan, completed
checkpoint | Install HW cylinder as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install toilet as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install kitchen sink plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower fittings as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install vanity plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install floor waste as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install supertub & plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | Install shower tray waste plumbing as per Approved Shop Drawing plans and manufacture instructions.
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 11 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Station 11 Module materials were scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 11_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 11_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 11_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_12.01.24_Station 13_Packing Onsite Items-Packaging & External Wrap Cover Inspection | [5 empty] | EGM_Ver1.0_12.01.24_Station 13_Packing Onsite Items-Packaging & External Wrap Cover Inspection
section | Station 13_Fitout Team_Items to be included in Module for onsite_Module A or B
checkpoint | Check and review as per Approved Shop Drawings Plans, specifications and as per list
checkpoint | Ostendo Station 13 Module material scan, completed
checkpoint | Check all items as per list included in Module
checkpoint | Check all items are secured in place
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: photo required and Signoff by Operator before going to next step (If No RFI)
section | Station 13_Internal Fixtures and Fittings Packaging_Module A or B
checkpoint | Toilet: Cistern fixed by using blue 14 day tape
checkpoint | Shower: Shower head taped in place to shower rail
checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using blue 14 day tape.
checkpoint | Bathroom: Bathroom Shower curtain is supplied and protected
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
holdpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 13_Packaging_External Protective Wrap Cover_Module A or B
checkpoint | Use protective film to cover a module completely
checkpoint | Ostendo Station 13 Module material scan, completed
checkpoint | Use heat Gun to seal the protective film.
textbox | Operator Name:
checkpoint | Make sure there are no gaps in the film
holdpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 13 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 13_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 13_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 13_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_12.01.24_Yard_Lifting, Loading & Shipment Inspection | [5 empty] | EGM_Ver1.0_12.01.24_Yard_Lifting, Loading & Shipment Inspection
section | Yard_Lifting, Loading & Shipment_Module A or B
checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle
checkpoint | Tie the module to the Transport Vehicle, using strops or with the equipment attached to the Vehicle this is by Specialist Transport Operator/ Driver
checkpoint | Make sure the module is correctly sitting on the Transport vehicles this is by Specialist Transport Operator/ Driver
checkpoint | Make sure the Module has been secured with the correct ties this is by Specialist Transport Operator/ Driver
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
holdpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Station 14_ Yard_Shipment_Module A or B
checkpoint | A Specialised Transportation Vehicle will be used to transport the module to Site
textbox | Operator Name:
checkpoint | Check if the Transport Company meet the approved transport criteria
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
section | Station 14 Inspection_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Review of Station 4 Module materials where scanned
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Station 14_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Station 14_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Station 14_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.
checklist | EGM_Ver1.0_19.12.23_Document/ Works_Records | [5 empty] | EGM_Ver1.0_19.12.23_Document/ Works_Records
section | Document / Attachment / Link / Photo
checkpoint | Records
checkpoint | On completion of work, overview photo required
textbox | Operator Name:
checkpoint | Hold point: Review and Signoff by Operator before going to next step (If No RFI)
section | Document/ Works Record_Signoff
checkpoint | Inspection
textbox | Operator Name:
checkpoint | Correct Record uploaded
checkpoint | Evaluated RFI Minor issue - Photo required:
checkpoint | Evaluated RFI Major issue - Photo required:
checkpoint | Evaluated RFI Critical issue - Photo required:
holdpoint | Hold point: Review and Signoff by Team Leader before going to next step (If No RFI)
checkpoint | Hold point: QA Manager
holdpoint | Hold point: Review & Signoff by QA Manager before going to next step (If No RFI)
section | Document/ Works Record_QA RFI_Minor
checkpoint | Photo required - RFI Minor issue outcome:
checkpoint | RFI Minor Review by QA Manager comments:
holdpoint | Hold point: Signoff RFI Review Minor by QA Manager before referring to PM
checkpoint | RFI Minor Final Check by Production Manager comments:
holdpoint | Hold point: Review and Signoff RFI Minor by Production Manager Final Check
section | Document/ Works Record_QA RFI_Major
checkpoint | Photo required - RFI Major issue outcome:
checkpoint | RFI Major Review by QA Manager comments:
checkpoint | RFI Major Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Major Final Review by Production Manager before referring to QCM
checkpoint | Hold point: Quality & Compliance Manager
holdpoint | Hold point: Signoff RFI Major Final Check by Quality & Compliance Manager
section | Document/ Works Record_QA RFI_Critical
checkpoint | Photo required - RFI Critical issue:
checkpoint | RFI Critical Review by QA Manager comments:
checkpoint | RFI Critical Review by Production Manager comments:
holdpoint | Hold point: Signoff RFI Critical Final Review by Production Manager before referring QA report to QCM.
checkpoint | RFI Critical Review by Quality & Compliance Manager comments:
checkpoint | RFI Critical Review by QCM documentation for Stakeholder approval:
checkpoint | RFI Critical Review by QCM documentation for TA/ BCA Application for Minor Variation:
holdpoint | Hold point: Signoff RFI Critical Approved MV Approved Final Check by QCM before RFI report.