## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Stainless Steel Pipe Site Welding | itp |  |  |  |  | ITP - Stainless Steel Pipe Site Welding
section | Details
checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
label | Quality: Hold Point - W
label | Quality: Sign - LS
label | Quality: Witness - AG
checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
label | Quality: Sign - AK
checkpoint | Familiarise yourself with the job
label | Quality: Sign - AK
checkpoint | Setup worksite, welding equipment & rollers
label | Quality: Sign - AK
checkpoint | Load length into rollers
label | Quality: Sign - AK
checkpoint | Bevel pipe ends
label | Quality: Sign - AK
checkpoint | Tack weld 6m lengths into instructed lengths
label | Quality: Sign - AK
label | Quality: ID - AK1
checkpoint | Check for straightness alignment
label | Quality: Hold Point - C
label | Quality: Sign - AK
label | Quality: Witness - AG
checkpoint | Setup purge baloons & purge with nitrogen
label | Quality: Hold Point - C
label | Quality: Sign - AK
label | Quality: Witness - AG
checkpoint | Peform butt welds
label | Quality: Sign - AK
label | Quality: ID - AK1
checkpoint | Tack flanges on spool lengths & check for square
label | Quality: Hold Point - C
label | Quality: Sign - AK
label | Quality: ID - AK1
label | Quality: Witness - AG
checkpoint | Weld flanges on ends
label | Quality: Sign - AK
label | Quality: ID - AK1
checkpoint | Passivate all welds
label | Quality: Sign - AK
checkpoint | Remove from rollers and move to lay down area
label | Quality: Sign - AK
checkpoint | Final inspection
label | Quality: Hold Point - H
label | Quality: Sign - AG
label | Quality: Witness - LS
holdpoint | HOLD POINT