## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP011 - Concrete Production | itp |  |  |  |  | FH-ZU2-QU-ITP011 - Concrete Production - Rev 0
section | 1 - Plant
checkpoint | 1.1 - AS1379 4.2.1
label | Inspection Description - Batch tolerances
label | Acceptance Criteria - AS1379 Table 4.1
label | Frequency - Each Batch
label | Initiated by - PS
label | Approved by - PS
label | Verification/Witness: HOL - W
label | Verifying Document - Electronic
label | Record Location - Batch computer
checkpoint | 1.2 - HOL QMS PN6.1
label | Inspection Description - Record Plant Malfunctions
label | Acceptance Criteria - All plant mulfunctions are to be documented
label | Frequency - Each Time
label | Initiated by - PS
label | Approved by - AOM
label | Verification/Witness: HOL - W
label | Verifying Document - Register
label | Record Location - AOM office
checkpoint | 1.3 - AS1379.3.3.2
label | Inspection Description - Weigh Hopper (Cem & Agg)
label | Test/Inspection method - AS1379
label | Acceptance Criteria - ± 0.4% of the Max. Scale Value
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification/Witness: HOL - W
label | Verifying Document - Calibration Report
label | Record Location - Google
checkpoint | 1.4 - AS1379.3.4.2
label | Inspection Description - Water Meters (Plant, Slump Stands & Trucks)
label | Test/Inspection method - TRBE652973
label | Acceptance Criteria - ± 2%
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification/Witness: HOL - W
label | Verifying Document - Calibration Report
label | Record Location - Google
checkpoint | 1.5 - AS1379.3.4.2
label | Inspection Description - Admixtures
label | Test/Inspection method - BASF TM033
label | Acceptance Criteria - ± 5%
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification/Witness: HOL - W
label | Verifying Document - Calibration Report
label | Record Location - Google
section | 2 - Cementitous materials
checkpoint | 2.1 - AS1379.2.2
label | Inspection Description - Type GP cement
label | Test/Inspection method - AS2350
label | Acceptance Criteria - AS3972 Table 2
label | Frequency - Cement Australia Supplied (as per AS3972 Clause 5.2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verification/Witness: Company - H
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - BECA Cl 11.4.7, 11.24.5
label | Inspection Description - Reference Sample
label | Acceptance Criteria - -
label | Frequency - Plant Sample : 10kg / 1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Company - W
label | Verifying Document - Record only
label | Record Location - Tech Mgr office
checkpoint | 2.2 - AS1379.2.2
label | Inspection Description - Flyash
label | Test/Inspection method - AS3583
label | Acceptance Criteria - AS/NZS3582.1 Table 1 - Grade 1
label | Frequency - Cement Australia Supplied (as per AS/NZS3582.1 Table 2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verification/Witness: Company - H
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - AS1379.2.2
label | Inspection Description - Slag
label | Test/Inspection method - AS3583
label | Acceptance Criteria - AS3582.2 Table 1
label | Frequency - Cement Australia Supplied (as per AS3582.2 Table 2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verification/Witness: Company - H
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Coarse Aggregate
checkpoint | 3.1 - AS1379.2.3
label | Inspection Description - Particle Size Distribution
label | Test/Inspection method - AS1141.11.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.2 - AS1379.2.3
label | Inspection Description - Flakiness Index
label | Test/Inspection method - AS1141.15
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per month
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.3 - AS1379.2.3
label | Inspection Description - Particle Density & Water Absorbtion
label | Test/Inspection method - AS1141.6.1, AS1141.5
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 3 months
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.4 - AS1379.2.3
label | Inspection Description - Los Angeles Abrasion Index Value
label | Test/Inspection method - AS1141.23
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.5 - AS1379.2.3
label | Inspection Description - Weak Particles
label | Test/Inspection method - AS1141.32
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.6 - AS1379.2.3
label | Inspection Description - Wet/Dry Strength Variation
label | Test/Inspection method - AS1141.22, AS2758.7
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.7 - AS1379.2.3
label | Inspection Description - Petrographic Analysis
label | Test/Inspection method - ASTM C295
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 2 years
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.8 - AS1379.2.3
label | Inspection Description - Sodium Sulphate Soundness
label | Test/Inspection method - AS1141.24
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 3.9 - BECA Cl 11.4.6.2
label | Inspection Description - Reference Sample
label | Acceptance Criteria - -
label | Frequency - Once Only : 2 x 25kg samples of each coarse aggregate fraction
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Company - W
label | Verifying Document - Record only
label | Record Location - Tech Mgr office
section | 4 - Fine Aggregate
checkpoint | 4.1 - AS1379.2.3
label | Inspection Description - Particle Size Distribution
label | Test/Inspection method - AS 1141.11.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.2 - AS1379.2.3
label | Inspection Description - Sodium Sulphate Soundness
label | Test/Inspection method - AS1141.24
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.3 - AS1379.2.3
label | Inspection Description - Particle Density & Water Absorbtion
label | Test/Inspection method - AS1141.6.1, AS1141.5
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 3 months
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.4 - AS1379.2.3
label | Inspection Description - Petrographic Analysis
label | Test/Inspection method - ASTM C295
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 2 years
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.5 - AS1379.2.3
label | Inspection Description - Sugar Content
label | Test/Inspection method - AS1141.35
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.6 - AS1379.2.3
label | Inspection Description - Clay & Fine Silts
label | Test/Inspection method - AS1141.33
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.7 - AS1379.2.3
label | Inspection Description - Organic Impurities
label | Test/Inspection method - AS1141.34
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per month
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.8 - AS1379.2.3
label | Inspection Description - pH Value
label | Test/Inspection method - AS1289.4.3.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier test report
label | Record Location - Tech Mgr office
checkpoint | 4.9 - BECA Cl 11.4.6.2
label | Inspection Description - Reference Sample
label | Acceptance Criteria - -
label | Frequency - Once Only : 2 x 25kg samples of fine aggregate
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Company - W
label | Verifying Document - Record only
label | Record Location - Tech Mgr office
section | 5 - Water
checkpoint | 5.1 - AS1379.2.4
label | Inspection Description - Mains water
label | Acceptance Criteria - Main complies
label | Frequency - Nil
label | Approved by -
checkpoint | 5.2 - AS1379.2.4
label | Inspection Description - Non mains water
label | ~ Sugar
label | ~ Oil & grease
label | ~ pH
label | ~ Chlorides
label | ~ Sulfates
label | ~ Total suspended solids
label | Test/Inspection method - AS1141.35 APHA 5520 AS1580.505.1
label | Acceptance Criteria - 100 mg/L max
label | ○ 50 mg/L max
label | ○ > 5
label | ○ 500 mg/L max
label | ○ 500 mg/L max
label | ○ 2000 mg/L max
label | Frequency - 1 / 6 months
label | Initiated by - AOM
label | Approved by - Tech Mgr
label | Verification/Witness: HOL - W
label | Verifying Document - Lab report
label | Record Location - Tech Mgr office
section | 6 - Admixtures
checkpoint | 6.1 - AS1379.2.5
label | Inspection Description - WR Admixture general acceptance
label | Test/Inspection method - AS1478.2
label | Acceptance Criteria - AS1478.1 Table 2.1
label | Frequency - Initial
label | Initiated by - Tech Mgr
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier report
label | Record Location - Tech Mgr office
checkpoint | 6.2 - AS1379.2.5
label | Inspection Description - WR Admixture Uniformity test
label | Test/Inspection method - AS1478.2
label | Acceptance Criteria - AS1478 Cl 2.1.3
label | [Supplier specs for pH (+/- 1), Relative density (+/- 0.02), Non-volitle content (+/- 2%)]
label | Frequency - MBCC Supplied (Each Batch)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Test Reports
label | Record Location - Plant
checkpoint | 6.3 - AS1379.2.5
label | Inspection Description - AEA Admixture general acceptance
label | Test/Inspection method - AS1478.2
label | Acceptance Criteria - AS1478.1 Table 2.1
label | Frequency - Initial
label | Initiated by - Tech Mgr
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Supplier report
label | Record Location - Tech Mgr office
checkpoint | 6.4 - AS1379.2.5
label | Inspection Description - AEA Admixture Uniformity test
label | Test/Inspection method - AS1478.2
label | Acceptance Criteria - AS1478 Cl 2.2.3
label | [Supplier specs for pH (+/- 1), Relative density (+/- 0.01), Non-volitle content (+/- 1%)]
label | Frequency - MBCC Supplied (Each Batch)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification/Witness: Supplier - W, R
label | Verification/Witness: HOL - W
label | Verifying Document - Test Reports
label | Record Location - Plant
section | 7 - Transport
checkpoint | 7.1 - HOL QMS PN6.1
label | Inspection Description - Agitator blade inspection
label | Acceptance Criteria - Concrete Barrel Solution - No excess buildup, No excess wear
label | Frequency - 1 / 3 months
label | Initiated by - PS
label | Approved by - AOM
label | Verification/Witness: HOL - W
label | Verifying Document - Inspection report
label | Record Location - Plant
checkpoint | 7.2 - AS1379 3.5.1 (a)
label | Inspection Description - Mixer uniformity test
label | Test/Inspection method - AS1012
label | Acceptance Criteria - AS1379 Appendix A Table A1
label | Frequency - Initial for agi type
label | Initiated by - Trans
label | Approved by - Tech Mgr
label | Verification/Witness: HOL - W
label | Verifying Document - Manufacturer report HOL test report
label | Record Location - Tech Mgr office
checklist | ITP014 - Sawcutting & Joint Sealing | itp |  |  |  |  | FH-ZU2-QU-ITP014 - Sawcutting & Joint Sealing - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for Correct Documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC
label | Reference Documents - Current revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented in accordance with PSP, EMP, TMP, JSEA, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Materials
label | Frequency - Prior to commencing Works
label | Acceptance Criteria - Joint sealer shall be Dowsil 888 silicone joint sealant or approved equivalent.
label | ○ Manufacturer’s instructions shall be provided to the Principal’s Representative prior to works commencing.
label | Reference Documents - Beca Spec 002 - 11.4.15 & 11.13.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
section | 2.0 - Installation
checkpoint | 2.1 - Define Area of Works
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All joints shall conform to the details and shall be constructed in the locations shown on the Drawings.
label | Reference Documents - Beca Spec 002 - 11.13.1 to 11.13.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.2 - PCC Curing
label | Frequency - Each Lot
label | Acceptance Criteria - In areas where sealing works are planned, confirm PCC has been cured for a minimum of 7 days prior to sealing.
label | Reference Documents - Beca Spec 002 - 11.13.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Cleaning of Joints
label | Frequency - Each Lot
label | Acceptance Criteria - Joint faces shall be thoroughly cleaned and dry prior to sealing. This shall be approved by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 - 11.13.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Backing Rod Install
label | Frequency - Each Lot
label | Acceptance Criteria - Backing rod to be installed to depth shown on the drawings.
label | Reference Documents - Beca Spec 002 – 11.13.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Sealant Install
label | Frequency - Each Lot
label | Acceptance Criteria - Sealant to be tooled off to correct recess. Excess sealant to be removed from the surface of the concrete.
label | Reference Documents - Beca Spec 002 – 11.13.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to confirm with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP024 - Line Marking | itp |  |  |  |  | FH-ZU2-QU-ITP024 - Line Marking - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex.
label | Reference Documents - Current revisions in Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
label | Reference Documents - PSP, EMP, TMP, WMS, SWMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Plant and Equipment
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Plant and equipment used in the works are appropriate to achieve specification requirements.
label | Reference Documents - BECA 15.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.4 - Materials
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The paint to be used shall be a premixed synthetic latex-based paint (such as WATTYL AIRPAVE or approved equivalent).
label | Reference Documents - BECA 15.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - Material Reports / This ITP Signed
label | HP
label | Responsibility - Project Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Material Handling
label | Frequency - Prior / During works
label | Acceptance Criteria - The paint Is to be packaged in 20 litre containers that are of durable construction without sharp edges. Paint containers are to be clearly labelled “Airport Pavement Marking Paint” as well as being labelled with the following: Manufacturer’s name, Colour, Batch number and Date.
label | Reference Documents - BECA 15.4.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.6 - Survey and setting out
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall carry out the setting out of the pavement Markings as shown on the drawings. This shall be approved by the Principal’s Representative.
label | Reference Documents - BECA 15.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project Engineer Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Construction
checkpoint | 2.1 - Removal of Existing Line Marking
label | Frequency - Each Lot
label | Acceptance Criteria - Existing pavement markings, at the locations shown on the Drawings, shall be removed by water blasting or other approved means that is non-destructive to the existing pavement surface.
label | Reference Documents - BECA 15.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Surface preparation
label | Frequency - Each Lot
label | Acceptance Criteria - The surface of the asphalt or concrete pavement in the areas to be painted shall be thoroughly cleaned prior to the application of the pavement marking paint. This shall be approved by the Principal’s Representative.
label | Reference Documents - BECA 15.6
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Weather Conditions
label | Frequency - Each Lot
label | Acceptance Criteria - Pavement marking shall not proceed during wet weather or when the pavement surface is wet or when rain is likely or during high winds.
label | Reference Documents - BECA 15.10
label | Inspection/Test Method - Verify & Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Application
label | Frequency - Each Lot
label | Acceptance Criteria - The paint must be applied in two even coats to provide the required minimum total dry film thickness as specified by the manufacturer. The second coat is to be applied no less than three days following the initial coat.
label | Reference Documents - BECA 15.8
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Application Rate and Conformity of Application
label | Frequency - Each Lot
label | Acceptance Criteria - Daily records of paint usage and the area covered shall be maintained by the Contractor.
label | Reference Documents - BECA 15.12
label | Inspection/Test Method - Daily Records
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Post Construction
checkpoint | 3.1 - Records
label | Frequency - Each Lot
label | Acceptance Criteria - Finished pavement markings shall conform to the following tolerances:
label | ○ Location of pavement markings ±10mm
label | ○ Width of any line or line forming an alpha/numeric symbol ±5mm
label | ○ Length of any line and the spacing of broken lines ±50mm
label | ○ Dimensions of any alpha/numeric symbol ±10mm
label | Reference Documents - BECA 15.9
label | Inspection/Test Method - Verify
label | Record of conformity - Survey
label | SCP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: