## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
3d56704f-44b9-436a-88a7-882ed39acce2 | checklist | Byford U-Beam Stage-1 Casting Checklist |  | Byford U-Beam Stage-1 Casting
33e1642c-1803-410e-97a2-b0e11c708144 | section | Pre-Pour Checklist
11f851a0-a6a3-4d59-b1ac-39894113681e | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
37d5a902-7e78-4fdb-b75b-cdc671e56b24 | checkpoint | Shop Drawings approved for Works
a930a70b-5901-46d1-b904-479b76705e9a | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
f8e73dfc-886b-4d67-98c6-6e39a8cdc024 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
188bfaff-0a90-410a-846f-bd10a3074607 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
75201410-af47-44a4-b17d-5cb4a070bb6c | checkpoint | Detailed inspection of Mould and cage
3a775a10-4da8-4ba4-a7a4-aa230ed7361b | checkpoint | Cover maintained and within tolerance
bb06cc61-73f9-4e6f-82e0-380334f05a80 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
16ec099a-5519-4d90-901c-3a895c01098e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
34fba665-51e3-4a97-a208-7eaeb6436470 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
16e1d1c1-a5d6-4667-a3c7-3626199f2b4d | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
5e51f49c-3c78-41d0-9dbe-4f35f1a90573 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
9b25c136-be44-436e-98b7-8c46b7bbfe60 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
aa360362-ce7c-422e-b5db-dd524bc99ac6 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
a59146c4-8389-4b27-a430-a0e10fe58a88 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (attach results)
10da2b4c-11ff-4e52-814b-be536cae3523 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
fcaf9f0f-4d97-40d8-b07b-25b126cdb638 | checkpoint | Stressing Records subject to Client Review
81d23dd9-4d09-4b90-917d-b0e6aeaa8bd4 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
13db744c-ff6c-4b3f-ac20-52a8366c53fd | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
453a6ea5-c6d8-49cb-929a-ef6d373f0b9a | checkpoint | All Cooling tubes installed as per drawings
0b16c686-7a3c-4c96-aef4-31f463d33762 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
71f1e260-f02b-484d-914e-30ad5ce59a4d | checkpoint | QA Engineer Check Completed by
ce66b55a-740e-4420-9af6-d758ef4df8ff | checkpoint | Client Inspector (if present)
005240e5-2a13-44b7-9332-b5241bba55e2 | section | Supervisor Release
7e5161d9-daf5-403d-8d04-b069ceda843f | checkpoint | Supervisor Release to Engineering Team
744d6e1f-ccd1-4388-bf84-da980ecaaaf1 | section | Casting Checklist
48dc3901-28eb-4839-bded-57c964432a68 | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
b8665d9b-69e4-4e89-b094-3af6606f451f | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
d5721a31-a1f5-4f79-8517-2ec58e037a02 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
22b9b714-b3c6-4a93-8934-39f2c4d89573 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
7f111803-14d0-4f3b-b9bb-13fa74ade85f | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
77330ade-9880-481f-b4a7-3bb835951f6b | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
ffca7c7b-8c5d-443f-ad1a-39b3fe87a6e0 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
a078c6ca-68ec-4220-a886-2219a1ed2c61 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
95c2cca6-ae7b-41c3-8f6e-a9438f19ab32 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
b9af6e4d-5823-46b0-b4d2-038e73110740 | checkpoint | Concrete Placed within allowable time from Batching Plant
2485c0ac-aa35-4f8e-b3e5-7c0bcc285238 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
de48d957-f511-41cb-951f-da6f1e690e36 | checkpoint | Required Finish Applied as per Drawings
56482f97-77fc-4514-913d-6286912611c4 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
8d61de29-0e51-4f68-9803-9b4477e33200 | checkpoint | Concrete Covered Overnight
ce91d371-b61e-4db0-b18d-031c7e474cd0 | checkpoint | Cylinders Stored next to Bed
811b1bb2-cb15-4ef2-853a-8043aeeb13af | section | Stripping Checklist
070206a7-8604-4197-a528-ee8aa39693bb | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
8e9b49f6-da6b-41ed-b538-d6eda4f92470 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
da054075-a340-46c1-b2e1-fe01a2dfdba7 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
0f98b8f4-cd35-4995-b2b9-77412833dde3 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
842c54d2-6b32-47fa-8915-3f894e5e2c80 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
dd6bf488-ea55-43f4-a12e-d69e9ca1ca14 | checkpoint | Lifted and Handled as per Drawings
4c1e18b8-2d8a-4de6-8a57-1c9fea30835f | checkpoint | Product Clearly Labelled
3689c579-22d8-45e4-b424-0bad08b0e895 | checkpoint | Storage as per Approved Temporary Works Drawings
25423762-ab12-4c53-891f-7fc34f4c11c0 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
86ba6e95-d86e-466b-86af-fa4392c911bf | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
b6cbb7fb-36f0-47b9-b746-3738f176afce | checkpoint | Specified Finish Achieved
420b3eac-c7c4-4d34-9cf6-a5eec17951b4 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
4cfeb342-b250-4eed-a3cb-8df53719d479 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
a066e65d-dae5-4d36-8ccf-f9666e0cbe48 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
19ba0b17-ff44-4ffa-ad81-e1aaac531416 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
d4586d36-39e1-4576-863c-e9de04638363 | section | Any Defect Identified
2594e669-41ad-40f8-988a-701f89055f7d | checkpoint | Punchlist Completed
cf7067bf-2a1e-4765-83a1-b795e2873f66 | checkpoint | Repairs Required (if applicable)
e45dfa64-6ce6-4064-8ef3-b37b5bd7ed1d | checkpoint | Repairs Completed as per approved WMS (if applicable)
837dd6b1-aaed-45c4-942a-c172bd9e77c2 | checkpoint | Crack Map Completed
5c9fb481-d8fe-44c0-a6d9-7d8bf8fa961f | checkpoint | Any NCR Required (if applicable)
7666c60d-dc6d-42f3-af68-9ed67b247b0b | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
cece918d-81a5-4548-9d1b-8e0623e69334 | section | As-Built Drawings
16dc0419-0937-4c4c-b0e1-4c10a3ffba78 | checkpoint | As-Built Drawings Completed, Stamped and Attached
44046711-60ca-4533-985b-aebef3a15d1a | section | Concrete Strength Test Report
e344b336-bc86-41d2-a759-656c6937784c | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
bdca8ed9-02cb-461a-892d-19d7e29eed76 | section | Transportation Requirements
938e1344-07c1-46f7-a4a5-e2aa7754ae0e | checkpoint | Certificate of Conformance
ff11f27d-8802-4bda-86a2-94e676b3f163 | checkpoint | Inspection Release Certificate
53cd7c3b-f148-4f24-8332-43f04076ecc0 | checkpoint | Delivery Notes
3225e364-6de3-40f2-b3d0-c6992c03ca7a | checkpoint | Delivery Docket
f901d6a0-e746-4121-8251-5959aded4c21 | section | Final Acceptance
01b97dc6-c460-4807-a4bb-9fbbad221373 | checkpoint | Completed by
7c13ea6a-47c9-4f2e-a94b-ab38b1c5c6df | checkpoint | Reviewed by
681538f2-bc4a-4dfb-b8d9-08994595cf93 | checkpoint | Client Representative (if applicable)
0c2966b2-bb35-4e3b-9215-d2a4ff017def | checklist | Byford U-Beam Stage-2 Casting Checklist |  | Byford U-Beam Stage-2 Casting Checklist
69e02ca0-aa40-4440-987b-fbfac32d8588 | section | Pre-Pour Checklist
e9d804bb-507a-4999-9de1-19b0cb8a7bcc | checkpoint-no-value | Details
1233fbbe-8a90-5695-bf6b-28144e51953d | textbox | Cast Number
d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 | textbox | Beam Number and Orientation
acb384d1-e98c-5a02-9f7c-1128a2c5f72b | textbox | End Diaphragm
97bfed52-24af-496f-b878-0367a5bf9c60 | checkpoint | Shop Drawings approved for Works
4b3f8c75-2893-4a84-b5cf-1e8bea62f84a | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
4c1b674a-8bd8-50e8-959b-bec5d6dadc3e | note | Length
822d1104-8a27-5ed9-980e-888b7bf6caaf | note | Width
830ee2ae-8950-5298-a691-e9600cf10537 | note | Height
bab4373d-5276-50ed-954e-45ea96aec8c3 | note | Straightness
b82d264a-3d32-5473-8664-32a90bab9013 | note | Cross-section
c3207d6f-31da-496f-a961-37de7ae5ee94 | checkpoint | Condeck Surface Checked
a0273126-e254-5157-8d98-f128fa5c6b52 | note | Cleaned
9bb4e700-f5d2-5e02-883e-e5072418e64b | note | Sealed
3ec0752e-0691-5a4f-86ac-8445eadef662 | note | Oiled
0e62dce7-e433-4ba4-8abd-00ab27e3a1a3 | checkpoint | Reinforcement in Accordance with Drawings
800fadac-1be9-5858-94f4-5d4746740084 | note | Reinforcement size
0f320d4a-3d88-5e76-9d42-76621d58e218 | note | Lap Length
f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 | note | Splicing
62881279-32c4-593b-b849-3eefda69eb96 | note | Bar Chairs
b31c7adc-8ff0-5948-b00d-593cf326b1e2 | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
12cb8723-6db8-5a57-b575-655471779936 | textbox | Blockout recess around lifting Hoops
80c2d060-3c27-4cae-a855-4e2c95630e80 | checkpoint | Detailed inspection of Mould and cage
94d72df5-e41c-41e9-a973-8fec3bf00e61 | checkpoint | Condeck (Top Slab) - Verify all brackets fixed at slab thickening
bec954e6-8601-4196-9e81-051772112915 | checkpoint | Cover maintained and within tolerance
98bbf309-ebbb-46ff-88db-e49d08f0d40f | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
9f215da9-19e9-5047-a80a-c229bb1325f1 | textbox | Ferrules M16x96 (Handrails)
8d90112a-ec60-5a67-a2f3-d316d5261991 | textbox | Ferrules M10x45 (Expansion Joint Cover)
d1b00e18-ceba-57fe-9b5e-6d4e7db97304 | textbox | Ferrules M10x45 (Ladder)
49d2450b-c55f-5f52-8737-b23eef564e73 | textbox | Ferrules (Other type, specify)
5d0578fd-8107-4832-8967-a90957ac2d4b | checkpoint | All Stainless Items are installed in accordance with Drawings
1e328254-d184-5f54-943a-e1976e1eb331 | textbox | Other type, specify
0ef49df0-35d8-4116-bdd5-7a16d4ea940d | checkpoint | Earthing and Bonding is installed in accordance with Drawings
87db205a-a14e-5be0-b795-5d53984ab585 | textbox | Earthing Terminals (FDB-16)
09abc58f-8a0f-5f60-96e2-32bee1276a84 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
a020b351-e865-5d5e-a4b5-b441cabfd625 | textbox | <20 mOhm across cage Length
4ef34acd-9e10-5711-9e70-4735a0a2bbd0 | textbox | Checklist Completed (North & South) (attach results)
1414f7c5-5e61-4aa7-a427-013b3f054cf0 | checkpoint | All Temperature Loggers are installed as per Approved WMS
7f2ff394-48d1-5d12-a9a5-88aa58174bf6 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
571ae87d-30f9-4a7f-9c57-c354eb6c4e33 | checkpoint | All Cooling tubes installed as per drawings
22055223-9286-4296-9beb-00bb5f4df5fa | checkpoint | QA Engineer Check Completed by
a31f14b7-a59d-45d4-923a-048498b5e296 | checkpoint | Client Inspector (if present)
118485a3-1c5d-4657-a89a-fe6114039488 | section | Supervisor Release
aa567090-54f6-484f-83c2-f0a5b2df1094 | checkpoint | Supervisor Release to Engineering Team
d16096b4-b137-41e1-b7c7-ce383af86553 | section | Casting Checklist
1c30cd3a-8fed-4c79-8dc6-ffec1e76e6af | checkpoint | Casting Information
1a647942-8258-57e6-b6ff-621161085e77 | textbox | Cast Date
bf85045e-7291-4e41-adfc-4f3930c1b224 | checkpoint | Concrete Delivery Dockets
d392af45-5195-5119-892d-80cfe0b6a20e | textbox | Concrete Delivery Dockets (list all)
ebcc38eb-b9fb-4703-92f0-a8406a18856e | checkpoint | Total Concrete Volume
60fa028a-b7ea-54d1-954a-1213bd11e8e1 | textbox | Volume (m3)
8446c524-f6d7-45a3-86c0-70114a1ef359 | checkpoint | Mix Design Verified
f8a395fa-8391-5639-a09e-c5241875a63d | textbox | Specify mix used
95766753-ca7b-4c77-8947-eb86b913dd28 | checkpoint | Ambient Temperature within Limits
a4f51cbb-ff6a-5071-bca5-5481459038f1 | note | max 38°C
a1109acb-badd-4ae9-bc6c-65a6b27c8094 | checkpoint | Concrete Temperature
897bf355-b709-54f5-9399-3a7efa254455 | note | max 32°C
7b69d6a1-c9f1-46bf-9407-ee9e74008ba1 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
e41fe62b-76cf-448a-97b9-634915c22099 | checkpoint | Trucks Tested for strength
1db14c07-5972-5f2c-9497-617ae1c2a547 | textbox | Test Report Reference Number (list all)
c51f7d46-2953-4497-8ad0-6dfbd622d0ea | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
bcfedf44-15f7-4abe-88f3-cd6592d879e9 | checkpoint | Concrete Placed within allowable time from Batching Plant
4e281710-dc4d-4f7e-b96e-a08250923013 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
d565c155-02a7-47a7-8a39-eee94646fe3d | checkpoint | Required Finish Applied as per Drawings
f46b299d-0b62-452b-b947-0fa3149803f7 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
12b6b7ab-4b40-4a9e-950e-edd052f41a07 | checkpoint | Concrete Covered Overnight
76acac69-7ec7-4237-821a-c6580bbb0c40 | checkpoint | Cylinders Stored next to Bed
228bfdc9-4a5b-4fa6-8f82-66b53d9dfae3 | section | Stripping Checklist
8a7b2b52-f8f6-4b98-9b5b-d554f32bc7e1 | checkpoint | Date Stripped
901c78d2-ef96-5ae6-a1f7-9a653c24de1a | textbox | Enter Date
43fe64c4-70f6-4cf3-a1e8-1171a28ed0c5 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f0b85fdc-6c4d-511a-a42b-626445232756 | note | Conversion KN to MPa = Reading / 7.851
786038d6-bea8-5d36-850d-c5b0f8eeb594 | note | Stripping strength 20MPa
ab2f98ba-453f-546d-8399-ab6d61235c1c | textbox | Stripping Strength (Stage-2 Casting)
a992bb3c-427c-464b-b122-9de737b09c32 | checkpoint | Lifting Strength Achieved
ddd53939-10f1-5062-be90-0c69a5b2b2d6 | note | Lifting strength required for stage 2 casting - 20MPa
990eb32e-733a-5942-8ad7-1dc6175f29d7 | textbox | Specify strength at time of lifting
f20fadb9-136e-4118-8037-44c59e33cc9c | checkpoint | Curing Strength (Stage-2 Casting)
775b182d-e021-55ec-9a45-7abb946c1815 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
c4a6b006-d64b-56cc-af22-7a32fa98085e | note | Tarped until the curing strength achieved
21c35c3b-fb0d-400c-9376-fa4aec637f58 | checkpoint | Lifted and Handled as per Drawings
844a9458-28bb-4117-ac76-c94bdd62e421 | checkpoint | Product Clearly Labelled
b7b6fa6f-368d-4d79-96a2-0a191a18267b | checkpoint | Storage as per Approved Temporary Works Drawings
e29db614-d051-4ba7-ad2c-c4a9eb29d205 | checkpoint | Secondary Curing as per Approved Methodology
8a3fc87f-1a7b-44bd-8fae-92eda854319f | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
df44e42b-2e80-5f94-ac7f-80765b72e6f9 | note | Length
e4265a90-0641-5ae7-9983-17040cae58b3 | note | Width
7bb4ba7f-c14e-56fd-9171-dbeee66caa97 | note | Height
ff36979f-97bd-5709-a920-421e847495e8 | note | Straightness
f932effb-f869-5bc3-b54d-3dc7703f8e53 | note | Cross-section
b4b7fb99-35a5-4a3d-8f53-5d3ef4511dc0 | checkpoint | Specified Finish Achieved
c174c223-617c-4bff-b666-a72c12630471 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 | textbox | Ferrules
3cde73a1-6070-5769-9afb-cb3e15618119 | textbox | Stainless Items
f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb | textbox | Lifters
8d91365d-45e2-5a6d-abc6-191ce31f5767 | textbox | Blockouts
b46c54eb-4f86-491b-8423-cb229ef6a560 | checkpoint | Post-Pour Works Completed (As Required)
7a542891-b623-52f8-ae88-77c1c09fb89f | textbox | Ferrules are Cleaned and Capped
80630288-7f59-5868-b4d3-3428afa34d9b | textbox | Roughened Surfaces are Greencut
915898d3-a5d9-5e68-9706-7a0fa68a24a2 | textbox | All Miscellaneous Items are Completed
7b44f1b2-c84f-4214-9883-c4421fb2c6b1 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
a3b8ed66-4aa0-40b2-a457-adcbaa10327d | section | Any Defect Identified
bdb4e0a3-e94c-4b15-b0f4-c32cd4de221d | checkpoint | Punchlist Completed
46f3bc41-7e30-4f9c-8bfd-8b3ad038d744 | checkpoint | Repairs Required (if applicable)
b3a4e113-562a-43f4-a6ce-1c7457a82149 | checkpoint | Repairs Completed as per approved WMS (if applicable)
891c918e-ae08-4fef-b297-3d7fb30f53a5 | checkpoint | Crack Map Completed
a600c08b-615b-42a4-a70e-31e69ba18b36 | checkpoint | Any NCR Required (if applicable)
63a845a7-9d37-46d2-817e-1a11a8a26dcd | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
e5452a26-a331-4ae9-9b7c-0f5b0e669687 | section | As-Built Drawings
18732704-20e1-4a1f-94be-a0a857027fe1 | checkpoint | As-Built Drawings Completed, Stamped and Attached
05afab1a-9537-4574-98d2-6a569cdd15cb | section | Concrete Strength Test Report
94fd4638-352c-43e4-a110-1248f6e13832 | checkpoint | Concrete Strength Test Report Received
72ed3bf3-f25d-562e-9513-1b400cbb5e33 | textbox | Concrete Test Report
009f2cbd-af76-54bf-99ce-3bcdafdfefd1 | textbox | 7 Day Strength (List all)
bde663bb-3906-572f-9122-80785c06ca94 | textbox | 28 Day Strength (List all)
bc7afb81-1cf5-4423-8b6a-8350107d682b | checklist | Preliminary Activities and Materials Approval Checklist |  | Preliminary Activities and Materials Approval
59c569d9-af0e-4098-9e2e-aa3ceef9353c | section | Preliminary Activities (Approved by Client)
71bbe339-b59b-4ee7-a177-b2afa4ff2b0d | checkpoint | Compliance to AS/NZ ISO 9001:2015
eee1cfaf-2b77-45a9-b1b4-b4c0c7c5fe10 | checkpoint | Permacast Project Quality Management Plan
53a4b40e-9c46-46b1-83e6-d9eac22f5120 | checkpoint | Inspection & Test Plan
1c57fd7e-486b-4f4c-a676-fc824b4104ac | checkpoint | MDR Index
5a3a34be-2061-4aa3-8723-9ce4d4051223 | checkpoint | Work Method Statement (WMS) - Prestress
24a58c3e-6de9-4510-8816-a570243eba2d | checkpoint | Work Method Statement (WMS) - Curing
64e897fb-d60a-4c61-a1e9-c2c192555eab | checkpoint | Concrete Repair Methodology
f94b045e-a0c4-4ce1-b160-3623c67cf5dd | checkpoint | Shop Drawings
a637bcfd-4260-4f22-bea5-93579c4569ef | checkpoint | Test Panel Prepared and Inspected by Client
8a7347c6-4425-4fe9-9bea-1c78d4e07f53 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
9c4dc1e5-2d12-41ad-bb06-fadedac91a77 | section | Concrete
2c541f82-813c-4188-aa46-8cc603292ec5 | checkpoint | S65 Concrete Mix Design Approved by Client
dc1e2d50-69a4-4cd5-9cdd-a4dc15079d78 | section | Steel Reinforcement
d64b2f66-aecf-4ddd-8c6f-d72e0119158d | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
5a9f8842-daa6-4d67-9ad6-fe8e19a0b438 | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
97ea2900-6005-4ffe-9fe1-b49465d336cb | section | Prestressing Tendons
37de0717-d100-4b80-a78e-7d6ef7885dca | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
3cd57bdd-d815-411a-b9d8-329298cc72c7 | checkpoint | Ensure that all Coil Numbers are recorded
46dcb04c-7e24-45e2-bd87-8af1badaf5ba | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
bae6b534-bc31-4ba7-a24d-236a94e11453 | checkpoint | Stressing Jack Calibration Certificates
2252962e-3b82-4954-8e0d-3cf647ca2f7b | section | Lifting Anchors
82a69b65-680f-4b5a-ac4c-d4248e506cc5 | checkpoint | Lifting Design Approved by Client
a264a881-bceb-4b35-aee7-342fbaa61330 | checkpoint | Lifting Devices Approved by Client
9f3f95c9-66d9-4332-8233-4cdaed838485 | checkpoint | Inspection of Delivery for Completeness and Quality
1474312c-6aad-454c-9129-272df66ec1d1 | section | Cast-in Items and Ferrules
35e450c8-afc8-47c0-9abc-151844699cb0 | checkpoint | All Cast in Materials Approved
28d50a56-12e8-40db-9e78-e0df7dcefc41 | checkpoint | Inspection of Delivery for Completeness and Quality
a0e9b0e9-f145-4563-a445-c31d14db3046 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v1) |  | Byford U-Beam Stage-1 Casting
1b283145-9444-42cc-86d4-7c38d61cc7b4 | section | Pre-Pour Checklist
34eb53e8-3762-4da2-9dd0-3cfa8ec76271 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
bca35014-dcf4-4ce1-886f-9d682980d4ae | checkpoint | Shop Drawings approved for Works
f656237f-1e93-43e5-9e64-2de978e3f465 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
5ced35c8-a6de-4316-abd5-d16386a3e515 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
3e79e8c0-bff8-4b13-8f03-d5c49d5e601a | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
73325ba1-df01-4195-8db7-dec36c028e92 | checkpoint | Detailed inspection of Mould and cage
e24f6dfe-d5f1-4186-a525-d4cc656ec91d | checkpoint | Cover maintained and within tolerance
4b276b4f-1b04-48ea-a1e5-e45b22cb7ec0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
d23968b0-8e43-4210-9ea6-d82f890a0c64 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
6c534ea7-ba65-4442-9940-e5496cfdc34c | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
c6c80186-6f4c-43bd-a6e2-92fff1b65498 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
2355acbc-c061-408d-82bc-4d247667621e | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
ee341819-7665-47fe-84cd-a72f1909bf47 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
5df617b8-e1a4-49ad-930a-ca610f481d3a | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
9ed13afc-e62d-4446-a0df-e1db36c11028 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
5a11a7b0-b7fb-4a0b-bb64-373b982ee9f4 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
7ffe0f24-b8fc-43d2-95d6-f722ca9116af | checkpoint | Stressing Records subject to Client Review
b7ccfb81-71b0-4489-9cfd-af807ee2f336 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
eb17fd1e-1b18-4d7b-8f08-374f2506d759 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
3a71a13d-2bfc-46e7-8017-689c85344f72 | checkpoint | All Cooling tubes installed as per drawings
1184bb1f-03d2-48bb-8018-e60e6ae3950a | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
356b7072-d85d-4f73-bc58-70887926aef6 | checkpoint | QA Engineer Check Completed by
99faac90-15b3-4a19-8154-43fc8d5f517c | checkpoint | Client Inspector (if present)
977002ac-7d4f-4018-a294-e4cbbd1d4c9a | section | Supervisor Release
236a0495-482c-4a98-af3f-093da395c35d | checkpoint | Supervisor Release to Engineering Team
4e39cc15-9c4b-44ba-8069-91cf45e7ba88 | section | Casting Checklist
67d33390-ecca-45d7-bbe8-6344b689379a | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
34fd634d-6622-452b-88ae-fb87ba2b8237 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
1f43ee4a-b478-466e-8f59-9f6a1f3d5304 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
85d5022a-792e-4580-a2e5-ad65c7f9cece | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
8d6500f8-b29a-4b7f-8a9a-d61032d3755e | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
2956e49e-9a58-44a3-b385-281b5415b99b | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
d501ec00-d49c-44e3-92a9-317483922c8e | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
ddeeae4d-65b5-5238-8db0-d3c954bf8722 | textbox | Slump (list all)
f695eb0e-7e3d-424d-b7ac-c4d2f7f3e0d5 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
bc324c2b-adee-40f4-a3f3-f272d89cdaaf | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
49af8714-c82c-4dfc-8d0f-68fecd29eedd | checkpoint | Concrete Placed within allowable time from Batching Plant
18ecfb61-a3e3-4207-8d6a-504cba7461fb | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
d3e17bc2-f332-4502-9c35-b47caf67f7cd | checkpoint | Required Finish Applied as per Drawings
9ce32ce4-392e-4bac-959c-f073a316740e | checkpoint | Retarders applied on Green Cut areas as shown in drawings
980ee978-0055-460c-b4c7-b940ff9f30f8 | checkpoint | Concrete Covered Overnight
f743b25b-f405-495c-adcf-128df4ab20a2 | checkpoint | Cylinders Stored next to Bed
66813685-59a4-4baf-8596-e5fcf17bf705 | section | Stripping Checklist
b8398943-2e34-4fbd-8eea-bd998103b54e | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
6a3eaa61-562b-4d35-bacf-9665ecccb02d | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
0fd2af72-69ff-48fe-8245-88ca4ea0db5f | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
6ec9907e-8da6-4e60-a6bb-6ec61e8ca37f | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
b753d217-63d9-454d-8664-97dfb498da50 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
c7b9632c-6155-4006-adc0-c8163164fd01 | checkpoint | Lifted and Handled as per Drawings
4aea4ed2-5ade-410a-92b3-0616f7a6604a | checkpoint | Product Clearly Labelled
d8586f61-b348-4593-a35e-555ee686ad06 | checkpoint | Storage as per Approved Temporary Works Drawings
5c7010b5-547d-4556-b1c0-098ff804b995 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
df2720c6-8e8a-4924-a259-81d259c04a8e | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
393ea6ab-422f-43a6-8de4-7c1189902535 | checkpoint | Specified Finish Achieved
8d59663c-7207-4d9a-af63-5ed89411693e | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
f94eeef2-a80f-41bf-8b7c-f1937ef36927 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
d0b5905b-24c8-48ca-b1e0-5377125d2553 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
5edf2845-e52e-4445-a0cb-8a38f812b75c | checkpoint | Temperature Logging Completed and Conforming. Attach Results
f4eba698-951b-4f37-a98a-2dc7dd18239e | section | Any Defect Identified
ea0ce409-f14d-4bcb-9a49-32d0662beb78 | checkpoint | Punchlist Completed
9df015d7-0e9e-465e-96b0-e0929aad9042 | checkpoint | Repairs Required (if applicable)
17aac10e-0d1f-4904-896f-83ec1131927e | checkpoint | Repairs Completed as per approved WMS (if applicable)
1b25b13f-243e-4d8b-9564-def2e17b7660 | checkpoint | Crack Map Completed
f9779003-f90c-4ae1-8582-a87b598a6fa2 | checkpoint | Any NCR Required (if applicable)
04d2f7c3-f652-425f-bc1d-03ff5e4a26d4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
1aa4adb4-6f84-4f7c-9ca7-b36439c98b5d | section | As-Built Drawings
88e1a23f-8b57-491f-8ed6-232c4178359c | checkpoint | As-Built Drawings Completed, Stamped and Attached
07a649aa-2895-47b7-ac63-598dd16f4f74 | section | Concrete Strength Test Report
0e893350-206d-4ccd-ac1a-c3fcef34e35f | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
8004d94e-4b54-4019-908a-39031e3de29b | section | Transportation Requirements
bba6ea79-9f52-43ea-ba05-2a4aacfdff66 | checkpoint | Certificate of Conformance
6fe71b55-0f51-4644-be2c-68cdb6ec80d7 | checkpoint | Inspection Release Certificate
95bace19-dd45-4f35-b988-b6023204932a | checkpoint | Delivery Notes
31542ef5-2aeb-400a-8f37-8c433765d29d | checkpoint | Delivery Docket
47f1f9ac-57c0-443d-befb-792347c7993e | section | Final Acceptance
6f2879df-abb9-4e59-9758-1a103be4314b | checkpoint | Completed by
8d0976ca-90ec-4d0d-bc3f-714af951b19d | checkpoint | Reviewed by
a838f616-38a3-475d-8884-d74867d7001f | checkpoint | Client Representative (if applicable)
98f82a63-c6bb-4343-8f90-38870db25e05 | checklist | Ω (Deprecated) Byford U-Beam Stage-2 Casting Checklist (old version, v1) |  | Byford U-Beam Stage-2 Casting Checklist
68e3499e-4ec3-4ceb-a224-7c1e41b0083a | section | Pre-Pour Checklist
6eefdc89-3e7d-4048-80d9-f15ef1ebd19e | checkpoint-no-value | Details
1233fbbe-8a90-5695-bf6b-28144e51953d | textbox | Cast Number
d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 | textbox | Beam Number and Orientation
acb384d1-e98c-5a02-9f7c-1128a2c5f72b | textbox | End Diaphragm
ac5291bc-9b21-45c7-8d84-994c2fdbf8f2 | checkpoint | Shop Drawings approved for Works
2016a2e5-4c55-4309-b921-d8d41e29515c | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
4c1b674a-8bd8-50e8-959b-bec5d6dadc3e | note | Length
822d1104-8a27-5ed9-980e-888b7bf6caaf | note | Width
830ee2ae-8950-5298-a691-e9600cf10537 | note | Height
bab4373d-5276-50ed-954e-45ea96aec8c3 | note | Straightness
b82d264a-3d32-5473-8664-32a90bab9013 | note | Cross-section
d17caf36-2f56-45aa-8839-eaab07f481c9 | checkpoint | Condeck Surface Checked
a0273126-e254-5157-8d98-f128fa5c6b52 | note | Cleaned
9bb4e700-f5d2-5e02-883e-e5072418e64b | note | Sealed
3ec0752e-0691-5a4f-86ac-8445eadef662 | note | Oiled
8cd57883-99a0-42f8-ad58-66984ad264eb | checkpoint | Reinforcement in Accordance with Drawings
800fadac-1be9-5858-94f4-5d4746740084 | note | Reinforcement size
0f320d4a-3d88-5e76-9d42-76621d58e218 | note | Lap Length
f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 | note | Splicing
62881279-32c4-593b-b849-3eefda69eb96 | note | Bar Chairs
b31c7adc-8ff0-5948-b00d-593cf326b1e2 | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
12cb8723-6db8-5a57-b575-655471779936 | textbox | Blockout recess around lifting Hoops
e6843dea-b3b0-4e97-9a47-a3efa46611d0 | checkpoint | Detailed inspection of Mould and cage
eaa4facd-1d2f-4b08-80e6-3990a928d2c8 | checkpoint | Condeck (Top Slab) - Verify all brackets fixed at slab thickening
b6a05ddc-b33c-4577-9ddc-3cc72a035764 | checkpoint | Cover maintained and within tolerance
8529a34d-76d8-4f31-85db-6967eb88a0b0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
9f215da9-19e9-5047-a80a-c229bb1325f1 | textbox | Ferrules M16x96 (Handrails)
8d90112a-ec60-5a67-a2f3-d316d5261991 | textbox | Ferrules M10x45 (Expansion Joint Cover)
d1b00e18-ceba-57fe-9b5e-6d4e7db97304 | textbox | Ferrules M16x45 (Ladder)
49d2450b-c55f-5f52-8737-b23eef564e73 | textbox | Ferrules (Other type, specify)
7b93bdc5-d314-438a-a850-e6d332b3e4f6 | checkpoint | All Stainless Items are installed in accordance with Drawings
1e328254-d184-5f54-943a-e1976e1eb331 | textbox | Other type, specify
848bea4a-5fd2-4663-ae39-9d8132912600 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
87db205a-a14e-5be0-b795-5d53984ab585 | textbox | Earthing Terminals (FDB-16)
09abc58f-8a0f-5f60-96e2-32bee1276a84 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
a020b351-e865-5d5e-a4b5-b441cabfd625 | textbox | <20 mOhm across cage Length
4ef34acd-9e10-5711-9e70-4735a0a2bbd0 | textbox | Checklist Completed (North & South) (attach results)
64866f6c-d90f-4fa3-a3b6-3e21dbf3f2aa | checkpoint | All Temperature Loggers are installed as per Approved WMS
7f2ff394-48d1-5d12-a9a5-88aa58174bf6 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
98201a77-f60d-42e1-aeac-0e247f07a663 | checkpoint | All Cooling tubes installed as per drawings
abc7bb6b-54c6-46e9-9079-dd2011873c1d | checkpoint | QA Engineer Check Completed by
13c337bd-ac29-48ff-981d-c8f0c3da8696 | checkpoint | Client Inspector (if present)
641990f8-5fbf-49c7-9db8-78772196809d | section | Supervisor Release
270e0471-ddaa-4fea-bf93-bc6830d4ef5d | checkpoint | Supervisor Release to Engineering Team
63475a55-b247-4c9f-a6af-8f9688b42a90 | section | Casting Checklist
88d83b51-14fd-4dd9-888e-f52da4ab48e4 | checkpoint | Casting Information
1a647942-8258-57e6-b6ff-621161085e77 | textbox | Cast Date
fecc0c3a-5096-4881-90b6-cccae4487b09 | checkpoint | Concrete Delivery Dockets
d392af45-5195-5119-892d-80cfe0b6a20e | textbox | Concrete Delivery Dockets (list all)
c64283ea-038c-4d06-8fc5-48ddcb739795 | checkpoint | Total Concrete Volume
60fa028a-b7ea-54d1-954a-1213bd11e8e1 | textbox | Volume (m3)
39897cd6-ff27-4861-8aee-a711a8c2cbdc | checkpoint | Mix Design Verified
f8a395fa-8391-5639-a09e-c5241875a63d | textbox | Specify mix used
eba528a8-7ff1-4e49-aeee-27a8ef33b623 | checkpoint | Ambient Temperature within Limits
a4f51cbb-ff6a-5071-bca5-5481459038f1 | note | max 38°C
2002f385-03af-43f4-858e-f106bb05accb | checkpoint | Concrete Temperature
897bf355-b709-54f5-9399-3a7efa254455 | note | max 32°C
d2f2f96e-3a73-4cbf-a3b8-a4fa69c044d7 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
51a0000b-6d9c-512b-afdd-7d5a45ae465e | textbox | Slump (list all)
8c53b798-3f67-45b1-a665-758c3169c99f | checkpoint | Trucks Tested for strength
1db14c07-5972-5f2c-9497-617ae1c2a547 | textbox | Test Report Reference Number (list all)
4b7e892d-b8ce-4bb5-8a6e-9496502a8a60 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
b59b4ded-7fa0-4694-a5a9-b00f8590f345 | checkpoint | Concrete Placed within allowable time from Batching Plant
319cc792-6968-4cc3-b6c5-a99f41eb2d97 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
718d8a30-99dd-4f73-83ac-380c831d2579 | checkpoint | Required Finish Applied as per Drawings
292f6f49-a744-4a83-8f6e-8a8a44f1fbc0 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
413d70ce-bd3e-463b-afc4-419b411a10de | checkpoint | Concrete Covered Overnight
516f68de-00f2-4e61-8f20-57944d7a8169 | checkpoint | Cylinders Stored next to Bed
031a6c14-2f56-4f87-a028-eff4d714973f | section | Stripping Checklist
076e0db6-0059-4127-b3ab-4f013bf30fb2 | checkpoint | Date Stripped
901c78d2-ef96-5ae6-a1f7-9a653c24de1a | textbox | Enter Date
850503af-24ff-4d57-ba84-aaf78a56acc4 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f0b85fdc-6c4d-511a-a42b-626445232756 | note | Conversion KN to MPa = Reading / 7.851
786038d6-bea8-5d36-850d-c5b0f8eeb594 | note | Stripping strength 20MPa
ab2f98ba-453f-546d-8399-ab6d61235c1c | textbox | Stripping Strength (Stage-2 Casting)
be8099a8-54d6-474a-8ca9-5ab2fc0d7bef | checkpoint | Lifting Strength Achieved
ddd53939-10f1-5062-be90-0c69a5b2b2d6 | note | Lifting strength required for stage 2 casting - 20MPa
990eb32e-733a-5942-8ad7-1dc6175f29d7 | textbox | Specify strength at time of lifting
16864bfc-1338-4dfd-882c-4b69230bc084 | checkpoint | Curing Strength (Stage-2 Casting)
775b182d-e021-55ec-9a45-7abb946c1815 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
c4a6b006-d64b-56cc-af22-7a32fa98085e | note | Tarped until the curing strength achieved
02c30163-e235-48e7-87f1-1703e463bf18 | checkpoint | Lifted and Handled as per Drawings
bb4a283c-bd7e-475d-a1b7-f3d1aa8f65c6 | checkpoint | Product Clearly Labelled
3aa16a9a-e718-4a6c-a90a-c2b5aee249db | checkpoint | Storage as per Approved Temporary Works Drawings
810abbdd-62e8-4356-bd02-e764a528a4f3 | checkpoint | Secondary Curing as per Approved Methodology
9a1677df-6ab7-45e9-b757-ae5877ee264d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
df44e42b-2e80-5f94-ac7f-80765b72e6f9 | note | Length
e4265a90-0641-5ae7-9983-17040cae58b3 | note | Width
7bb4ba7f-c14e-56fd-9171-dbeee66caa97 | note | Height
ff36979f-97bd-5709-a920-421e847495e8 | note | Straightness
f932effb-f869-5bc3-b54d-3dc7703f8e53 | note | Cross-section
30ccb5b5-812e-4b9b-8f3b-6c2bfd14644a | checkpoint | Specified Finish Achieved
c35933d3-afe2-483f-8653-4170bdb5ed17 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 | textbox | Ferrules
3cde73a1-6070-5769-9afb-cb3e15618119 | textbox | Stainless Items
f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb | textbox | Lifters
8d91365d-45e2-5a6d-abc6-191ce31f5767 | textbox | Blockouts
13bd3877-1b7a-42bf-b918-89927084649f | checkpoint | Post-Pour Works Completed (As Required)
7a542891-b623-52f8-ae88-77c1c09fb89f | textbox | Ferrules are Cleaned and Capped
80630288-7f59-5868-b4d3-3428afa34d9b | textbox | Roughened Surfaces are Greencut
915898d3-a5d9-5e68-9706-7a0fa68a24a2 | textbox | All Miscellaneous Items are Completed
d6e3d8bf-4ab1-4dc9-abd1-2585855323bb | checkpoint | Temperature Logging Completed and Conforming. Attach Results
b27b11ea-6c6b-4acb-8c20-3dbdaad30d3d | section | Any Defect Identified
3b98eaf7-717e-4b08-92e6-2c0f193e079f | checkpoint | Punchlist Completed
802199c4-5558-40fa-a321-79a686c16752 | checkpoint | Repairs Required (if applicable)
8093547a-ee5b-4731-923d-f89189fd48a3 | checkpoint | Repairs Completed as per approved WMS (if applicable)
99cec26b-bb2c-4c06-919d-15ca8569b6d8 | checkpoint | Crack Map Completed
dca1dbb7-0aee-4152-ad0d-39cedf858014 | checkpoint | Any NCR Required (if applicable)
0c873deb-8fee-488b-89cb-f98a99faca72 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
2ab4d46d-a47b-47af-8a0a-812e74c51c85 | section | As-Built Drawings
eb5d1254-5417-4d2b-8863-ea78b86c8750 | checkpoint | As-Built Drawings Completed, Stamped and Attached
f4df64ac-f83e-4122-8da8-59131910cf70 | section | Concrete Strength Test Report
d5a1cee2-30d1-497d-9924-b455d50c06e2 | checkpoint | Concrete Strength Test Report Received
72ed3bf3-f25d-562e-9513-1b400cbb5e33 | textbox | Concrete Test Report
009f2cbd-af76-54bf-99ce-3bcdafdfefd1 | textbox | 7 Day Strength (List all)
bde663bb-3906-572f-9122-80785c06ca94 | textbox | 28 Day Strength (List all)