## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Usage Count | Resource Id
62bdad12-82ae-4271-bc89-2debeb3addae | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v5) |  | Byford U-Beam Stage-1 Casting
1b1b440c-5a18-4c57-ac0c-9074e13c2685 | section | Pre-Pour Checklist
1a291fad-9b7e-4618-93a0-1bfff11e0544 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
d3cf1fd0-2266-4186-8fc0-58b4987b4fac | checkpoint | Shop Drawings approved for Works
739089d1-a6b3-44ac-9d28-2f1b65c29528 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
381a28be-d28b-4a87-ba58-31b91f2e8b80 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
4535edca-caae-4978-8c60-dbbff0de524c | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
f155caf0-47fc-470f-9baf-9a019c6899a8 | checkpoint | Detailed inspection of Mould and cage
da31a7c2-134a-413f-a2dc-ae40b0f9267d | checkpoint | Cover maintained and within tolerance
2fbaa658-283d-4ed1-a0ca-623c94510297 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
89d741db-ee2e-4efe-849d-fde648c3a13e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
7b5d9be1-9495-45a9-b36e-5e5fce14e7c3 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
4226ad74-c696-4624-991e-647aa6d7c7da | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
b1bd01ee-bf01-4eb3-ba7d-f5d47d3d7c8c | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
338d7c9a-0810-491e-9c4f-a41be850ca84 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
77bdb0e3-fe34-4455-94c0-efa27d7e29b1 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
56991184-d5e9-49e0-95db-6c256eeaf4b1 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
b64daf8c-ebe9-4874-992a-f13a7a37a552 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
005796b5-741c-4337-93c9-5aee5626bd77 | checkpoint | Stressing Records subject to Client Review
f60970e2-4f62-4e06-a93e-5565410b5e7e | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
e350b963-0f9a-4eb6-a471-9743147f3667 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
f808d145-74cf-4e61-898a-17a1ee05744e | checkpoint | All Cooling tubes installed as per drawings
142b530e-bd05-4998-b414-b53e9b1c6b2e | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
2b394658-1394-47f6-a143-ee65ca36e942 | checkpoint | QA Engineer Check Completed by
4f178805-d844-4aef-a933-c5ab5b3820ee | checkpoint | Client Inspector (if present)
23b09e8e-9587-48c7-9605-dede3893246c | section | Supervisor Release
14e8143e-2cf8-4ba9-a114-6f4975f44eca | checkpoint | Supervisor Release to Engineering Team
57c80b52-9587-441d-9c29-a0fffe4839bd | section | Casting Checklist
d18bfcb0-a595-4398-952b-bef09b142afa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
f623377d-7c46-4fff-8042-72898547e344 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
7ff25190-997d-44f2-832a-f6176a132e71 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
56660cea-363a-4f7e-b6b9-891127611966 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
fee5efeb-4c2b-4be2-a739-baf477657e8e | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
f93f04ae-c1ef-4d28-983f-2c9a40a1d763 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
d29704c1-9f32-4d81-9166-559caeebe8fd | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
b1bd22bf-c05b-4c5e-8cdb-32f85e4d057e | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
b32bea16-6c2a-40d5-a463-016508daeaec | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
d25bf2ad-1b30-40ef-81ae-0f4dbef15987 | checkpoint | Concrete Placed within allowable time from Batching Plant
1dc102f4-3968-458f-9963-bb68e0952d9d | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
06ea2e2f-31cd-42da-9d33-9e46f81443c5 | checkpoint | Required Finish Applied as per Drawings
9f3d66be-46f7-4975-b47b-3a94d96ca509 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
fe3ae268-bfee-462e-9455-bcf30aa58f80 | checkpoint | Concrete Covered Overnight
17695593-bee1-47e9-a6a8-b7dc84d3351a | checkpoint | Cylinders Stored next to Bed
999aa7e6-348d-4e6f-b273-a9bbccf703ba | section | Stripping Checklist
a46326b8-96e0-4380-8a0a-f1e3be38c99b | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
3c46ded3-5a0b-4f7f-b2d8-6d0869acb1d1 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
2b496297-1898-402a-85c4-689c83056e8f | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
cd1eaf01-af71-4cd8-851e-410233c03dde | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
f6be81c8-a9c5-4a1c-a26e-f95291e3728b | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
0dbe3b4c-238d-47ed-8511-6f9dfbb9f1b6 | checkpoint | Lifted and Handled as per Drawings
0928680d-0759-40f9-b2e7-9b56d224f006 | checkpoint | Product Clearly Labelled
4b3fe9dd-cbaa-4da3-8677-502b75643a21 | checkpoint | Storage as per Approved Temporary Works Drawings
f4488890-d2ae-47ae-8299-bc8de095c648 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
0e83ccb2-f70b-447e-b184-83f7defa145a | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
aacdfc7b-72d3-4647-be28-a66f4c392a6a | checkpoint | Specified Finish Achieved
6f140038-ed3a-4858-aa34-c8fd141f5f78 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
156dede2-65c2-4f2e-be8a-7aa10668d8cb | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
a5c85fa1-d77c-4833-a019-eb75dd874066 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
6c3c734d-65f9-4d56-9e67-35a97c1c5745 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
51c333a4-60d9-4e7e-94fe-c5972f83ce35 | section | Any Defect Identified
3da307c5-9645-4b67-b287-d57ca2c30d45 | checkpoint | Punchlist Completed
0bac4e6b-e34b-4811-bf84-0c8e1b3eb4de | checkpoint | Repairs Required (if applicable)
5673237c-27d7-48ad-942b-095455997022 | checkpoint | Repairs Completed as per approved WMS (if applicable)
7e51243d-e785-4f77-98a0-c71fd631eb49 | checkpoint | Crack Map Completed
f3756da5-1b03-4b3f-a97f-5c03fc33f5ce | checkpoint | Any NCR Required (if applicable)
bead0ee9-bbeb-4f08-abfe-2e807dd4bb44 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
cbfbea84-5a2c-421e-9fe4-2182dbad39ef | section | As-Built Drawings
54cfb20e-db41-4029-8e55-03cef3c531ef | checkpoint | As-Built Drawings Completed, Stamped and Attached
61cd656f-f572-4033-840a-7ff10581198b | section | Concrete Strength Test Report
0af5ff20-170d-4d54-8029-e08e72becd2f | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
b7627a95-520e-4eed-bf3c-55aaf1384183 | section | Transportation Requirements
ce2a2392-113f-4db3-a5bd-d1b227b01e00 | checkpoint | Certificate of Conformance
434267a4-6b35-4c32-8ceb-89d80041ae1a | checkpoint | Inspection Release Certificate
451c2fcf-bd49-4455-86fb-61cad6441e57 | checkpoint | Delivery Notes
e052749c-63fc-448a-9b7d-cddd9c5cc509 | checkpoint | Delivery Docket
e228b169-eaf2-4304-92dc-c8d273bc58be | section | Final Acceptance
1f179a7f-acb5-47b8-bca4-922a73bc5cfe | checkpoint | Completed by
10648b87-b6ba-471d-b585-ef05a81061f0 | checkpoint | Reviewed by
8a87bf67-0165-4c15-9129-339ec8ac9e56 | checkpoint | Client Representative (if applicable)