## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Usage Count | Resource Id
f97c04cb-e84f-4111-a04a-15a36666c047 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v6) |  | Byford U-Beam Stage-1 Casting
5ecc6c1c-8604-488b-b893-7ee4611f2848 | section | Pre-Pour Checklist
9f9daa56-af15-4fb7-b0e9-d9ae33de7925 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
5d540e87-eab5-441c-a2be-0cc9c10e0378 | checkpoint | Shop Drawings approved for Works
414ba0cf-6fb0-46ff-9269-ddd0e826dc65 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
0453c80c-e6dd-4dcb-b765-55d9ca47a5d0 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
5644c2c3-e7c8-46f8-9b92-f2c0b489cde8 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
911b3c55-93ce-4666-9242-57c7d7d1f5e9 | checkpoint | Detailed inspection of Mould and cage
0f06d059-05c9-4698-9bcb-f137be4f364e | checkpoint | Cover maintained and within tolerance
dcd24123-1050-49d1-9d9a-81a23c5504e1 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
99195206-d988-4893-8247-217bfbf58f54 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
93c511a8-fbf5-410a-9140-f0ed1b39423d | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
d4ccbce2-2833-4857-aa6c-14b718996fa9 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
4a89e171-783f-4371-9df3-fcc417dcd367 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
5cf50ae2-4781-49dc-ba8b-9675c339f936 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
5327f771-0b17-4cb2-b8b1-d258c7957e46 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
9bb7fc88-b26c-4a88-b866-be7753bca25e | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
e2b78500-542c-4774-bbf6-643274404f5a | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
4785fb5c-fcdd-4346-9bc4-7e4d0890008d | checkpoint | Stressing Records subject to Client Review
c6d4f67b-a6a4-4415-b434-88dcd96b26de | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
fc283d20-3091-490b-bd9c-09cbcfb3d9cf | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
9cdde248-7f53-4e43-951b-81e15a7f707c | checkpoint | All Cooling tubes installed as per drawings
d5311910-5419-4bc5-9be4-bf78cb84a27b | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
cd28d381-d3c5-4247-be4b-16121985c662 | checkpoint | QA Engineer Check Completed by
733e0fcc-dd5b-4e27-99de-d6d96f6044b3 | checkpoint | Client Inspector (if present)
a3755b3d-192a-41b6-84f3-aee03505bdc9 | section | Supervisor Release
d1e2e20f-c83c-43c7-ad1f-f188bd65747a | checkpoint | Supervisor Release to Engineering Team
cccf3d2b-4143-430c-af0d-95b0ae3ce4fa | section | Casting Checklist
9c449893-f5be-46ed-b61e-44ab69dd00f2 | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
db624138-0225-4c2a-8c59-9b127659d4a5 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
d9735afd-36b7-4d6b-bea1-4895a5eb0717 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
7a4ccadc-a99b-4a0d-8b5f-5355224b413d | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
cccd79fe-e913-425a-8dc9-b1a4d1650f69 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
e0ea1b75-9977-427f-8dfd-79c774954f93 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
839c01e8-6987-470b-91bc-6a5aa2e2c0fb | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
6f3f0c7a-574f-4fa3-ae51-ea9b7fc86358 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
08fecb49-d7ee-4cc0-9ec3-6a61a9ba0283 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
a0b025e7-1918-445f-a8b6-abd615b25434 | checkpoint | Concrete Placed within allowable time from Batching Plant
0cf6a427-3c26-4350-ace5-6a2b3659f93d | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
fbb978b0-2e8c-415a-bd95-72daba6e3024 | checkpoint | Required Finish Applied as per Drawings
197f653f-2d71-46c4-898a-2c7edf281f84 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
47801c60-fdda-40b6-a301-68215f3ac1db | checkpoint | Concrete Covered Overnight
1bc262ec-3379-45bc-9e00-366bbb73fde6 | checkpoint | Cylinders Stored next to Bed
44f764bb-6392-4359-8b29-f82646a44088 | section | Stripping Checklist
664561d6-82f6-4179-bc48-c14ce75d9d43 | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
cae13cb1-3c20-46bc-ba7d-bd9c1e6baf99 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
5a499d6a-05e5-42a0-86b6-04ca46735e01 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
b860d7bc-e7e6-4355-b381-b154649a5d25 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
1c6c5b72-2b95-49bf-9397-f269c2dc04f7 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
68e06c43-603f-4e1d-a545-623e6a08ec58 | checkpoint | Lifted and Handled as per Drawings
7aea5fb5-ead9-4ecf-b114-59df6dad46fe | checkpoint | Product Clearly Labelled
2532c7f6-a9f7-4571-a49d-1b86aa1b3a82 | checkpoint | Storage as per Approved Temporary Works Drawings
cf6edfaf-eca0-432b-9a47-c6c950d6e97b | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
37df03c0-f279-4d0c-98c7-f956ac3eecf4 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
726e2bb0-13f5-4cc5-b88a-3b9f8348c5a1 | checkpoint | Specified Finish Achieved
43bdece9-ca5f-478a-96e7-f95e01cbc9ee | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
09838d21-9bce-4ef6-9568-6032533f9391 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
833743b2-cf24-45a0-8ee5-7557cd9a9e23 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
dad62a14-18e5-4d8f-aff6-7ab888755899 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
03b65f75-7bb0-4705-8b96-f20244bdb3a8 | section | Any Defect Identified
5281d86a-d58b-4c3e-a31c-8a88a4998da5 | checkpoint | Punchlist Completed
38c96f34-1901-4f6b-a40f-46985c672747 | checkpoint | Repairs Required (if applicable)
14020edc-6c16-4620-93e3-6e054959d1c9 | checkpoint | Repairs Completed as per approved WMS (if applicable)
b0fc0a74-135a-4bcd-8128-323d5e5c84e8 | checkpoint | Crack Map Completed
c166e15a-9dc8-4c48-9ed8-46596bd63a55 | checkpoint | Any NCR Required (if applicable)
d12433c7-9ac9-4834-9f0b-89c98c65e4a9 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
fc222699-83c8-4e50-9ba6-e5746490d2bf | section | As-Built Drawings
20918cf1-8b82-447d-ba73-21148504474c | checkpoint | As-Built Drawings Completed, Stamped and Attached
36d88ad5-cae2-49e9-bff8-9e7be7dc6b7d | section | Concrete Strength Test Report
1559bdcb-1637-44ea-b976-e0cd99211bf5 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
8b1a3ca2-45cc-4a80-b03a-a4b89b7ff9b6 | section | Transportation Requirements
18010854-bc98-4fbc-9e07-2e68eae08397 | checkpoint | Certificate of Conformance
056f9500-9f6a-492e-a024-80b12bec9e38 | checkpoint | Inspection Release Certificate
3b346d18-e6f6-4829-9639-1ee26a3e03d0 | checkpoint | Delivery Notes
0595c502-0551-4a40-a3a9-00f5ae4d1d3a | checkpoint | Delivery Docket
a7861972-4389-466d-b03a-729d36c2b0ee | section | Final Acceptance
8a4f3352-2178-482c-9694-cc3627eef3e5 | checkpoint | Completed by
be4d2b44-0315-44e5-81ca-0954ad3e460c | checkpoint | Reviewed by
8061f469-6d04-4c41-a87d-23a49468f227 | checkpoint | Client Representative (if applicable)