## toreid1-1
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
aa8a39b0-8aff-444d-8305-94f2d56e26ad |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-1 BN46-E and BN46-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN46-E
9b15b775-b0ed-4e4e-8987-6d76b705f8b2 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-1 BN46-E and BN46-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN46-W
09e7a7a6-7e67-4c7f-b98c-a900047aaa29 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-2 BN43-E and BN43-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN43-E
9fa27af6-5a60-4811-9cd2-5524724d4f93 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-2 BN43-E and BN43-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN43-W
1ee72c3e-ce1b-426f-a083-98392cd0a506 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-3 BN13-E and BN13-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN13-E
d5fd9f63-0f40-4efe-b851-874cab771d80 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-3 BN13-E and BN13-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN13-W
1c0c783e-d24a-4e80-87ab-c9824c9abad0 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-4 BN04-W and BN04-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN04-W
126fe8ae-9817-4e67-b952-e413c62516e4 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-4 BN04-W and BN04-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN04-E
3fe75f77-0205-49dd-9f7f-2e0bc7c59952 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-5 BN01-E and BN01-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN01-E
8ba2cec9-ec60-402e-a9c0-ecbfb0aac885 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-5 BN01-E and BN01-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN01-W
632922d7-d4cb-4829-bce0-3a6fe352b87e |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-6 BN07-W and BN07-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN07-W
d5b71eff-3f7e-4873-82f0-2e22857b53e6 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-6 BN07-W and BN07-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN07-E
b77236ea-0814-4f5a-87ca-e9422cd41d98 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-7 BN10-E and BN10-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN10-E
61cb45d8-220f-45e6-b156-67f50ba49821 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-7 BN10-E and BN10-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN10-W
b6946d03-7a45-4c77-bac4-47e9aa596107 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-8 BN33-W and BN33-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN33-W
3774359c-f0b4-41c7-8146-aefaa551b621 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-8 BN33-W and BN33-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN33-E
e77229ab-aaa1-4423-83d6-5bdb515998ac |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-9 BN38-E and BN38-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN38-E
f5e21f13-cbad-45a9-9ebd-229c5ed8e68f |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-9 BN38-E and BN38-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN38-W
b141ee88-8b0c-4f12-bf8c-0427b6d1d915 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-10 BN33-CE and BN34-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN33-CE
8ca206e1-8fce-41a5-b4ff-49b9c2f06e36 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-10 BN33-CE and BN34-E; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN34-E
a1025218-63a8-41fc-ab60-8553ab89c106 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-11 BN34-CE and BN34-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN34-CE
f2c54c9b-4c07-4fbe-a04a-e48de97426f3 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-11 BN34-CE and BN34-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN34-W
3aadc3c5-7aba-4bca-aa24-7d8abdb3fd28 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-12 BN42-E and BN06-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN42-E
ffe2ec7c-c13d-44e6-b494-5cb33fd93aab |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-12 BN42-E and BN06-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN06-W
875616b4-ae2d-4f02-9e51-d5649d1a1d0d |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-13 Wungong Bridge B01-E and B01-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist Wungong B01-E
ba01dbb2-0cc5-4d9b-9468-593f29069566 |  | pass | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-13 Wungong Bridge B01-E and B01-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist Wungong B01-W
4236285d-3558-4d21-91b1-c2135ad60622 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-14 BN33-CW and BN30-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN33-CW
9791ad64-f5ca-42c6-a806-fff00e647730 |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-14 BN33-CW and BN30-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN30-W
cda56796-64ac-4b77-a02e-fcf5a76207dc |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-15 BN34-CW and BN29-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN34-CW
7c306945-6c81-434a-ab1a-e50b74f15adc |  | work-in-progress | 20346279188fdb0c8c22d4e73836c53288bd77337972682283ca02231864161c | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Cast-15 BN34-CW and BN29-W; Tier 3: Byford U-Beam Stage-2 Casting Checklist BN29-W