## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Courtyards under paving |  |  |  |  | Yes | Courtyards under paving | 01cc59cb-092b-4110-b508-779ffdea9ceb
checkpoint-status |  |  | checkpoint | Apply primer
checklist-flat |  |  | checklist | Level 1 plant room/L.L roof plant room |  |  |  |  | Yes | Level 1 plant room/L.L roof plant room | 0ad0094c-5857-4221-80ac-f4d99f23a02d
checkpoint-status |  |  | checkpoint | Apply tremproof 200EC primer
checkpoint-status |  |  | checkpoint | Apply Vulkem 360 base coat
checkpoint-status |  |  | checkpoint | Apply Vulkem 951 top coat
checklist-flat |  |  | checklist | Apply 2 coats Vulkem NEM 150mm upstands |  |  |  |  | Yes | Apply 2 coats Vulkem NEM 150mm upstands | 14c29db1-5992-4bc6-967e-3d20b1633135
checklist-flat |  |  | checklist | Stairs/BOH/Dryares |  |  |  |  | Yes | Stairs/BOH/Dryares | 17bcf864-5281-434c-9c8a-17c8af553a92
checkpoint-status |  |  | checkpoint | Apply 2 coats Flowcoat OP light grey to 0.35 DFT
checklist-sectioned |  |  | checklist | Standard ITP - Aus Standards - Wet Area Waterproofing |  |  |  |  | Yes | Standard ITP - Aus Standards - Wet Area Waterproofing | 228fc213-18b9-48b1-8fbf-75d68b017533
checkpoint-group |  |  | section | 1 - Pre-Commencement Activities
checkpoint-status |  |  | checkpoint | Project Self-Assessment Tool- BU Project Audits -
checkpoint-status |  |  | checkpoint | 1.1 - Submission of Waterproofing System products
label | 6f093118-99a9-5bd3-af4e-b3b5a47e78d0 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | 4d9766db-1063-5d71-9ad0-6e4e154bd4f6 |  | note | Acceptance Criteria - Approval of Waterproofing System - confirmation of compatibility with substrate and follow-on trade requirements
label | c6a816de-92c9-5381-80c9-414e4c629cfb |  | note | Test/ Inspection - Review & Verify
label | 8d7dea86-ecf1-5ed7-b916-d6fca59fb7ac |  | note | Test/Inspection Frequency - One-off prior to commencement
label | a3a27c52-bd38-5fd7-9dd6-d1000368ad92 |  | note | Inspection: Subcontractor - WS (I)
label | 5735740d-7eb0-535b-9068-056260dd2d7e |  | note | Inspection: John Holland - PE (R)
label | 5d76cd7a-c090-5799-8596-0c767316cde4 |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.2 - Submission of Waterproofing System Warranties
label | 6ddf78af-9a17-5be2-8f1e-9b21ff299d4d |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | 96f0c1ed-f9ae-534d-b719-8d5240becdc1 |  | note | Acceptance Criteria - Warranty is for required duration and relevant party
label | 8220e93f-e774-5f04-b9dc-8f37f8dcbeaa |  | note | Test/ Inspection - Review & Verify
label | d16e5ea8-9c0c-5a64-ae7f-e4f4678983bf |  | note | Test/Inspection Frequency - One-off prior to commencement
label | 12da7609-eb78-57e0-a616-a940926be7f4 |  | note | Inspection: Subcontractor - WS (I)
label | dc0f6f67-9242-525b-bcd9-ebe959c9e553 |  | note | Inspection: John Holland - PE (R)
label | a5015fd1-78b5-5a03-96ab-d88011d396c1 |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.3 - Submission of Manufacturer's Application Method Statement (MAMS)
label | 60a74713-80a4-5fb4-ba5c-9faefdda0a99 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | c0975b77-7816-57c8-84f4-a2a9d33b28b6 |  | note | Acceptance Criteria - Approval of MAMS by Waterproofing Consultant
label | d7a7b636-8b61-51a6-a72e-5f8f6bd38776 |  | note | Test/ Inspection - Review & Verify
label | 9aea9d67-50b6-5e95-9cfd-8e185a1e809b |  | note | Test/Inspection Frequency - One-off prior to commencement
label | ea0c9c11-d0d5-53a8-a796-0cf2cdd1dee2 |  | note | Inspection: Subcontractor - WS (I)
label | 8ffaa8d8-8205-5b64-8e5e-d58d663eaf14 |  | note | Inspection: John Holland - PE (R)
label | 4be8152d-a93c-594e-9c27-9bed14ddf65e |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.4 - Submission of AMS and WRA Content - including Safety Data Sheets for chemicals
label | 850fd7a0-7d3e-5168-ab85-76b1817b6808 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | afcba0d4-95fd-5305-a1e3-c74b268a5b5d |  | note | Acceptance Criteria - Approval of AMSs and WRAs
label | 0266f3a8-d8f8-5bb5-950d-e20cc625cf06 |  | note | Test/ Inspection - Review & Verify
label | c9768110-ff62-53f2-9b21-200ff9606f4d |  | note | Test/Inspection Frequency - One-off prior to commencement
label | 0ce60546-80a5-5f4c-9ce2-17cd5efa62dd |  | note | Inspection: Subcontractor - WS (I)
label | eae0dddb-37a8-5377-8a1d-b1114220a070 |  | note | Inspection: John Holland - PE (R)
label | ad5fb686-1685-5c97-9394-341d36ff4e68 |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.5 - Waterproofing company to demonstrate Competency of Applicators
label | a603c104-70d1-5b02-9445-2d404ad6d258 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | fc3f48e3-38b1-5fd7-978f-c461fc7b446c |  | note | Acceptance Criteria - Competency scheme document, register of applicators
label | a52a7591-e7d2-5af6-aa36-8c25542339a8 |  | note | Test/ Inspection - Review & Verify
label | 76e092bb-fc88-58d1-b5f6-b18361a5f879 |  | note | Test/Inspection Frequency - One-off prior to commencement
label | f1701295-a55d-53b4-8b0b-bdaa5451c582 |  | note | Inspection: Subcontractor - WS (I)
label | bec80d59-81bf-5f2b-92aa-fcd451acaaea |  | note | Inspection: John Holland - PE (R)
label | fb1a3c85-70ff-523c-81be-513f3e102853 |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.6 - Detailed design complete - including shop details
label | 0971256f-83bc-595d-a60e-0e6d4bb3d4e7 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | ae43b0bc-757f-56c3-8184-51702f6441d7 |  | note | Acceptance Criteria - Approval of shop drawings
label | 80da7c98-4141-5ec1-8773-d8193592fe95 |  | note | Test/ Inspection - Review & Verify
label | 78bfae7f-4a97-5b19-8fd5-0191f8e8570b |  | note | Test/Inspection Frequency - One-off prior to commencement
label | 9f42db96-a1b7-5e32-bf7d-54d97a891771 |  | note | Inspection: Subcontractor - WS (I)
label | c105b2df-fcf3-5dff-8b48-26f717424701 |  | note | Inspection: John Holland - PE (R)
label | 2f8041e9-da5b-58bc-b9c6-592026dd9e68 |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.7 - Testing equipment details - and calibration records (if electronic leak detection specified)
label | 713dfe55-6176-585e-a799-48e6ec2b4e3e |  | note | Specification Reference - AS3740 App C3 / GBA-SPE-AR-AS-0001
label | 40800fd4-39de-5d7e-9819-a475517f7e00 |  | note | Acceptance Criteria - In calibration
label | 6053e470-3bfa-5988-b621-c96545245ca1 |  | note | Test/ Inspection - Review & Verify
label | d239e3db-f278-5666-bf84-7b6181e8b9ea |  | note | Test/Inspection Frequency - One-off prior to commencement
label | 771052f6-4b2f-5a1a-ab20-d50d8b44bfc4 |  | note | Inspection: Subcontractor - WS (I)
label | 80175da7-2490-5340-94b2-3d038f6df0e0 |  | note | Inspection: John Holland - PE (R)
label | 3d2233e4-8ebd-5e1f-99d3-e9c83e424b0e |  | note | Inspection: Nominated Authority - WC (R)
checkpoint-status |  |  | checkpoint | 1.8 - First of Type Inspection -joint witness and sign-off on Prototype or First Install with membrane system representative (as below)
label | 008998e3-6468-5ac5-9486-296b425efbaf |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | ffa05eab-2b3f-5dcc-84f8-3002df4bd2a6 |  | note | Acceptance Criteria - Joint acceptance of the First of Type and close-out of any agreed issues
label | 5fcee83b-9e1d-5779-a2f6-3e957dbf4b18 |  | note | Test/ Inspection - Review & Verify
label | 3802be7a-3ad1-55dc-aac7-57bfd39307cc |  | note | Test/Inspection Frequency - One-off prior to commencement
label | ebabfbc3-9716-5530-bbf8-1025bccdcf0a |  | note | Inspection: Subcontractor - WS (H)
label | 99814c0b-4404-52b5-aaf0-9974aad71a8b |  | note | Inspection: John Holland - PE (H)
label | 340f49f1-aaee-5c91-a08a-18ca6e63ab6c |  | note | Inspection: Nominated Authority - WC (H)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Construction Inspections
checkpoint-status |  |  | checkpoint | 2.1 - Install Concrete substrate and wall system
label | cfb3dd58-137e-5402-a270-5c7abc42941b |  | note | Specification Reference - AS3600 / GBA-SPE-AR-AS-0001
label | fd7b894b-d712-525b-bea6-d285454fe19e |  | note | Acceptance Criteria - Project specification criteria
label | 0de9e403-5086-548b-af58-e028b864ab29 |  | note | Test/ Inspection - Installation and Inspection
label | 0a0c8bc2-6c6f-5d4f-a59b-3eca7832ca97 |  | note | Test/Inspection Frequency - Each wet area
label | 028c2920-b2a3-5f77-87aa-07ffcb4f42fe |  | note | Inspection: Subcontractor - SS (I)
label | 1efa6ef6-ae85-5977-a0ac-0e779f14029b |  | note | Inspection: John Holland - PE (S)
label | 2daf3233-41cc-557e-85cf-c045f6a968d0 |  | note | Records & Comments - Project Self-Assessment Tool- BU Project Audits
checkpoint-status |  |  | checkpoint | 2.2 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
label | 85ca0317-6151-5315-9cec-cbae96ace255 |  | note | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
label | 55b825b7-085e-5127-ada0-edc57999f298 |  | note | Acceptance Criteria - Slabs require a relative humidity of less than 75%
label | acf9c02e-b2b6-5f9c-ae9e-83f21987c71d |  | note | Test/ Inspection - Measurement
label | 77132e1e-89ff-5f68-8f38-937f4958fd24 |  | note | Test/Inspection Frequency - Each wet area
label | 20e31e75-da79-59b3-be58-2b7cde5f3651 |  | note | Inspection: Subcontractor - WS (I)
label | 181853b4-093e-5cca-95d7-8daa692db860 |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.3 - Drainage installation - puddle flange installation
label | 3112353e-a6ca-5da5-b860-a4415a869725 |  | note | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
label | 0ad56244-3e65-52b2-8ada-0bbb95cdc4b4 |  | note | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
label | 0f544c6d-9485-5786-a164-078f7e7a1782 |  | note | Test/ Inspection - Installation and Inspection
label | 2b4aa9ba-7582-581a-a6e8-272dd336511c |  | note | Test/Inspection Frequency - Each wet area
label | 6af08bfa-ec14-5532-84a1-ed0a2c8f7269 |  | note | Inspection: Subcontractor - HS (I)
label | 31a579fe-3eee-5135-b3e2-e96f65f5eb42 |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.4 - Substrate condition Inspection
label | e2fb6f54-07b0-5bd3-b2ab-5e4db4827b6f |  | note | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
label | a72912a7-015a-5792-bd91-09a47655deb1 |  | note | Acceptance Criteria - Clean and free of laitence/debris, holes patched
label | ec5102e3-ecbb-568f-8943-76be35c79e0e |  | note | Test/ Inspection - Inspection
label | f83fd6a1-2a6a-5bbd-a1e1-ae9cd956e8e4 |  | note | Test/Inspection Frequency - Each wet area
label | 87084b74-70ff-5e80-92d8-0926a77605a4 |  | note | Inspection: Subcontractor - WS (I)
label | 7547851b-1bc9-5027-be41-57e103c6c04f |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.5 - Substrate falls - measurement - note actual fall on checklist, take photos
label | 481c01de-69da-54b8-9c70-696772ccd638 |  | note | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
label | 752de7b1-4dad-526b-a8a9-6f28f1bb5087 |  | note | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
label | 3770c0e8-dbca-51c1-8b85-37000998c8a8 |  | note | Test/ Inspection - Measurement
label | 68ad544f-5268-5e66-b1a7-de4f77e362d3 |  | note | Test/Inspection Frequency - Each wet area
label | 14bb07ca-f0a2-5a6d-abef-67c3b94a38dd |  | note | Inspection: Subcontractor - WS (I)
label | afdca61b-f464-5b8f-9e0e-b73775a29f12 |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.6 - Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
label | d8d49e0c-d246-598c-80b3-01f0ab771509 |  | note | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
label | 0e67a143-e195-5b20-a533-770a718bdcac |  | note | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
label | 5307c265-1201-5b8c-9e30-9bdf5c567273 |  | note | Test/ Inspection - Installation and Inspection
label | cf821021-1e77-57b0-b6b4-303b5a0ac8e1 |  | note | Test/Inspection Frequency - Each wet area
label | 74f3680f-ca7b-56e4-b84d-6c1ae163cfb2 |  | note | Inspection: Subcontractor - WS (I)
label | 090fe7bd-a6f0-5ffb-8e2f-3d11a71ffb4a |  | note | Inspection: John Holland - PE (S)
text | a8c980a6-2060-5065-ba91-943df2a9cbc6 |  | textbox | Records & Comments - Measured fall:
checkpoint-status |  |  | checkpoint | 2.7 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
label | de04c6ef-df36-58c7-837c-a0b0b5fa2192 |  | note | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
label | 706806d3-6d77-55f2-abb9-abc200176bbc |  | note | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
label | 2302b936-7e0c-549a-816c-c4376290817d |  | note | Test/ Inspection - Measurement
label | b261f3c3-056b-5194-8932-b28bdce88522 |  | note | Test/Inspection Frequency - Each wet area
label | 650f98ad-a5f4-52ea-b869-f8a1d7eb4486 |  | note | Inspection: Subcontractor - WS (I)
label | 8225e3d4-49df-5af8-b98a-6e428b17abe9 |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.8 - Subcontractor Pre-placement Check: Confirm equipment, personnel and temperature is acceptable for membrane installation - note equipment ref, name of applicators and temperature on checklist
label | 96fcc4a2-d739-5893-aed1-ac97e8bf3679 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | b6c6c891-383b-5918-8c2e-cd067ae56e07 |  | note | Acceptance Criteria - Everything ready to install
label | 551b6088-222d-569e-81cc-122fcc647e86 |  | note | Test/ Inspection - Review & Verify
label | 67cb20fb-4ad7-5cdd-b27c-f75f0f2d669c |  | note | Test/Inspection Frequency - Each wet area
label | 55ecb822-0c48-5d41-bc76-0186c13828b0 |  | note | Inspection: Subcontractor - WS (I)
label | 520b8986-5aee-5619-bc96-54977d132498 |  | note | Inspection: John Holland - PE (S)
text | fd244bd8-c64b-5bf2-abe9-1ff614bb86a2 |  | textbox | Records & Comments - Required size:
text | a9278808-c6fb-5029-a583-f71728c9301c |  | textbox | Measured size:
checkpoint-status |  |  | checkpoint | 2.9 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
label | 0c5cd41a-adc3-526d-8475-07d8ddaa3985 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | c0103be7-cef8-5a4f-a96d-6136cb89f195 |  | note | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
label | 9411cde0-97f2-5cef-8326-650477f83820 |  | note | Test/ Inspection - Visual Inspection
label | 166b756d-004f-5681-a94d-96fde3c946b6 |  | note | Test/Inspection Frequency - Each wet area
label | 9d0436c3-908e-57d8-b9ed-2267ff498d99 |  | note | Inspection: Subcontractor - WS (H)
label | 8d43ec98-e0cb-5294-a9f2-f44ac650f0cf |  | note | Inspection: John Holland - PE (H)
text | 58dfc272-4439-5736-b51b-2693b65e603e |  | textbox | Records & Comments - Applicator Names:
text | 49577584-3669-51b8-8175-b361cd4d5d4a |  | textbox | Temperature at placement:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - 100% Witness Point: Watch the Subcontractor apply primer in line with MAMS - take photograph of primer container with technical details and photo/video of application
label | 330bd17c-b8c6-5df7-a173-d80cbf867df9 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | 01c4d632-6715-51ce-87cd-2fc4e05523d1 |  | note | Acceptance Criteria - Correct primer applied
label | d41bc991-00ba-5157-a327-a9db09a5b2ae |  | note | Test/ Inspection - Installation and Inspection
label | 300ce177-ab8a-5448-8924-33d39108056f |  | note | Test/Inspection Frequency - Each wet area
label | 4ceb8057-87dc-5d75-b692-8a88617af2f5 |  | note | Inspection: Subcontractor - WS (I)
label | e773b966-2069-5983-9789-a156700907e1 |  | note | Inspection: John Holland - PE (W)
checkpoint-status |  |  | checkpoint | 2.11 - 100% Witness Point: Watch the Subcontractor apply membrane layers in line with MAMS and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
label | 5b5df964-5e5a-54b0-acd9-5f29a63f1960 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | 71a0bce3-e460-5975-973c-47553276cfbd |  | note | Acceptance Criteria - Each layer applied in line with MAMS requirements, timing between layers in line with the MAMS
label | 992c8bb7-aab1-5670-8b66-3c364cc17b56 |  | note | Test/ Inspection - Installation and Inspection
label | 00b69f48-f357-5707-8943-e6c25abb7345 |  | note | Test/Inspection Frequency - Each wet area
label | 22772c0e-e40c-599c-a85f-07a00c22d109 |  | note | Inspection: Subcontractor - WS (I)
label | bc537db5-8d7e-5e5b-ac9a-2e8caf7a0b74 |  | note | Inspection: John Holland - PE (W)
checkpoint-status |  |  | checkpoint | 2.12 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
label | ba3dba0c-10a6-50d4-adeb-590068469182 |  | note | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
label | 0f4e498a-9d79-51eb-80bd-16d104a29fd1 |  | note | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
label | f34132aa-199e-5995-b820-6f3f0c3ed77e |  | note | Test/ Inspection - Installation and Inspection
label | 6e852438-f48c-50e1-9e86-839474cc931b |  | note | Test/Inspection Frequency - Each wet area
label | de8ad2ce-003c-5e3b-9cf3-4365e5ed7fa8 |  | note | Inspection: Subcontractor - WS (H)
label | e86356a6-0b40-5549-bae3-b5d214af1154 |  | note | Inspection: John Holland - PE (H)
text | f284ba1f-3ca6-5055-afd3-c48f57e65780 |  | textbox | Records & Comments - Layer 1 time:
text | fa1af8e4-2411-59f9-b60b-d7bd4777739b |  | textbox | Layer 2 time:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.13 - Membrane compound setting time - note planned and actual setting time on checklist
label | 6f9b6518-2ee7-559a-a3b8-5040ccd66ecb |  | note | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
label | 19e66bd9-86d0-52ca-8964-53ba27e06c65 |  | note | Test/ Inspection - Installation and Inspection
label | 2b733462-0a7e-5956-a749-8b737ec2720f |  | note | Test/Inspection Frequency - Each wet area
label | 87340120-e7c9-57a2-8393-ad4cb948ea19 |  | note | Inspection: Subcontractor - WS (I)
label | 8a247427-88bb-59ab-92fb-289e8a5f6192 |  | note | Inspection: John Holland - PE (S)
checkpoint-status |  |  | checkpoint | 2.14 - HOLD POINT: Confirm that setting time for membrane has been complied with
label | 806091a2-5c02-5463-b762-bf88537b3d8a |  | note | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
label | 43a8a105-6eb8-590c-abc7-f7e6382590ef |  | note | Test/ Inspection - Installation and Inspection
label | 0ce81d9d-ce3e-5b27-b48a-6fde3bbd02ec |  | note | Test/Inspection Frequency - Each wet area
label | 7c5e4942-ac19-52d5-878e-bf04d49fbb68 |  | note | Inspection: Subcontractor - WS (H)
label | 860bd8dc-99c9-51c1-ad0f-4f8eb3dc28e2 |  | note | Inspection: John Holland - PE (H)
text | 226c061e-6344-5dc5-acaa-c1f37497253c |  | textbox | Records & Comments - Planned setting time:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.15 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
label | 92207366-3eaf-5d84-b52a-f74571274e66 |  | note | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
label | e8217b37-78e1-54fd-a434-fd87718daf8d |  | note | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
label | a05122d2-20e9-5449-b9dc-65c5b97f2af8 |  | note | Test/ Inspection - Test
label | bc649829-5c96-5d82-ba34-ad237e6094c6 |  | note | Test/Inspection Frequency - Each wet area
label | a90de1a7-f5fd-5fc3-8fb0-b42299f735bd |  | note | Inspection: Subcontractor - WS (I)
label | bea02841-3a11-51ef-8d17-297976dcb599 |  | note | Inspection: John Holland - PE (W)
label | 1b042be0-18a7-5090-9536-2b3864198cc7 |  | note | Inspection: Nominated Authority - DC (W)
text | 753659b0-ff7a-5daa-a88f-840029a2477b |  | textbox | Records & Comments - Observed setting time:
checkpoint-status |  |  | checkpoint | 2.16 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure that they do not damage the membrane system.
label | f710e785-c6e6-58ef-9da1-33d658cad451 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | 2d6ab6c6-bb0c-53fa-9b6b-693159f04489 |  | note | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
label | 6c9087db-200f-50b5-a708-f7cf2d440ce0 |  | note | Test/ Inspection - Installation and Inspection
label | afd2192d-da1d-5ea6-a945-ff3a36822215 |  | note | Test/Inspection Frequency - Each wet area
label | 43c1576e-4bf9-573b-98f3-fc15b56aed29 |  | note | Inspection: Subcontractor - WS (I)
label | 8b53d9db-ec94-5315-b8aa-fdce58e9c541 |  | note | Inspection: John Holland - PE (W)
checkpoint-group |  |  | section | 3 - Close-Out
checkpoint-status |  |  | checkpoint | 3.1 - ITP close-out.
label | 3f231675-555e-5718-96a8-886a24d12e39 |  | note | Specification Reference - GBA-SPE-AR-AS-0001
label | cb596300-b4ac-567d-a927-caf3eac73b18 |  | note | Acceptance Criteria - All prior items of this ITP have been complied with.
label | de6d3e28-b094-5cfd-b7e3-184dec4b9837 |  | note | Test/Inspection Frequency - Each Lot
label | fcd865b0-74b7-5f79-929c-149104a75e89 |  | note | Inspection: John Holland - QR (R)
label | 35a0c847-eb1e-5865-a94f-fb840236e901 |  | note | Records & Comments - All records loaded into the Work Lot System and Verified.
checklist-flat |  |  | checklist | Epoxy screeds to fall wet area setdowns |  |  |  |  | Yes | Epoxy screeds to fall wet area setdowns | 22f9ffd3-1302-4e49-a3db-0beca43cef66
checkpoint-status |  |  | checkpoint | Install screed to fall using Hychem GP epoxy/sand mortar.
checklist-flat |  |  | checklist | Epoxy wall coating to ensuites 74 @ 23sqm per cell |  |  |  |  | Yes | Epoxy wall coating to ensuites 74 @ 23sqm per cell | 2fbd8bbc-cefb-4a0d-aed2-49b896ba6172
checkpoint-status |  |  | checkpoint | Mechanicall sand walls
checkpoint-status |  |  | checkpoint | Prime with Hychem GP epoxy resin
checkpoint-status |  |  | checkpoint | Apply 2 coats Hychem SF 20v epoxy
checklist-flat |  |  | checklist | Protection |  |  |  |  | Yes | Protection | 3e902051-f6eb-48d0-8bdf-a8244ca8018e
checkpoint-status |  |  | checkpoint | Supply and install protection to horizontal surfaces
checkpoint-status |  |  | checkpoint | Remove protection
checklist-flat |  |  | checklist | Protection to BOH |  |  |  |  | Yes | Protection to BOH | 534670e5-15f5-4463-936b-c8e6e58cb76d
checkpoint-status |  |  | checkpoint | Install protection to horizontal surfaces
checkpoint-status |  |  | checkpoint | Remove Protection
checklist-flat |  |  | checklist | Trims to ensuite doorways |  |  |  |  | Yes | Trims to ensuite doorways | 5e08dbd3-ff39-4999-9a1d-b2fec8949b42
checkpoint-status |  |  | checkpoint | Supply and install trims to doorways
checklist-flat |  |  | checklist | Protection |  |  |  |  | Yes | Protection | 6c8d0b28-cac8-439b-9e4d-3a0b0c2ec159
checkpoint-status |  |  | checkpoint | Install protection to horizontal surfaces
checklist-flat |  |  | checklist | Rmove protection |  |  |  |  | Yes | Rmove protection | 8221db8d-0e79-4104-98f0-fd278d9fa600
checklist-flat |  |  | checklist | L.L Roof plant |  |  |  |  | Yes | L.L Roof plant | 837ba23d-be6d-40e9-af7d-823079f9b058
checkpoint-status |  |  | checkpoint | Apply Tremproof 200EC primer
checkpoint-status |  |  | checkpoint | Apply Vulkem 360 base coat
checkpoint-status |  |  | checkpoint | Apply 951 top coat 150mm upstands
checklist-flat |  |  | checklist | Under wet area screeds (50mm Set Downs) |  |  |  |  | Yes | Under wet area screeds (50mm Set Downs) | 84ae6cda-03c5-49aa-b170-ab7df954a80f
checkpoint-status |  |  | checkpoint | Caulk to junctions
checkpoint-status |  |  | checkpoint | Apply 2 coats Hyclad E
checkpoint-status |  |  | checkpoint | Return 150mm above screed
checklist-flat |  |  | checklist | Roof Areas |  |  |  |  | Yes | Roof Areas | 97042648-9ed2-4f44-a89f-d9cb3f2d3faa
checkpoint-status |  |  | checkpoint | Apply Primer
checkpoint-status |  |  | checkpoint | Apply base layer 3mm
checkpoint-status |  |  | checkpoint | Apply top layer 4mm mineral finish
checkpoint-status |  |  | checkpoint | Pressure strip termination at 150mm
checkpoint-status |  |  | checkpoint | ILD testing
checklist-flat |  |  | checklist | FLGE 505.2 Deckshield ID 1.5mm |  |  |  |  | Yes | FLGE 505.2 Deckshield ID 1.5mm | 9dd631d5-c627-4b5f-8186-1e033a1682df
checkpoint-status |  |  | checkpoint | Apply flowcrete flowprime and broadcast aggregate
checkpoint-status |  |  | checkpoint | Apply seal coat of Flowcoat OP
checkpoint-status |  |  | checkpoint | Apply top coat of Deckshield UV
checklist-flat |  |  | checklist | Coving |  |  |  |  | Yes | Coving | ad55fd8b-f2b2-4fa3-8d08-33b983925177
checkpoint-status |  |  | checkpoint | Install coving (40mm radius) vinyl flake 150mm high.
checklist-flat |  |  | checklist | FLGE 505.3 Dark grey Deckshield ID 2mm |  |  |  |  | Yes | FLGE 505.3 Dark grey Deckshield ID 2mm | bae28371-6a97-4258-8b8d-d4674ad4fd28
checkpoint-status |  |  | checkpoint | Apply 2 coats Flowprime and broadcast with aggregate
checkpoint-status |  |  | checkpoint | Apply 1 coat Flowcoat OP
checkpoint-status |  |  | checkpoint | Apply1 coat Deckshield UV
checklist-flat |  |  | checklist | Below ground tremco system |  |  |  |  | Yes | Below ground tremco system | c40fc633-bbb6-4404-93aa-2fd9ba180bf6
checkpoint-status |  |  | checkpoint | Tremco Paraseal system installed.
checkpoint-status |  |  | checkpoint | Pressure strip install
checkpoint-status |  |  | checkpoint | Install Versidrain 8 geo
checklist-flat |  |  | checklist | Car Park Sealer |  |  |  |  | Yes | Car Park Sealer | d83872f8-6614-4f90-9e82-6ee504952cd3
checkpoint-status |  |  | checkpoint | Apply Carpark sealer P4 rating
checklist-flat |  |  | checklist | Vinyl flake epoxy system wet area setdowns |  |  |  |  | Yes | Vinyl flake epoxy system wet area setdowns | f1a51230-f35e-41ce-9e23-eed3f6800fdc
checkpoint-status |  |  | checkpoint | Prime screeds
checkpoint-status |  |  | checkpoint | Apply 2 coats Hychem SF20 epoxy
checkpoint-status |  |  | checkpoint | Apply vinyl flakes
checkpoint-status |  |  | checkpoint | Apply 2 coats Hychem PA sealer includes 150mm upstands
checklist-flat |  |  | checklist | Sealing of Pour Joints |  |  |  |  | Yes | Sealing of Pour Joints | f8287ec0-60d9-4e8d-95d6-58b4e050f22a
checkpoint-status |  |  | checkpoint | Supply and install Enviro joint band
checklist-flat |  |  | checklist | ILD |  |  |  |  | Yes | ILD | f9909915-bd29-4e89-8450-a7d41a3020d7
checkpoint-status |  |  | checkpoint | ILD testing