## Planning ITP
ITP NAME: |  | Standard ITP - Aus Standards - Wet Area Waterproofing
AS 3740-2021 (Waterproofing of Domestic Wet Areas); ASTM F2170 Standard Test Method for Determining Relative Humidity in Concrete Floor Slabs Using In Situ Probes; ETN-00006 Waterproofing Systems
ITP No. | [5 empty] | AMS Title |  |  |  |  | AMS Ref
Revision No. |  |  | Date |  |  | Lot Number
Prepared by | [5 empty] | Reviewed by |  |  |  |  | Approved by
Item No. | Operational Activities |  |  | Verification | [5 empty] | Inspection | [5 empty] | Records & Comments
|  |  |  | Specification Reference (JH) | Specification Reference | Acceptance Criteria | Test/ Inspection | Test/Inspection Frequency |  | Subcontractor |  | John Holland |  | Nominated Authority
[10 empty] | Key | Sign/Date | Key | Sign/Date | Key | Sign/Date
1 | Pre-Commencement Activities
1.1 | Submission of Waterproofing System products |  |  | JHG ETN-00006 | GBA-SPE-AR-AS-0001 | Approval of Waterproofing System - confirmation of compatibility with substrate and follow-on trade requirements | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.2 | Submission of Waterproofing System Warranties |  |  | JHG ETN-00006 3.2 / 3.3 | GBA-SPE-AR-AS-0001 | Warranty is for required duration and relevant party | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.3 | Submission of Manufacturer's Application Method Statement (MAMS) |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Approval of MAMS by Waterproofing Consultant | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.4 | Submission of AMS and WRA Content - including Safety Data Sheets for chemicals |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Approval of AMSs and WRAs | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.5 | Waterproofing company to demonstrate Competency of Applicators |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Competency scheme document, register of applicators | Review & Verify | One-off prior to commencement |  | WS (I) |  | PE (R) |  | WC (R)
1.6 | Detailed design complete - including shop details |  |  | JHG ETN-00006 3.1 | GBA-SPE-AR-AS-0001 | Approval of shop drawings | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.7 | Testing equipment details - and calibration records (if electronic leak detection specified) |  |  | AS3740 App C3 | AS3740 App C3 / GBA-SPE-AR-AS-0001 | In calibration | Review & Verify | One-off prior to commencement | Dropdown | WS (I) |  | PE (R) |  | WC (R)
1.8 | First of Type Inspection -joint witness and sign-off on Prototype or First Install with membrane system representative (as below) |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Joint acceptance of the First of Type and close-out of any agreed issues | Review & Verify | One-off prior to commencement | Dropdown | WS (H) |  | PE (H) |  | WC (H)
2 | Construction Inspections
2.1 | Install Concrete substrate and wall system |  |  | AS3600 | AS3600 / GBA-SPE-AR-AS-0001 | Project specification criteria | Installation and Inspection | Each wet area | Dropdown | SS (I) |  | PE (S)
2.2 | Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout |  |  | ASTM F2170, AS3740 cl 4.4.3, JHG ETN-00006 3.4 | ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001 | Slabs require a relative humidity of less than 75% | Measurement | Each wet area | Dropdown | WS (I) |  | PE (S)
2.3 | Drainage installation - puddle flange installation |  |  | AS3740 fig 4.3.1 | AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001 | Installed rebated in substrate, undamaged, capped to prevent ingress of debris | Installation and Inspection | Each wet area | Dropdown | HS (I) |  | PE (S)
2.4 | Substrate condition Inspection |  |  | AS3740 cl 4.4.1, JHG ETN-00006 3.4 | AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001 | Clean and free of laitence/debris, holes patched | Inspection | Each wet area | Dropdown | WS (I) |  | PE (S)
2.5 | Substrate falls - measurement - note actual fall on checklist, take photos |  |  | AS3740 cl 2.3.1 / 2.3.2 | AS3740 cl 2.3.1 / 2.3.2 | Falls are to the drain - min 1:80 in shower area, otherwise 1:100 | Measurement | Each wet area | Dropdown | WS (I) |  | PE (S) |  |  |  | Measured fall: . . . . . .
2.6 | Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation. |  |  | AS3740 4.5.3, 4.8, 4.9, 4.12 | AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001 | Waterbars in line with approved shop drawings and AS3740 requirements. | Installation and Inspection | Each wet area | Dropdown | WS (I) |  | PE (S)
2.7 | Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size |  |  | AS3740 4.5.3, 4.10 | AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001 | Bond Breaker/fillet to XXXX size based on class of membrane | Measurement | Each wet area | Dropdown | WS (I) |  | PE (S) |  |  |  | Required size: . . . . . . Measured size: . . . . . .
2.8 | Subcoontractor Pre-placement Check: Confirm equipment, personnel and temperature is acceptable for membrane installation - note equipment ref, name of applicators and temperature on checklist |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Everything ready to install | Review & Verify | Each wet area |  | WS (I) |  | PE (S) |  |  |  | Applicator Names: . . . . . . Temperature at placement: . . . . . .
2.9 | HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Previous steps complete in line with the Australian Standards, specifications and ETN | Visual Inspection | Each wet area |  | WS (H) |  | PE (H)
2.10 | 100% Witness Point: Watch the Subcontractor apply primer in line with MAMS - take photograph of primer container with technical details and photo/video of application |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Correct primer applied | Installation and Inspection | Each wet area |  | WS (I) |  | PE (W)
2.11 | 100% Witness Point: Watch the Subcontractor apply membrane layers in line with MAMS and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist |  |  | JHG ETN-00006 3.3 | GBA-SPE-AR-AS-0001 | Each layer applied in line with MAMS requirements, timing between layers in line with the MAMS | Installation and Inspection | Each wet area |  | WS (I) |  | PE (W) |  |  |  | Layer 1 time: . . . . . . Layer 2 time: . . . . . .
2.12 | HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation. |  |  | AS3740 Figures, AS3740 cl 4.5.3, 4.6 | AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001 | Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard | Installation and Inspection | Each wet area |  | WS (H) |  | PE (H)
2.13 | Membrane compound setting time - note planned and actual setting time on checklist |  |  | AS3740 cl 4.5.2 | AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001 |  | Installation and Inspection | Each wet area |  | WS (I) |  | PE (S) |  |  |  | Planned setting time: . . . . . .
2.14 | HOLD POINT: Confirm that setting time for membrane has been complied with |  |  | AS3740 cl 4.5.2 | AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001 |  | Installation and Inspection | Each wet area |  | WS (H) |  | PE (H) |  |  |  | Observed setting time: . . . . . .
2.15 | Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction |  |  | AS3740 cl 4.5.4, JHG ETN-00006 3.3 | AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001 | Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported | Test | Each wet area |  | WS (I) |  | PE (W) |  | DC (W)
2.16 | 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure that they do not damage the membrane system. |  |  | JHG ETN-00006 3.5 | GBA-SPE-AR-AS-0001 | Each layer applied in line with MAMS requirements - dressed into puddle flange | Installation and Inspection | Each wet area |  | WS (I) |  | PE (W)
3 | Close-Out
3.1 | ITP close-out. |  |  |  | GBA-SPE-AR-AS-0001 | All prior items of this ITP have been complied with. |  | Each Lot |  |  |  | QR (R) |  |  |  | All records loaded into the Work Lot System and Verified.
Keys: |  |  | Inspection Roles Types:
(S) Surveillance Point |  |  | PE - Project Engineer |  |  |  | SR - Subcontractor Representative | [5 empty] | IR - Independent Reviewer
(I) Inspection of Works |  |  | QR - Quality Representative |  |  |  | SU - Surveyor | [5 empty] | NA - Nominated Authority
(W) Witness Point |  |  | SE - Site Engineer |  |  |  | WS - Waterproofing Subcontractor | [5 empty] | PR - Principal's Representative
(H) Hold Point |  |  | SF - Supervisor / Foreman |  |  |  | SS - Structural Subcontractor | [5 empty] | * Other codes may be added as required
(R) Review | [6 empty] | HS - Hydraulics Subcontractor
DC - Design Consultant

## Sheet1
ITP Action Code | What happens
(H) Hold Point | A Hold Point notice must be issued and released by the nominated independent party
(W) Witness Point | A Witness Point notice must be issued and released by the nominated independent party
(R) Review | The nominated party must review the documented output of this activity
(S) Surveillance Point | The nominated party must keep an eye on this but not do anything specific
(I) Inspection of Works | The nominated party must inspect the works at this stage and sign the checklist to confirm acceptance