## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Standard ITP - Aus Standards - Wet Area Waterproofing |  |  |  |  | Yes | Standard ITP - Aus Standards - Wet Area Waterproofing
section | 1 - Pre-Commencement Activities
checkpoint | Project Self-Assessment Tool- BU Project Audits -
checkpoint | 1.1 - Submission of Waterproofing System products
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Approval of Waterproofing System - confirmation of compatibility with substrate and follow-on trade requirements
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.2 - Submission of Waterproofing System Warranties
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Warranty is for required duration and relevant party
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.3 - Submission of Manufacturer's Application Method Statement (MAMS)
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Approval of MAMS by Waterproofing Consultant
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.4 - Submission of AMS and WRA Content - including Safety Data Sheets for chemicals
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Approval of AMSs and WRAs
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.5 - Waterproofing company to demonstrate Competency of Applicators
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Competency scheme document, register of applicators
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.6 - Detailed design complete - including shop details
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Approval of shop drawings
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.7 - Testing equipment details - and calibration records (if electronic leak detection specified)
label | Specification Reference - AS3740 App C3 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - In calibration
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (R)
label | Inspection: Nominated Authority - WC (R)
checkpoint | 1.8 - First of Type Inspection -joint witness and sign-off on Prototype or First Install with membrane system representative (as below)
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Joint acceptance of the First of Type and close-out of any agreed issues
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - One-off prior to commencement
label | Inspection: Subcontractor - WS (H)
label | Inspection: John Holland - PE (H)
label | Inspection: Nominated Authority - WC (H)
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Inspections
checkpoint | 2.1 - Install Concrete substrate and wall system
label | Specification Reference - AS3600 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Project specification criteria
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - SS (I)
label | Inspection: John Holland - PE (S)
label | Records & Comments - Project Self-Assessment Tool- BU Project Audits
checkpoint | 2.2 - Concrete moisture content check - measure moisture content of concrete substrate - note details on checklist with photo of readout
label | Specification Reference - ASTM F2170, AS3740 cl 4.4.3 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Slabs require a relative humidity of less than 75%
label | Test/ Inspection - Measurement
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.3 - Drainage installation - puddle flange installation
label | Specification Reference - AS3740 fig 4.3.1 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Installed rebated in substrate, undamaged, capped to prevent ingress of debris
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - HS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.4 - Substrate condition Inspection
label | Specification Reference - AS3740 cl 4.4.1, JHG ETN-00006 3.4 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Clean and free of laitence/debris, holes patched
label | Test/ Inspection - Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.5 - Substrate falls - measurement - note actual fall on checklist, take photos
label | Specification Reference - AS3740 cl 2.3.1 / 2.3.2
label | Acceptance Criteria - Falls are to the drain - min 1:80 in shower area, otherwise 1:100
label | Test/ Inspection - Measurement
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.6 - Waterbars installed to edge of shower area and at door openings, waterbars installed to in-wall tap and shower rose surrounds - attach photos of correct installation.
label | Specification Reference - AS3740 4.5.3, 4.8, 4.9, 4.12 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Waterbars in line with approved shop drawings and AS3740 requirements.
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
text | Records & Comments - Measured fall:
checkpoint | 2.7 - Bond breaker/fillets for Class 1/2/3 membrane installed to wall/floor junctions - attach photos of correct size
label | Specification Reference - AS3740 4.5.3, 4.10 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Bond Breaker/fillet to XXXX size based on class of membrane
label | Test/ Inspection - Measurement
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.8 - Subcontractor Pre-placement Check: Confirm equipment, personnel and temperature is acceptable for membrane installation - note equipment ref, name of applicators and temperature on checklist
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Everything ready to install
label | Test/ Inspection - Review & Verify
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
text | Records & Comments - Required size:
text | Measured size:
checkpoint | 2.9 - HOLD POINT: Inspect substrate and confirm that steps above are complete and that membrane may be applied
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Previous steps complete in line with the Australian Standards, specifications and ETN
label | Test/ Inspection - Visual Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (H)
label | Inspection: John Holland - PE (H)
text | Records & Comments - Applicator Names:
text | Temperature at placement:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - 100% Witness Point: Watch the Subcontractor apply primer in line with MAMS - take photograph of primer container with technical details and photo/video of application
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Correct primer applied
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (W)
checkpoint | 2.11 - 100% Witness Point: Watch the Subcontractor apply membrane layers in line with MAMS and the figures in AS3740 - take photograph of membrane container with technical details and photo/video of application - note details of timing on checklist
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Each layer applied in line with MAMS requirements, timing between layers in line with the MAMS
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (W)
checkpoint | 2.12 - HOLD POINT: - Inspection to confirm integrity of the membrane and completion of installation.
label | Specification Reference - AS3740 Figures, AS3740 cl 4.5.3, 4.6 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Continuity of the membrane, no installation defects such as pinholes, measure dry film thickness, confirm vertical termination heights and details in the standard
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (H)
label | Inspection: John Holland - PE (H)
text | Records & Comments - Layer 1 time:
text | Layer 2 time:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.13 - Membrane compound setting time - note planned and actual setting time on checklist
label | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (S)
checkpoint | 2.14 - HOLD POINT: Confirm that setting time for membrane has been complied with
label | Specification Reference - AS3740 cl 4.5.2 / GBA-SPE-AR-AS-0001
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (H)
label | Inspection: John Holland - PE (H)
text | Records & Comments - Planned setting time:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - Membrane test - Flood / Electronic Leak Detection / Seam Probe test the area in line with the AMS instruction
label | Specification Reference - AS3740 cl 4.5.4 / GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Flood test - no leakage observed / measured over 24 hours Electronic Leak Detection Test - no points of electrical conduction identified Seam probe test - no seam failures reported
label | Test/ Inspection - Test
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (W)
label | Inspection: Nominated Authority - DC (W)
text | Records & Comments - Observed setting time:
checkpoint | 2.16 - 100% Witness Point: Supervise the follow-on Subcontractor(s) to ensure that they do not damage the membrane system.
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - Each layer applied in line with MAMS requirements - dressed into puddle flange
label | Test/ Inspection - Installation and Inspection
label | Test/Inspection Frequency - Each wet area
label | Inspection: Subcontractor - WS (I)
label | Inspection: John Holland - PE (W)
section | 3 - Close-Out
checkpoint | 3.1 - ITP close-out.
label | Specification Reference - GBA-SPE-AR-AS-0001
label | Acceptance Criteria - All prior items of this ITP have been complied with.
label | Test/Inspection Frequency - Each Lot
label | Inspection: John Holland - QR (R)
label | Records & Comments - All records loaded into the Work Lot System and Verified.