## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ONSITE - Stiffener Rectification |  |  |  |  | Yes | ONSITE - Stiffener Rectification | 76e23132-48e6-418a-a762-2f83de8fb461
checkpoint-status |  |  | checkpoint | Remove panel from current position and place on adjacent A-Frame, Back of Sheet facing out
label | 0f08c167-2d94-5e3a-8caf-fb9ddc9e7869 |  | note | Insert Photos showing removed panels placed on A-Frame
checkpoint-status |  |  | checkpoint | Record panel number or position, take photo of current condition of the Dowsil adhesion
label | dd77664c-84d2-58d2-9d1b-504f1fd8627a |  | note | Insert Photos showing current condition of the Dowsil stiffener adhesion.
checkpoint-status |  |  | checkpoint | Lightly abrade both sides of the desired stiffeners, spray Isopropyl and wipe off with clean rag. Photos to be taken during process
label | 6ff79b51-13ca-50a8-83e5-7c3e1e4e9f31 |  | note | Insert photos taken during process outlined above.
checkpoint-status |  |  | checkpoint | Record batch number of Dowsil 795 for warranty purposes
label | fa5e94c9-4ec7-571d-95e4-10b0b62469a7 |  | note | Insert photo of batch number of Dowsil 795 located on box / carton of origin (outside of box)
checkpoint-status |  |  | checkpoint | Apply generous amount of Dowsil 795 to both sides of stiffener, ensuring pregnation under the stiffener, apply watered detergent spray and comb off utilising tool. All excess product to be wiped on newspaper and placed in supplied bin. Photos to be taken at completion showing continuous application of Dowsil 795 to both sides of stiffeners
label | fa5e94c9-4ec7-571d-95e4-10b0b62469a7 |  | note | Insert photos taken during process outlined above.
checkpoint-status |  |  | checkpoint | While the DOWSIl 795 is curing and prior to step 7 check the stiffener cutouts at each end of the stiffeners. Take photos using a tape measuring showing the stiffener cutout lengths
label | 3d240ce3-75b8-562a-a144-92ef0fb184af |  | note | Insert photos taken showing length of stiffener cutouts with tape measure
checkpoint-status |  |  | checkpoint | For checkouts with the length of the checkout over 90mm, install supporting brackets (3mm aluminium plate) to each side of the stiffener using x5 12ga Bimeatal Tek Screws to each side
label | 4a415597-d6e5-59ff-a7ad-db552564b319 |  | note | Insert photos showing support brackets have been installed correctly where required (cutout lengths greater than 90mm)
checkpoint-status |  |  | checkpoint | Panel to remain on A frame for 10 minutes to enable to product to skin, then lifted back into its original fixed position.
label | 5b0ac8cc-67cd-5218-979b-3b2758e9db89 |  | note | Insert photo of completed panel prior to re-installment