## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Roof Works | itp |  |  |  |  | ITP Checklist - Roof Works
section | Pressure wash roof
checkpoint | Ensure all dirt, dust, loose material, and contaminants are removed.
checkpoint | Confirm surface is clean and dry prior to next step.
section | Prime with Silcor® BS
checkpoint | Apply primer in accordance with manufacturer’s technical data sheet (TDS).
checkpoint | Check for full, even coverage with no missed areas.
section | Apply Silcor® 575LB
checkpoint | Install in accordance with manufacturer’s specifications.
checkpoint | Ensure correct film thickness and curing times.
section | Apply two (2) top coats of Silcor® Top Coat 75
checkpoint | Apply first coat to required coverage and allow to cure as per TDS.
checkpoint | Apply second coat ensuring consistent finish and full coverage.
section | Conduct ILD Testing (Integrity Leak Detection)
checkpoint | Perform testing in line with project requirements and industry standards.
checkpoint | Record and rectify any defects prior to sign-off.
section | Close out
checkpoint | Final visual inspection to confirm works are complete and compliant.
checkpoint | Submit all test results, inspection records, and warranties for approval.