## Table 1
GRAYSON ENGINEERING (2015) LTD
INSPECTION & TEST PLAN
LEGEND |  | Date : 18/06/2025 | CLIENT: Hawkins Construction Ltd |  |  |  | Job Number : 5600 |  | Construction Category : CC3
W = Witness Point |  | P = Perform H = Hold Point | PROJECT: AIAL Domestic Processor - Pier |  |  |  | Revision : 5, Issued for Construction
M = Monitor A = Approved |  | C = Client GEL = Grayson Eng Ltd | WORK SCOPE: Shop Drawings, Material, Fabrication Paint, Delivery and Installation
RWC = Responsible Welding Coordinator |  | R = Review SGS=Third Party Inspections |  |  |  |  | Approval by : |  | Date:
Revision Records
Revision Number |  | Revision Description |  |  |  |  | Revised by | Date | Comments
B |  | Issued ITP rev B to address client's comments, and implement changes from Rev A. |  |  |  |  | GK | 2024-12-16
C |  | Issued ITP Rev C to address client's comment from Rev B & RFI#GEL-QA-5600-003 |  |  |  |  | GK | 2025-02-28
D |  | Issued ITP Revision D to Incorporate client feedback from Revision C |  |  |  |  | GK | 2025-03-20
1 |  | Added "R" item 4.8 for Client and SGS, and issued for Construction with Revision 1 |  |  |  |  | GK | 2024-03-24
2 |  | Added a note to item 1.8, of use non ACRS Mills, the route of compliance with SCNZ:111 for other accreditations. |  |  |  |  | GK | 2025-05-14
3 |  | Added item 1.8 & 1.9 to cover Third Party Accredited Mills with route of compliance using SCNZ:111 |  |  |  |  | GK | 2025-05-28
4 |  | Clarity provided to item 1.8 to cover Third Party Accredited Mills with route of compliance using SCNZ:111 |  |  |  |  | GK | 2025-06-10
5 |  | Updated as per SGS request: Item 1.6: Removed 'R' for SGS since it is already covered in Items 1.7 to 1.9 (MTC's review).And Items 3.1, 3.2, 3.3, 4.6, 4.7: Changed SGS role from 'R' to 'P'. |  |  |  |  | GK | 2025-06-18
ITEM | Inspection/Activity |  | Acceptance Criteria | Performed | Records | Stage/Frequency | INSPECTION BY |  |  | Comments
[7 empty] | GEL | C | SGS
1 | Pre - Start Fabrication
1.1 | Technical review |  | AS/NZS 5131 : 2016 - Section 4.5.2, ISO 3434.2 & Client Specification | GEL | Technical Review | Post Award | P | R | R | Prior to Construction
1.2 | Shop Drawings |  | AS/NZS 5131 :2016 Section 4.4 & Structural Specification : 6.7 | Cadtec/GEL | Approved Drawings | Prior to Fabrication | H | R | R | Please refer to Section 6.7 of the Structural Spec to ensure that all items are covered.
1.3 | Quality Management System |  | ISO 9001 & AS/NZS 3834 Certification is Current | GEL | QMS Records | Awarded | R | — | — | —
1.4 | SFC Certification to be current and minimum CC3 as per the Construction Category, if any non SFC Certified, Sub-Contractors are Proposed to be used, approval required from the design engineer and principal. |  | AS/NZS 5131 & Structural Specification :6.4.2.3 | GEL | GEL QMS records | SFC Certificates | R | — | — | —
1.5 | Document Approval - Submission of Quality Plan, ITP and Procedures for Client Approval |  | AS/NZS5131:2016, Client Specification | GEL | QP and ITP Transmittal Records | Post Award and Prior to Works Execution | P | R | R | —
1.6 | Material Procurement |  | AS/NZS 5131 : 2016 Section 4.6 & AS/NZS 3404.1:2009 Section 2, Structural Specification:6.8.3 | GEL | Purchase Orders | All Purchase Orders | P | R |  | All the Materials Substitution Shall be Approved Via RFI, 4 Weeks prior to Steel Procurement
1.7 | Steel Supply (Third Party Certified Mill - ACRS ONLY) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 |  | Structural Specification: 6.4.2.6 & 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E | GEL Independent third Party | Steel Mill Certificates | Each Delivery Received Third Party Audits Quarterly | R | R | R | Material Certificates Included in Manufacturer Data Reports
1.8 | Steel Supply (Third Party Certified Mill - Non- ACRS) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 |  | Structural Specification: 6.4.2.6 & 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E ○ Report: SCNZ 111:2018 | GEL Independent third Party | Steel Mill Certificates Third Party Product Certification | Each Delivery Received Third Party Audits Quarterly | R | R | R | Material Certificates Included in Manufacturer Data Reports Where steel is to be procured from a non-ACRS mill, the compliance pathway is to be requested for each Mill using TSUBs referencing the guidance provided in Report SCNZ 111:2018. Ref. Figure 3 for CC3 pathway
1.9 | Steel Supply (Non-Third Party Certified Mill Certs) (Requirements additional to 1.7 above ) 100% Independent Third Party Material Chemical and Mechanical Verification testing undertaken in NZ |  | Third Party Test Reports ○ Chemical, Mechanical and Weldability comparison ○ Testing Accordance with SCNZ 111:2018 Standard Sample & Test Plan | NZ based IANZ Accredited Laboratory Independent third Party | Steel Mill Certificates All third party Test Certificates | Each Delivery Received - 100% of all heat numbers Third Party Audits Quarterly | P/R/A | R | R | Material Certificates & Third Party Test Reports, Included in Manufacturer Data Reports
1.1 | Material Delivery Confirm As per the Purchase order Confirm Heat Numbers as per the delivery docket Confirm all Steel marked with Heat number & PO number prior to Unloading truck |  | AS/NZS5131:2016 ISO 3834.2 GEL Procedures | GEL | Delivery Notes Steel Mill Certificates | Each Delivery Received | H | — | — | —
2 | Start Fabrication & Welding
2.1 | Material Traceability Heat Number of each item is traceable by part Mark on assembly shop drawing reference back to nesting/cutting schedule Confirm Heat Numbers as per the delivery docket confirm all steel marked with Heat Number, and PO number if possible Prior to Unloading Truck. |  | AS/NZS5131:2016 - 4.7 ISO 3834.2 GEL Procedures | GEL | Assembly shop drawings and nesting/cutting schedules | All Parts | P | — | R | —
2.2 | Fabrication - Material Cutting, Shaping, Holing, and Corners, accordance with the Construction Standard, Unless otherwise specified in the drawings/Specification - Supervised by Workshop Supervisors |  | AS/NZS 3404.1:2009 Section 3 ○ AS/NZS 5131:2016 Section 6 ○ Approved Fabrication drawings | GEL | GEL Procedures & Approved Drawings | Every Fabricated Item | P | — | R | —
2.3 | Fabrication Inspection - performed by Workshop Supervisor/RWC |  | AS/NZS 5131:2016 Section 13.5 | GEL | QC Fabrication & Weld Summary Reports | Every Fabricated Item | H | — | R | —
2.4 | Fabrication Tolerances : Shall confirm to the construction standard requirements unless specified in the drawings |  | AS/NZS 5131:2016 Structural Specification : 6.10.2 | GEL | Shop Drawings | Every Fabricated Item | H | — | R | —
2.5 | Weld Access Holes: Weld Access holes shall be accordance with the Construction Standard left open after welding, and the access hole area shall be cleaned to meet Welding Standards, unless otherwise specified on the drawings/specification or confirmed by the design engineer for closure, |  | AS/NZS5131:2016 Section 6.7.7 Structural Specification : 6.12.5.2 RFI # GEL-QA-5600-001 | GEL | Approved drawings / Structural Specification | All the Access hole members | P | R | — | Weld Access Holes to be Closed on Category 1 and 2 members and Remain Open on Category 3 and 4 Members, As Per RFI#189(GEL-QA-RFI-5600-001)
2.6 | Welding Procedures - Approved Prior to Welding |  | AS/NZS 5131:2016 Section 7.4.1 ○ AS/NZS 1554.1:2014 | GEL Welding Supervisor / Inspector | QC Summary - Welding Procedure Register | — | P | A | R | —
2.7 | Welding Plan - Qualified Welding Supervisor/Competent Person |  | AS/NZS 5131:2016 Section 7 ○ AS/NZS 1554.1:2014 ISO 3834.2 ○ Approved Fabrication drawings | GEL Welding Supervisor | QC Fabrication & Weld Summary Reports | Every Welding Item | P | — | R | —
2.8 | Welder Qualifications |  | AS/NZS 5131:2016 Section 7.4.1 ISO9606.1:2017 | GEL Welding Inspector | QC Summary - Welder Qualification Register | All Weld Joints | P | A | R | —
2.9 | Welding Traceability to be provided by welders ID Recorded near to the weld joint and on the workshop drawings, this shall then transferred to the welding Fabrication Welding Summary, for submission in the MDR |  | AS/NZS5131:2016 Section 7.4.2 & Table 7.4 AS/NZS/ISO 3834.2 | GEL Workshop/ Welding Supervisor | Fabrication & Weld Summary Reports | All weld Joints | P | — | R | —
2.1 | Weld Category : All Weld are category SP(Structural Purpose ) Unless Specifically stated on drawings as Category GP |  | AS/NZS 1554.1:2014 &Structural Spec :6.12.1 | GEL Workshop/ Welding Supervisor | Approved Shop Drawings | All | P | — | R | —
2.11 | Welding - Clean all Welded Areas, smooth the edges and remove any spatter, AESS - Architecturally exposed structural steel (AESS) Shall confirm to the requirements Construction Standard/Specification |  | AS/NZS 5131:2016 AESS Structural Specification : 6.15 | GEL | Approved Shop Drawings | As per the specification | P | R/A |  | —
3 | Post weld
3.1 | Visual Scanning : 100% - Category A,B & C, Visual Examination : 100% - Category A, 25% - Category B & C, |  | AS/NZS 5131 Appendix I Structural Specification: 6.12.5 (Table 6.5 and 6.6) ○ AS/NZS 3404.1:2009 Section 8 ○ AS/NZS/ISO 3834.2 | Independent third Party | QC Fabrication & Weld Summary & NDT Reports | All Welds | H | R | P
3.2 | Non Visual Examination NDT Requirements, Non Visual Examination in Accordance with AS/NZs 5131 Table I7 and Table I5 Magnetic Particle Testing (MPI)- AS1171 Ultrasonic test (UT) - AS2207 |  | AS/NZS 5131:2016 Section 13.6 ○ AS/NZS 3404.1:2009 Section 8 ○ AS/NZS/ISO 3834.2 Structural Specification: 6.12.5 (Table 6.5 & 6.6) ○ AS 2207 & AS1171 | Independent third Party | NDT Reports | Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, Category "A" - UT 50% (25%)²of Butt welds including 10 of the first 10 joints ¹ & Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | H | R | P | Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
Notes: 1 - Ultrasonic Testing on buttwelds shall include scanning for lamellar defects on plates in excess of 30mm thick. 2 - Extent of testing may be reduced to the figure in brackets once the welding inspector is satisfied is that the contractor is consistently achieving the weld QA requirements.
3.3 | Weld Defects : All Weld defects revealed by visual or non - visual examination shall be repaired with the requirements of the standard, each weld defect shall be assessed in accordance with the appropriate, clause in the relevant part of the AS/NZS 1554 series, |  | AS/NZS 5131:2016 AS/NZS 1554.1:2014 Section 5.8 Structural Specification : 6.12.6 | GEL | NDE Reports | Any Weld Repair | P/H | R | P | Weld Inspector Report Required
4 | Site Erection
4.1 | Compile Site Delivery Docket/Load List - Load List /delivery Dockets to be maintained, Fabricated components to be delivered to site - Load and Phase wise |  | GEL Procedures | GEL | Delivery Dockets | All Site Delivered Materials | P/M | R | — | —
4.2 | Site Erection - Drawings and Document Revision Review |  | AS/NZS 5131:2016 Section 11,12 & Appendix F&AS/NZS 3404.1:2009 Sec 4 | GEL | IFC Drawings | All Structural Steel | P | R | — | —
4.3 | Erection Tolerances |  | AS/NZS 3404.1:2009 & AS/NZS 5131:2016 Section 12 Structural Specification: 6.13.2 | GEL | Site Sign off Reports | All Structural Steel | P | R/A | — | —
4.4 | Methodology - Installation and Erections tightening of bolts, tensioning of bolts, and all other required methods |  | AS/NZS 5131:2016, & GEL Procedures Structural Specification: 6.13.3 | GEL | Site Sign off Reports | All Structural Steel | P/R/A | R/A | — | —
4.5 | Site Welding - Qualified Welders |  | AS/NZS 5131:2016 Section 7 AS/NZS 1554.1:2014 ISO 3834.2 Approved drawings | GEL | Welder Qualification Register | All site Welding | P | R | R | —
4.6 | Site - Visual Scanning : 100% Category A,B & C Visual Examination : 100% Category A, and 25% Category B & C |  | AS/NZS ISO3834.2 AS/NZS 1554.1:2014 AS/NZS 5131: Section 13.6 | Independent third Party | Inspection Reports | All Welds | P/M/R | R | P | —
4.7 | Site - NDT Testing Non Visual : Magnetic Particle Testing AS1171 Ultrasonic Testing AS2207 |  | AS/NZS 5131:2016 Section 13.6 AS/NZS 3404.1:2009 Section 8 AS/NZS ISO3834.2, AS/NZS 1554.1:2014 AS1171,AS2207 & GEL Procedures Structural Spec:6.12.5 (Table 6.5 & 6.6) | Independent third Party | NDE Reports | Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, & Category "B" MPI to 10% of Fillet Welds Category "A" - UT 100% (50%)²of Butt welds ¹ & Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | P/M/R | R | P | Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
Notes: 1 - Ultrasonic Testing on buttwelds shall include scanning for lamellar defects on plates in excess of 30mm thick. 2 - Extent of testing may be reduced to the figure in brackets once the welding inspector is satisfied is that the contractor is consistently achieving the weld QA requirements.
4.8 | Bolts,Nuts,Fateners and Screws |  | AS/NZS1252.1 & AS/NZS 5131:2016 Section 5.5 & Structural Spec:6.11.4 & 6.11.4.1&2 | GEL | Material Register with Certs &Site Sign off Reports | All the Site connections | P | R | R | for Grade info Please see Structural Spec.
4.9 | Bolting Installation |  | AS/NZS 3404.1:2009 Section 4 & AS/NZS 5131:2016 Section 8 GEL Procedure : OP022 | GEL | Site Sign off Reports | Each Member | P | R | R | —
4.1 | Site Final Inspection |  | AS/NZS 5131 :2016 & AS/NZS 2312 | GEL | QC Site Sign off Reports/Summary | Completion of Each Phase / or As agreed | H | H | — | —
5 | Documentation
5.1 | Manufacturer Data Records(MDR) - Compile all the quality documentation as required by the specification and submit to the client |  | AS/NZS5131:2016 Appendix E Structural Specification: 6.4.2.5 & 6.5(PS) ○ AS/NZS ISO3834.2 | GEL | Manufacturer Dat Reports (MDR) | Completion of Work | P | R | — | Including PS3 and EPD Information
Venugopal Komire - 18/06/2025
| Name, Signature & date |  | Name, Signature & date |  |  |  | Name, Signature & date
| GEL |  |  | CLIENT |  |  |  | TPI