## Sheet1
1.1 | Technical review | AS/NZS 5131 : 2016 - Section 4.5.2, ISO 3434.2 CHAR(AMP) Client Specification | GEL | Technical Review | Post Award | P | R | R | Prior to Construction | 1.1 - Technical review | Acceptance Criteria - AS/NZS 5131 : 2016 - Section 4.5.2, ISO 3434.2 CHAR(AMP) Client Specification | Performed - GEL | Records - Technical Review | Stage/Frequency - Post Award | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - Prior to Construction | 1.1 - Technical review
1.2 | Shop Drawings | AS/NZS 5131 :2016 Section 4.4 CHAR(AMP) Structural Specification : 6.7 | Cadtec/GEL | Approved Drawings | Prior to Fabrication | H | R | R | Please refer to Section 6.7 of the Structural Spec to ensure that all items are covered. | 1.2 - Shop Drawings | Acceptance Criteria - AS/NZS 5131 :2016 Section 4.4 CHAR(AMP) Structural Specification : 6.7 | Performed - Cadtec/GEL | Records - Approved Drawings | Stage/Frequency - Prior to Fabrication | INSPECTION BY: GEL - H | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - Please refer to Section 6.7 of the Structural Spec to ensure that all items are covered. | Acceptance Criteria - AS/NZS 5131 : 2016 - Section 4.5.2, ISO 3434.2 CHAR(AMP) Client Specification
1.3 | Quality Management System | ISO 9001 CHAR(AMP) AS/NZS 3834 Certification is Current | GEL | QMS Records | Awarded | R | — | — | — | 1.3 - Quality Management System | Acceptance Criteria - ISO 9001 CHAR(AMP) AS/NZS 3834 Certification is Current | Performed - GEL | Records - QMS Records | Stage/Frequency - Awarded | INSPECTION BY: GEL - R | INSPECTION BY: C - — | INSPECTION BY: SGS - — | Comments - — | Performed - GEL
1.4 | SFC Certification to be current and minimum CC3 as per the Construction Category, if any non SFC Certified, Sub-Contractors are Proposed to be used, approval required from the design engineer and principal. | AS/NZS 5131 CHAR(AMP) Structural Specification :6.4.2.3 | GEL | GEL QMS records | SFC Certificates | R | — | — | — | 1.4 - SFC Certification to be current and minimum CC3 as per the Construction Category, if any non SFC Certified, Sub-Contractors are Proposed to be used, approval required from the design engineer and principal. | Acceptance Criteria - AS/NZS 5131 CHAR(AMP) Structural Specification :6.4.2.3 | Performed - GEL | Records - GEL QMS records | Stage/Frequency - SFC Certificates | INSPECTION BY: GEL - R | INSPECTION BY: C - — | INSPECTION BY: SGS - — | Comments - — | Records - Technical Review
1.5 | Document Approval - Submission of Quality Plan, ITP and Procedures for Client Approval | AS/NZS5131:2016, Client Specification | GEL | QP and ITP Transmittal Records | Post Award and Prior to Works Execution | P | R | R | — | 1.5 - Document Approval - Submission of Quality Plan, ITP and Procedures for Client Approval | Acceptance Criteria - AS/NZS5131:2016, Client Specification | Performed - GEL | Records - QP and ITP Transmittal Records | Stage/Frequency - Post Award and Prior to Works Execution | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - — | Stage/Frequency - Post Award
1.7 | Steel Supply (Third Party Certified Mill - ACRS ONLY) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 | Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E | GEL Independent third Party | Steel Mill Certificates | Each Delivery Received Third Party Audits Quarterly | R | R | R | Material Certificates Included in Manufacturer Data Reports | 1.7 - Steel Supply (Third Party Certified Mill - ACRS ONLY) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 | Acceptance Criteria - Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E | Performed - GEL Independent third Party | Records - Steel Mill Certificates | Stage/Frequency - Each Delivery Received Third Party Audits Quarterly | INSPECTION BY: GEL - R | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - Material Certificates Included in Manufacturer Data Reports | INSPECTION BY: GEL - P
1.8 | Steel Supply (Third Party Certified Mill - Non- ACRS) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 | Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E ○ Report: SCNZ 111:2018 | GEL Independent third Party | Steel Mill Certificates Third Party Product Certification | Each Delivery Received Third Party Audits Quarterly | R | R | R | Material Certificates Included in Manufacturer Data Reports Where steel is to be procured from a non-ACRS mill, the compliance pathway is to be requested for each Mill using TSUBs referencing the guidance provided in Report SCNZ 111:2018. Ref. Figure 3 for CC3 pathway | 1.8 - Steel Supply (Third Party Certified Mill - Non- ACRS) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1 | Acceptance Criteria - Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E ○ Report: SCNZ 111:2018 | Performed - GEL Independent third Party | Records - Steel Mill Certificates Third Party Product Certification | Stage/Frequency - Each Delivery Received Third Party Audits Quarterly | INSPECTION BY: GEL - R | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - Material Certificates Included in Manufacturer Data Reports Where steel is to be procured from a non-ACRS mill, the compliance pathway is to be requested for each Mill using TSUBs referencing the guidance provided in Report SCNZ 111:2018. Ref. Figure 3 for CC3 pathway | INSPECTION BY: C - R
1.9 | Steel Supply (Non-Third Party Certified Mill Certs) (Requirements additional to 1.7 above ) 100% Independent Third Party Material Chemical and Mechanical Verification testing undertaken in NZ | Third Party Test Reports ○ Chemical, Mechanical and Weldability comparison ○ Testing Accordance with SCNZ 111:2018 Standard Sample CHAR(AMP) Test Plan | NZ based IANZ Accredited Laboratory Independent third Party | Steel Mill Certificates All third party Test Certificates | Each Delivery Received - 100% of all heat numbers Third Party Audits Quarterly | P/R/A | R | R | Material Certificates CHAR(AMP) Third Party Test Reports, Included in Manufacturer Data Reports | 1.9 - Steel Supply (Non-Third Party Certified Mill Certs) (Requirements additional to 1.7 above ) 100% Independent Third Party Material Chemical and Mechanical Verification testing undertaken in NZ | Acceptance Criteria - Third Party Test Reports ○ Chemical, Mechanical and Weldability comparison ○ Testing Accordance with SCNZ 111:2018 Standard Sample CHAR(AMP) Test Plan | Performed - NZ based IANZ Accredited Laboratory Independent third Party | Records - Steel Mill Certificates All third party Test Certificates | Stage/Frequency - Each Delivery Received - 100% of all heat numbers Third Party Audits Quarterly | INSPECTION BY: GEL - P/R/A | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - Material Certificates CHAR(AMP) Third Party Test Reports, Included in Manufacturer Data Reports | INSPECTION BY: SGS - R
1.1 | Material Delivery Confirm As per the Purchase order Confirm Heat Numbers as per the delivery docket Confirm all Steel marked with Heat number CHAR(AMP) PO number prior to Unloading truck | AS/NZS5131:2016 ISO 3834.2 GEL Procedures | GEL | Delivery Notes Steel Mill Certificates | Each Delivery Received | H | — | — | — | 1.1 - Material Delivery Confirm As per the Purchase order Confirm Heat Numbers as per the delivery docket Confirm all Steel marked with Heat number CHAR(AMP) PO number prior to Unloading truck | Acceptance Criteria - AS/NZS5131:2016 ISO 3834.2 GEL Procedures | Performed - GEL | Records - Delivery Notes Steel Mill Certificates | Stage/Frequency - Each Delivery Received | INSPECTION BY: GEL - H | INSPECTION BY: C - — | INSPECTION BY: SGS - — | Comments - — | Comments - Prior to Construction
2.1 | Material Traceability Heat Number of each item is traceable by part Mark on assembly shop drawing reference back to nesting/cutting schedule Confirm Heat Numbers as per the delivery docket confirm all steel marked with Heat Number, and PO number if possible Prior to Unloading Truck. | AS/NZS5131:2016 - 4.7 ISO 3834.2 GEL Procedures | GEL | Assembly shop drawings and nesting/cutting schedules | All Parts | P | — | R | — | 2.1 - Material Traceability Heat Number of each item is traceable by part Mark on assembly shop drawing reference back to nesting/cutting schedule Confirm Heat Numbers as per the delivery docket confirm all steel marked with Heat Number, and PO number if possible Prior to Unloading Truck. | Acceptance Criteria - AS/NZS5131:2016 - 4.7 ISO 3834.2 GEL Procedures | Performed - GEL | Records - Assembly shop drawings and nesting/cutting schedules | Stage/Frequency - All Parts | INSPECTION BY: GEL - P | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | 1.2 - Shop Drawings
2.2 | Fabrication - Material Cutting, Shaping, Holing, and Corners, accordance with the Construction Standard, Unless otherwise specified in the drawings/Specification - Supervised by Workshop Supervisors | AS/NZS 3404.1:2009 Section 3 ○ AS/NZS 5131:2016 Section 6 ○ Approved Fabrication drawings | GEL | GEL Procedures CHAR(AMP) Approved Drawings | Every Fabricated Item | P | — | R | — | 2.2 - Fabrication - Material Cutting, Shaping, Holing, and Corners, accordance with the Construction Standard, Unless otherwise specified in the drawings/Specification - Supervised by Workshop Supervisors | Acceptance Criteria - AS/NZS 3404.1:2009 Section 3 ○ AS/NZS 5131:2016 Section 6 ○ Approved Fabrication drawings | Performed - GEL | Records - GEL Procedures CHAR(AMP) Approved Drawings | Stage/Frequency - Every Fabricated Item | INSPECTION BY: GEL - P | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | Acceptance Criteria - AS/NZS 5131 :2016 Section 4.4 CHAR(AMP) Structural Specification : 6.7
2.3 | Fabrication Inspection - performed by Workshop Supervisor/RWC | AS/NZS 5131:2016 Section 13.5 | GEL | QC Fabrication CHAR(AMP) Weld Summary Reports | Every Fabricated Item | H | — | R | — | 2.3 - Fabrication Inspection - performed by Workshop Supervisor/RWC | Acceptance Criteria - AS/NZS 5131:2016 Section 13.5 | Performed - GEL | Records - QC Fabrication CHAR(AMP) Weld Summary Reports | Stage/Frequency - Every Fabricated Item | INSPECTION BY: GEL - H | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | Performed - Cadtec/GEL
2.4 | Fabrication Tolerances : Shall confirm to the construction standard requirements unless specified in the drawings | AS/NZS 5131:2016 Structural Specification : 6.10.2 | GEL | Shop Drawings | Every Fabricated Item | H | — | R | — | 2.4 - Fabrication Tolerances : Shall confirm to the construction standard requirements unless specified in the drawings | Acceptance Criteria - AS/NZS 5131:2016 Structural Specification : 6.10.2 | Performed - GEL | Records - Shop Drawings | Stage/Frequency - Every Fabricated Item | INSPECTION BY: GEL - H | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | Records - Approved Drawings
2.5 | Weld Access Holes: Weld Access holes shall be accordance with the Construction Standard left open after welding, and the access hole area shall be cleaned to meet Welding Standards, unless otherwise specified on the drawings/specification or confirmed by the design engineer for closure, | AS/NZS5131:2016 Section 6.7.7 Structural Specification : 6.12.5.2 RFI # GEL-QA-5600-001 | GEL | Approved drawings / Structural Specification | All the Access hole members | P | R | — | Weld Access Holes to be Closed on Category 1 and 2 members and Remain Open on Category 3 and 4 Members, As Per RFI#189(GEL-QA-RFI-5600-001) | 2.5 - Weld Access Holes: Weld Access holes shall be accordance with the Construction Standard left open after welding, and the access hole area shall be cleaned to meet Welding Standards, unless otherwise specified on the drawings/specification or confirmed by the design engineer for closure, | Acceptance Criteria - AS/NZS5131:2016 Section 6.7.7 Structural Specification : 6.12.5.2 RFI # GEL-QA-5600-001 | Performed - GEL | Records - Approved drawings / Structural Specification | Stage/Frequency - All the Access hole members | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - — | Comments - Weld Access Holes to be Closed on Category 1 and 2 members and Remain Open on Category 3 and 4 Members, As Per RFI#189(GEL-QA-RFI-5600-001) | Stage/Frequency - Prior to Fabrication
2.6 | Welding Procedures - Approved Prior to Welding | AS/NZS 5131:2016 Section 7.4.1 ○ AS/NZS 1554.1:2014 | GEL Welding Supervisor / Inspector | QC Summary - Welding Procedure Register | — | P | A | R | — | 2.6 - Welding Procedures - Approved Prior to Welding | Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1 ○ AS/NZS 1554.1:2014 | Performed - GEL Welding Supervisor / Inspector | Records - QC Summary - Welding Procedure Register | Stage/Frequency - — | INSPECTION BY: GEL - P | INSPECTION BY: C - A | INSPECTION BY: SGS - R | Comments - — | INSPECTION BY: GEL - H
2.7 | Welding Plan - Qualified Welding Supervisor/Competent Person | AS/NZS 5131:2016 Section 7 ○ AS/NZS 1554.1:2014 ISO 3834.2 ○ Approved Fabrication drawings | GEL Welding Supervisor | QC Fabrication CHAR(AMP) Weld Summary Reports | Every Welding Item | P | — | R | — | 2.7 - Welding Plan - Qualified Welding Supervisor/Competent Person | Acceptance Criteria - AS/NZS 5131:2016 Section 7 ○ AS/NZS 1554.1:2014 ISO 3834.2 ○ Approved Fabrication drawings | Performed - GEL Welding Supervisor | Records - QC Fabrication CHAR(AMP) Weld Summary Reports | Stage/Frequency - Every Welding Item | INSPECTION BY: GEL - P | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | INSPECTION BY: C - R
2.8 | Welder Qualifications | AS/NZS 5131:2016 Section 7.4.1 ISO9606.1:2017 | GEL Welding Inspector | QC Summary - Welder Qualification Register | All Weld Joints | P | A | R | — | 2.8 - Welder Qualifications | Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1 ISO9606.1:2017 | Performed - GEL Welding Inspector | Records - QC Summary - Welder Qualification Register | Stage/Frequency - All Weld Joints | INSPECTION BY: GEL - P | INSPECTION BY: C - A | INSPECTION BY: SGS - R | Comments - — | INSPECTION BY: SGS - R
2.9 | Welding Traceability to be provided by welders ID Recorded near to the weld joint and on the workshop drawings, this shall then transferred to the welding Fabrication Welding Summary, for submission in the MDR | AS/NZS5131:2016 Section 7.4.2 CHAR(AMP) Table 7.4 AS/NZS/ISO 3834.2 | GEL Workshop/ Welding Supervisor | Fabrication CHAR(AMP) Weld Summary Reports | All weld Joints | P | — | R | — | 2.9 - Welding Traceability to be provided by welders ID Recorded near to the weld joint and on the workshop drawings, this shall then transferred to the welding Fabrication Welding Summary, for submission in the MDR | Acceptance Criteria - AS/NZS5131:2016 Section 7.4.2 CHAR(AMP) Table 7.4 AS/NZS/ISO 3834.2 | Performed - GEL Workshop/ Welding Supervisor | Records - Fabrication CHAR(AMP) Weld Summary Reports | Stage/Frequency - All weld Joints | INSPECTION BY: GEL - P | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | Comments - Please refer to Section 6.7 of the Structural Spec to ensure that all items are covered.
2.1 | Weld Category : All Weld are category SP(Structural Purpose ) Unless Specifically stated on drawings as Category GP | AS/NZS 1554.1:2014 CHAR(AMP)Structural Spec :6.12.1 | GEL Workshop/ Welding Supervisor | Approved Shop Drawings | All | P | — | R | — | 2.1 - Weld Category : All Weld are category SP(Structural Purpose ) Unless Specifically stated on drawings as Category GP | Acceptance Criteria - AS/NZS 1554.1:2014 CHAR(AMP)Structural Spec :6.12.1 | Performed - GEL Workshop/ Welding Supervisor | Records - Approved Shop Drawings | Stage/Frequency - All | INSPECTION BY: GEL - P | INSPECTION BY: C - — | INSPECTION BY: SGS - R | Comments - — | 1.3 - Quality Management System
3.2 | Non Visual Examination NDT Requirements, Non Visual Examination in Accordance with AS/NZs 5131 Table I7 and Table I5 Magnetic Particle Testing (MPI)- AS1171 Ultrasonic test (UT) - AS2207 | AS/NZS 5131:2016 Section 13.6 ○ AS/NZS 3404.1:2009 Section 8 ○ AS/NZS/ISO 3834.2 Structural Specification: 6.12.5 (Table 6.5 CHAR(AMP) 6.6) ○ AS 2207 CHAR(AMP) AS1171 | Independent third Party | NDT Reports | Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, Category "A" - UT 50% (25%)²of Butt welds including 10 of the first 10 joints ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | H | R | P | Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14 | 3.2 - Non Visual Examination NDT Requirements, Non Visual Examination in Accordance with AS/NZs 5131 Table I7 and Table I5 Magnetic Particle Testing (MPI)- AS1171 Ultrasonic test (UT) - AS2207 | Acceptance Criteria - AS/NZS 5131:2016 Section 13.6 ○ AS/NZS 3404.1:2009 Section 8 ○ AS/NZS/ISO 3834.2 Structural Specification: 6.12.5 (Table 6.5 CHAR(AMP) 6.6) ○ AS 2207 CHAR(AMP) AS1171 | Performed - Independent third Party | Records - NDT Reports | Stage/Frequency - Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, Category "A" - UT 50% (25%)²of Butt welds including 10 of the first 10 joints ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | INSPECTION BY: GEL - H | INSPECTION BY: C - R | INSPECTION BY: SGS - P | Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14 | Acceptance Criteria - ISO 9001 CHAR(AMP) AS/NZS 3834 Certification is Current
3.3 | Weld Defects : All Weld defects revealed by visual or non - visual examination shall be repaired with the requirements of the standard, each weld defect shall be assessed in accordance with the appropriate, clause in the relevant part of the AS/NZS 1554 series, | AS/NZS 5131:2016 AS/NZS 1554.1:2014 Section 5.8 Structural Specification : 6.12.6 | GEL | NDE Reports | Any Weld Repair | P/H | R | P | Weld Inspector Report Required | 3.3 - Weld Defects : All Weld defects revealed by visual or non - visual examination shall be repaired with the requirements of the standard, each weld defect shall be assessed in accordance with the appropriate, clause in the relevant part of the AS/NZS 1554 series, | Acceptance Criteria - AS/NZS 5131:2016 AS/NZS 1554.1:2014 Section 5.8 Structural Specification : 6.12.6 | Performed - GEL | Records - NDE Reports | Stage/Frequency - Any Weld Repair | INSPECTION BY: GEL - P/H | INSPECTION BY: C - R | INSPECTION BY: SGS - P | Comments - Weld Inspector Report Required | Performed - GEL
4.1 | Compile Site Delivery Docket/Load List - Load List /delivery Dockets to be maintained, Fabricated components to be delivered to site - Load and Phase wise | GEL Procedures | GEL | Delivery Dockets | All Site Delivered Materials | P/M | R | — | — | 4.1 - Compile Site Delivery Docket/Load List - Load List /delivery Dockets to be maintained, Fabricated components to be delivered to site - Load and Phase wise | Acceptance Criteria - GEL Procedures | Performed - GEL | Records - Delivery Dockets | Stage/Frequency - All Site Delivered Materials | INSPECTION BY: GEL - P/M | INSPECTION BY: C - R | INSPECTION BY: SGS - — | Comments - — | Records - QMS Records
4.2 | Site Erection - Drawings and Document Revision Review | AS/NZS 5131:2016 Section 11,12 CHAR(AMP) Appendix FCHAR(AMP)AS/NZS 3404.1:2009 Sec 4 | GEL | IFC Drawings | All Structural Steel | P | R | — | — | 4.2 - Site Erection - Drawings and Document Revision Review | Acceptance Criteria - AS/NZS 5131:2016 Section 11,12 CHAR(AMP) Appendix FCHAR(AMP)AS/NZS 3404.1:2009 Sec 4 | Performed - GEL | Records - IFC Drawings | Stage/Frequency - All Structural Steel | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - — | Comments - — | Stage/Frequency - Awarded
4.3 | Erection Tolerances | AS/NZS 3404.1:2009 CHAR(AMP) AS/NZS 5131:2016 Section 12 Structural Specification: 6.13.2 | GEL | Site Sign off Reports | All Structural Steel | P | R/A | — | — | 4.3 - Erection Tolerances | Acceptance Criteria - AS/NZS 3404.1:2009 CHAR(AMP) AS/NZS 5131:2016 Section 12 Structural Specification: 6.13.2 | Performed - GEL | Records - Site Sign off Reports | Stage/Frequency - All Structural Steel | INSPECTION BY: GEL - P | INSPECTION BY: C - R/A | INSPECTION BY: SGS - — | Comments - — | INSPECTION BY: GEL - R
4.4 | Methodology - Installation and Erections tightening of bolts, tensioning of bolts, and all other required methods | AS/NZS 5131:2016, CHAR(AMP) GEL Procedures Structural Specification: 6.13.3 | GEL | Site Sign off Reports | All Structural Steel | P/R/A | R/A | — | — | 4.4 - Methodology - Installation and Erections tightening of bolts, tensioning of bolts, and all other required methods | Acceptance Criteria - AS/NZS 5131:2016, CHAR(AMP) GEL Procedures Structural Specification: 6.13.3 | Performed - GEL | Records - Site Sign off Reports | Stage/Frequency - All Structural Steel | INSPECTION BY: GEL - P/R/A | INSPECTION BY: C - R/A | INSPECTION BY: SGS - — | Comments - — | INSPECTION BY: C - —
4.5 | Site Welding - Qualified Welders | AS/NZS 5131:2016 Section 7 AS/NZS 1554.1:2014 ISO 3834.2 Approved drawings | GEL | Welder Qualification Register | All site Welding | P | R | R | — | 4.5 - Site Welding - Qualified Welders | Acceptance Criteria - AS/NZS 5131:2016 Section 7 AS/NZS 1554.1:2014 ISO 3834.2 Approved drawings | Performed - GEL | Records - Welder Qualification Register | Stage/Frequency - All site Welding | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - — | INSPECTION BY: SGS - —
4.6 | Site - Visual Scanning : 100% Category A,B CHAR(AMP) C Visual Examination : 100% Category A, and 25% Category B CHAR(AMP) C | AS/NZS ISO3834.2 AS/NZS 1554.1:2014 AS/NZS 5131: Section 13.6 | Independent third Party | Inspection Reports | All Welds | P/M/R | R | P | — | 4.6 - Site - Visual Scanning : 100% Category A,B CHAR(AMP) C Visual Examination : 100% Category A, and 25% Category B CHAR(AMP) C | Acceptance Criteria - AS/NZS ISO3834.2 AS/NZS 1554.1:2014 AS/NZS 5131: Section 13.6 | Performed - Independent third Party | Records - Inspection Reports | Stage/Frequency - All Welds | INSPECTION BY: GEL - P/M/R | INSPECTION BY: C - R | INSPECTION BY: SGS - P | Comments - — | Comments - —
4.7 | Site - NDT Testing Non Visual : Magnetic Particle Testing AS1171 Ultrasonic Testing AS2207 | AS/NZS 5131:2016 Section 13.6 AS/NZS 3404.1:2009 Section 8 AS/NZS ISO3834.2, AS/NZS 1554.1:2014 AS1171,AS2207 CHAR(AMP) GEL Procedures Structural Spec:6.12.5 (Table 6.5 CHAR(AMP) 6.6) | Independent third Party | NDE Reports | Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, CHAR(AMP) Category "B" MPI to 10% of Fillet Welds Category "A" - UT 100% (50%)²of Butt welds ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | P/M/R | R | P | Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14 | 4.7 - Site - NDT Testing Non Visual : Magnetic Particle Testing AS1171 Ultrasonic Testing AS2207 | Acceptance Criteria - AS/NZS 5131:2016 Section 13.6 AS/NZS 3404.1:2009 Section 8 AS/NZS ISO3834.2, AS/NZS 1554.1:2014 AS1171,AS2207 CHAR(AMP) GEL Procedures Structural Spec:6.12.5 (Table 6.5 CHAR(AMP) 6.6) | Performed - Independent third Party | Records - NDE Reports | Stage/Frequency - Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, CHAR(AMP) Category "B" MPI to 10% of Fillet Welds Category "A" - UT 100% (50%)²of Butt welds ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints. | INSPECTION BY: GEL - P/M/R | INSPECTION BY: C - R | INSPECTION BY: SGS - P | Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14 | 1.4 - SFC Certification to be current and minimum CC3 as per the Construction Category, if any non SFC Certified, Sub-Contractors are Proposed to be used, approval required from the design engineer and principal.
4.8 | Bolts,Nuts,Fateners and Screws | AS/NZS1252.1 CHAR(AMP) AS/NZS 5131:2016 Section 5.5 CHAR(AMP) Structural Spec:6.11.4 CHAR(AMP) 6.11.4.1CHAR(AMP)2 | GEL | Material Register with Certs CHAR(AMP)Site Sign off Reports | All the Site connections | P | R | R | for Grade info Please see Structural Spec. | 4.8 - Bolts,Nuts,Fateners and Screws | Acceptance Criteria - AS/NZS1252.1 CHAR(AMP) AS/NZS 5131:2016 Section 5.5 CHAR(AMP) Structural Spec:6.11.4 CHAR(AMP) 6.11.4.1CHAR(AMP)2 | Performed - GEL | Records - Material Register with Certs CHAR(AMP)Site Sign off Reports | Stage/Frequency - All the Site connections | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - for Grade info Please see Structural Spec. | Acceptance Criteria - AS/NZS 5131 CHAR(AMP) Structural Specification :6.4.2.3
4.9 | Bolting Installation | AS/NZS 3404.1:2009 Section 4 CHAR(AMP) AS/NZS 5131:2016 Section 8 GEL Procedure : OP022 | GEL | Site Sign off Reports | Each Member | P | R | R | — | 4.9 - Bolting Installation | Acceptance Criteria - AS/NZS 3404.1:2009 Section 4 CHAR(AMP) AS/NZS 5131:2016 Section 8 GEL Procedure : OP022 | Performed - GEL | Records - Site Sign off Reports | Stage/Frequency - Each Member | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - R | Comments - — | Performed - GEL
4.1 | Site Final Inspection | AS/NZS 5131 :2016 CHAR(AMP) AS/NZS 2312 | GEL | QC Site Sign off Reports/Summary | Completion of Each Phase / or As agreed | H | H | — | — | 4.1 - Site Final Inspection | Acceptance Criteria - AS/NZS 5131 :2016 CHAR(AMP) AS/NZS 2312 | Performed - GEL | Records - QC Site Sign off Reports/Summary | Stage/Frequency - Completion of Each Phase / or As agreed | INSPECTION BY: GEL - H | INSPECTION BY: C - H | INSPECTION BY: SGS - — | Comments - — | Records - GEL QMS records
5.1 | Manufacturer Data Records(MDR) - Compile all the quality documentation as required by the specification and submit to the client | AS/NZS5131:2016 Appendix E Structural Specification: 6.4.2.5 CHAR(AMP) 6.5(PS) ○ AS/NZS ISO3834.2 | GEL | Manufacturer Dat Reports (MDR) | Completion of Work | P | R | — | Including PS3 and EPD Information | 5.1 - Manufacturer Data Records(MDR) - Compile all the quality documentation as required by the specification and submit to the client | Acceptance Criteria - AS/NZS5131:2016 Appendix E Structural Specification: 6.4.2.5 CHAR(AMP) 6.5(PS) ○ AS/NZS ISO3834.2 | Performed - GEL | Records - Manufacturer Dat Reports (MDR) | Stage/Frequency - Completion of Work | INSPECTION BY: GEL - P | INSPECTION BY: C - R | INSPECTION BY: SGS - — | Comments - Including PS3 and EPD Information | Stage/Frequency - SFC Certificates
INSPECTION BY: GEL - R
INSPECTION BY: C - —
INSPECTION BY: SGS - —
Comments - —
1.5 - Document Approval - Submission of Quality Plan, ITP and Procedures for Client Approval
Acceptance Criteria - AS/NZS5131:2016, Client Specification
Performed - GEL
Records - QP and ITP Transmittal Records
Stage/Frequency - Post Award and Prior to Works Execution
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - —
1.7 - Steel Supply (Third Party Certified Mill - ACRS ONLY) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1
Acceptance Criteria - Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E
Performed - GEL Independent third Party
Records - Steel Mill Certificates
Stage/Frequency - Each Delivery Received Third Party Audits Quarterly
INSPECTION BY: GEL - R
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - Material Certificates Included in Manufacturer Data Reports
1.8 - Steel Supply (Third Party Certified Mill - Non- ACRS) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1
Acceptance Criteria - Structural Specification: 6.4.2.6 CHAR(AMP) 6.8 ○ NZS1163 Grade 350/400 ○ NZS1594 Grade 300 ○ NZS3678 Grade 350 L15 ○ NZS 3679.1 Grade 300/300 SO ○ NZS 3679.2 Grade 350 L15 / SO ○ NZS4600 G450 Z275 ○ NZS 4671 Grade 300E ○ Report: SCNZ 111:2018
Performed - GEL Independent third Party
Records - Steel Mill Certificates Third Party Product Certification
Stage/Frequency - Each Delivery Received Third Party Audits Quarterly
INSPECTION BY: GEL - R
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - Material Certificates Included in Manufacturer Data Reports Where steel is to be procured from a non-ACRS mill, the compliance pathway is to be requested for each Mill using TSUBs referencing the guidance provided in Report SCNZ 111:2018. Ref. Figure 3 for CC3 pathway
1.9 - Steel Supply (Non-Third Party Certified Mill Certs) (Requirements additional to 1.7 above ) 100% Independent Third Party Material Chemical and Mechanical Verification testing undertaken in NZ
Acceptance Criteria - Third Party Test Reports ○ Chemical, Mechanical and Weldability comparison ○ Testing Accordance with SCNZ 111:2018 Standard Sample CHAR(AMP) Test Plan
Performed - NZ based IANZ Accredited Laboratory Independent third Party
Records - Steel Mill Certificates All third party Test Certificates
Stage/Frequency - Each Delivery Received - 100% of all heat numbers Third Party Audits Quarterly
INSPECTION BY: GEL - P/R/A
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - Material Certificates CHAR(AMP) Third Party Test Reports, Included in Manufacturer Data Reports
1.1 - Material Delivery Confirm As per the Purchase order Confirm Heat Numbers as per the delivery docket Confirm all Steel marked with Heat number CHAR(AMP) PO number prior to Unloading truck
Acceptance Criteria - AS/NZS5131:2016 ISO 3834.2 GEL Procedures
Performed - GEL
Records - Delivery Notes Steel Mill Certificates
Stage/Frequency - Each Delivery Received
INSPECTION BY: GEL - H
INSPECTION BY: C - —
INSPECTION BY: SGS - —
Comments - —
2.1 - Material Traceability Heat Number of each item is traceable by part Mark on assembly shop drawing reference back to nesting/cutting schedule Confirm Heat Numbers as per the delivery docket confirm all steel marked with Heat Number, and PO number if possible Prior to Unloading Truck.
Acceptance Criteria - AS/NZS5131:2016 - 4.7 ISO 3834.2 GEL Procedures
Performed - GEL
Records - Assembly shop drawings and nesting/cutting schedules
Stage/Frequency - All Parts
INSPECTION BY: GEL - P
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.2 - Fabrication - Material Cutting, Shaping, Holing, and Corners, accordance with the Construction Standard, Unless otherwise specified in the drawings/Specification - Supervised by Workshop Supervisors
Acceptance Criteria - AS/NZS 3404.1:2009 Section 3 ○ AS/NZS 5131:2016 Section 6 ○ Approved Fabrication drawings
Performed - GEL
Records - GEL Procedures CHAR(AMP) Approved Drawings
Stage/Frequency - Every Fabricated Item
INSPECTION BY: GEL - P
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.3 - Fabrication Inspection - performed by Workshop Supervisor/RWC
Acceptance Criteria - AS/NZS 5131:2016 Section 13.5
Performed - GEL
Records - QC Fabrication CHAR(AMP) Weld Summary Reports
Stage/Frequency - Every Fabricated Item
INSPECTION BY: GEL - H
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.4 - Fabrication Tolerances : Shall confirm to the construction standard requirements unless specified in the drawings
Acceptance Criteria - AS/NZS 5131:2016 Structural Specification : 6.10.2
Performed - GEL
Records - Shop Drawings
Stage/Frequency - Every Fabricated Item
INSPECTION BY: GEL - H
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.5 - Weld Access Holes: Weld Access holes shall be accordance with the Construction Standard left open after welding, and the access hole area shall be cleaned to meet Welding Standards, unless otherwise specified on the drawings/specification or confirmed by the design engineer for closure,
Acceptance Criteria - AS/NZS5131:2016 Section 6.7.7 Structural Specification : 6.12.5.2 RFI # GEL-QA-5600-001
Performed - GEL
Records - Approved drawings / Structural Specification
Stage/Frequency - All the Access hole members
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - —
Comments - Weld Access Holes to be Closed on Category 1 and 2 members and Remain Open on Category 3 and 4 Members, As Per RFI#189(GEL-QA-RFI-5600-001)
2.6 - Welding Procedures - Approved Prior to Welding
Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1 ○ AS/NZS 1554.1:2014
Performed - GEL Welding Supervisor / Inspector
Records - QC Summary - Welding Procedure Register
Stage/Frequency - —
INSPECTION BY: GEL - P
INSPECTION BY: C - A
INSPECTION BY: SGS - R
Comments - —
2.7 - Welding Plan - Qualified Welding Supervisor/Competent Person
Acceptance Criteria - AS/NZS 5131:2016 Section 7 ○ AS/NZS 1554.1:2014 ISO 3834.2 ○ Approved Fabrication drawings
Performed - GEL Welding Supervisor
Records - QC Fabrication CHAR(AMP) Weld Summary Reports
Stage/Frequency - Every Welding Item
INSPECTION BY: GEL - P
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.8 - Welder Qualifications
Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1 ISO9606.1:2017
Performed - GEL Welding Inspector
Records - QC Summary - Welder Qualification Register
Stage/Frequency - All Weld Joints
INSPECTION BY: GEL - P
INSPECTION BY: C - A
INSPECTION BY: SGS - R
Comments - —
2.9 - Welding Traceability to be provided by welders ID Recorded near to the weld joint and on the workshop drawings, this shall then transferred to the welding Fabrication Welding Summary, for submission in the MDR
Acceptance Criteria - AS/NZS5131:2016 Section 7.4.2 CHAR(AMP) Table 7.4 AS/NZS/ISO 3834.2
Performed - GEL Workshop/ Welding Supervisor
Records - Fabrication CHAR(AMP) Weld Summary Reports
Stage/Frequency - All weld Joints
INSPECTION BY: GEL - P
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
2.1 - Weld Category : All Weld are category SP(Structural Purpose ) Unless Specifically stated on drawings as Category GP
Acceptance Criteria - AS/NZS 1554.1:2014 CHAR(AMP)Structural Spec :6.12.1
Performed - GEL Workshop/ Welding Supervisor
Records - Approved Shop Drawings
Stage/Frequency - All
INSPECTION BY: GEL - P
INSPECTION BY: C - —
INSPECTION BY: SGS - R
Comments - —
3.2 - Non Visual Examination NDT Requirements, Non Visual Examination in Accordance with AS/NZs 5131 Table I7 and Table I5 Magnetic Particle Testing (MPI)- AS1171 Ultrasonic test (UT) - AS2207
Acceptance Criteria - AS/NZS 5131:2016 Section 13.6 ○ AS/NZS 3404.1:2009 Section 8 ○ AS/NZS/ISO 3834.2 Structural Specification: 6.12.5 (Table 6.5 CHAR(AMP) 6.6) ○ AS 2207 CHAR(AMP) AS1171
Performed - Independent third Party
Records - NDT Reports
Stage/Frequency - Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, Category "A" - UT 50% (25%)²of Butt welds including 10 of the first 10 joints ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints.
INSPECTION BY: GEL - H
INSPECTION BY: C - R
INSPECTION BY: SGS - P
Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
3.3 - Weld Defects : All Weld defects revealed by visual or non - visual examination shall be repaired with the requirements of the standard, each weld defect shall be assessed in accordance with the appropriate, clause in the relevant part of the AS/NZS 1554 series,
Acceptance Criteria - AS/NZS 5131:2016 AS/NZS 1554.1:2014 Section 5.8 Structural Specification : 6.12.6
Performed - GEL
Records - NDE Reports
Stage/Frequency - Any Weld Repair
INSPECTION BY: GEL - P/H
INSPECTION BY: C - R
INSPECTION BY: SGS - P
Comments - Weld Inspector Report Required
4.1 - Compile Site Delivery Docket/Load List - Load List /delivery Dockets to be maintained, Fabricated components to be delivered to site - Load and Phase wise
Acceptance Criteria - GEL Procedures
Performed - GEL
Records - Delivery Dockets
Stage/Frequency - All Site Delivered Materials
INSPECTION BY: GEL - P/M
INSPECTION BY: C - R
INSPECTION BY: SGS - —
Comments - —
4.2 - Site Erection - Drawings and Document Revision Review
Acceptance Criteria - AS/NZS 5131:2016 Section 11,12 CHAR(AMP) Appendix FCHAR(AMP)AS/NZS 3404.1:2009 Sec 4
Performed - GEL
Records - IFC Drawings
Stage/Frequency - All Structural Steel
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - —
Comments - —
4.3 - Erection Tolerances
Acceptance Criteria - AS/NZS 3404.1:2009 CHAR(AMP) AS/NZS 5131:2016 Section 12 Structural Specification: 6.13.2
Performed - GEL
Records - Site Sign off Reports
Stage/Frequency - All Structural Steel
INSPECTION BY: GEL - P
INSPECTION BY: C - R/A
INSPECTION BY: SGS - —
Comments - —
4.4 - Methodology - Installation and Erections tightening of bolts, tensioning of bolts, and all other required methods
Acceptance Criteria - AS/NZS 5131:2016, CHAR(AMP) GEL Procedures Structural Specification: 6.13.3
Performed - GEL
Records - Site Sign off Reports
Stage/Frequency - All Structural Steel
INSPECTION BY: GEL - P/R/A
INSPECTION BY: C - R/A
INSPECTION BY: SGS - —
Comments - —
4.5 - Site Welding - Qualified Welders
Acceptance Criteria - AS/NZS 5131:2016 Section 7 AS/NZS 1554.1:2014 ISO 3834.2 Approved drawings
Performed - GEL
Records - Welder Qualification Register
Stage/Frequency - All site Welding
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - —
4.6 - Site - Visual Scanning : 100% Category A,B CHAR(AMP) C Visual Examination : 100% Category A, and 25% Category B CHAR(AMP) C
Acceptance Criteria - AS/NZS ISO3834.2 AS/NZS 1554.1:2014 AS/NZS 5131: Section 13.6
Performed - Independent third Party
Records - Inspection Reports
Stage/Frequency - All Welds
INSPECTION BY: GEL - P/M/R
INSPECTION BY: C - R
INSPECTION BY: SGS - P
Comments - —
4.7 - Site - NDT Testing Non Visual : Magnetic Particle Testing AS1171 Ultrasonic Testing AS2207
Acceptance Criteria - AS/NZS 5131:2016 Section 13.6 AS/NZS 3404.1:2009 Section 8 AS/NZS ISO3834.2, AS/NZS 1554.1:2014 AS1171,AS2207 CHAR(AMP) GEL Procedures Structural Spec:6.12.5 (Table 6.5 CHAR(AMP) 6.6)
Performed - Independent third Party
Records - NDE Reports
Stage/Frequency - Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints, CHAR(AMP) Category "B" MPI to 10% of Fillet Welds Category "A" - UT 100% (50%)²of Butt welds ¹ CHAR(AMP) Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints.
INSPECTION BY: GEL - P/M/R
INSPECTION BY: C - R
INSPECTION BY: SGS - P
Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1 Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
4.8 - Bolts,Nuts,Fateners and Screws
Acceptance Criteria - AS/NZS1252.1 CHAR(AMP) AS/NZS 5131:2016 Section 5.5 CHAR(AMP) Structural Spec:6.11.4 CHAR(AMP) 6.11.4.1CHAR(AMP)2
Performed - GEL
Records - Material Register with Certs CHAR(AMP)Site Sign off Reports
Stage/Frequency - All the Site connections
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - for Grade info Please see Structural Spec.
4.9 - Bolting Installation
Acceptance Criteria - AS/NZS 3404.1:2009 Section 4 CHAR(AMP) AS/NZS 5131:2016 Section 8 GEL Procedure : OP022
Performed - GEL
Records - Site Sign off Reports
Stage/Frequency - Each Member
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - R
Comments - —
4.1 - Site Final Inspection
Acceptance Criteria - AS/NZS 5131 :2016 CHAR(AMP) AS/NZS 2312
Performed - GEL
Records - QC Site Sign off Reports/Summary
Stage/Frequency - Completion of Each Phase / or As agreed
INSPECTION BY: GEL - H
INSPECTION BY: C - H
INSPECTION BY: SGS - —
Comments - —
5.1 - Manufacturer Data Records(MDR) - Compile all the quality documentation as required by the specification and submit to the client
Acceptance Criteria - AS/NZS5131:2016 Appendix E Structural Specification: 6.4.2.5 CHAR(AMP) 6.5(PS) ○ AS/NZS ISO3834.2
Performed - GEL
Records - Manufacturer Dat Reports (MDR)
Stage/Frequency - Completion of Work
INSPECTION BY: GEL - P
INSPECTION BY: C - R
INSPECTION BY: SGS - —
Comments - Including PS3 and EPD Information