## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-008 - Structural Steel Pier | itp |  |  |  |  | ITP-008 - Structural Steel Pier - Rev05
section | 1.0 - Pre-Start Fabrication
checkpoint | 1.1 - Technical review
label | Acceptance Criteria - AS/NZS 5131 : 2016 - Section 4.5.2, ISO 3434.2 & Client Specification
label | Performed - GEL
label | Records - Technical Review
label | Stage/Frequency - Post Award
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - Prior to Construction
checkpoint | 1.2 - Shop Drawings
label | Acceptance Criteria - AS/NZS 5131 :2016 Section 4.4 & Structural Specification: 6.7
label | Performed - Cadtec/GEL
label | Records - Approved Drawings
label | Stage/Frequency - Prior to Fabrication
label | INSPECTION BY: GEL - H
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - Please refer to Section 6.7 of the Structural Spec to ensure that all items are covered.
holdpoint | HOLD POINT
checkpoint | 1.3 - Quality Management System
label | Acceptance Criteria - ISO 9001 & AS/NZS 3834 Certification is Current
label | Performed - GEL
label | Records - QMS Records
label | Stage/Frequency - Awarded
label | INSPECTION BY: GEL - R
checkpoint | 1.4 - SFC Certification to be current and minimum CC3 as per the Construction Category, if any non SFC Certified, Sub-Contractors are Proposed to be used, approval required from the design engineer and principal.
label | Acceptance Criteria - AS/NZS 5131 & Structural Specification: 6.4.2.3
label | Performed - GEL
label | Records - GEL QMS records
label | Stage/Frequency - SFC Certificates
label | INSPECTION BY: GEL - R
checkpoint | 1.5 - Document Approval - Submission of Quality Plan, ITP and Procedures for Client Approval
label | Acceptance Criteria - AS/NZS5131:2016, Client Specification
label | Performed - GEL
label | Records - QP and ITP Transmittal Records
label | Stage/Frequency - Post Award and Prior to Works Execution
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
checkpoint | 1.7 - Steel Supply (Third Party Certified Mill - ACRS ONLY) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1
label | Acceptance Criteria - Structural Specification: 6.4.2.6 & 6.8
label | ○ NZS1163 Grade 350/400
label | ○ NZS1594 Grade 300
label | ○ NZS3678 Grade 350 L15
label | ○ NZS 3679.1 Grade 300/300 SO
label | ○ NZS 3679.2 Grade 350 L15 / SO
label | ○ NZS4600 G450 Z275
label | ○ NZS 4671 Grade 300E
label | Performed - GEL, Independent third Party
label | Records - Steel Mill Certificates
label | Stage/Frequency - Each Delivery Received, Third Party Audits Quarterly
label | INSPECTION BY: GEL - R
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - Material Certificates Included in Manufacturer Data Reports
checkpoint | 1.8 - Steel Supply (Third Party Certified Mill - Non- ACRS) Steel grade to Comply With relevant Standards as required by Specification and NZS 3404.1
label | Acceptance Criteria - Structural Specification: 6.4.2.6 & 6.8
label | ○ NZS1163 Grade 350/400
label | ○ NZS1594 Grade 300
label | ○ NZS3678 Grade 350 L15
label | ○ NZS 3679.1 Grade 300/300 SO
label | ○ NZS 3679.2 Grade 350 L15 / SO
label | ○ NZS4600 G450 Z275
label | ○ NZS 4671 Grade 300E
label | ○ Report: SCNZ 111:2018
label | Performed - GEL, Independent third Party
label | Records - Steel Mill Certificates, Third Party Product Certification
label | Stage/Frequency - Each Delivery Received, Third Party Audits Quarterly
label | INSPECTION BY: GEL - R
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - Material Certificates Included in Manufacturer Data Reports
label | ○ Where steel is to be procured from a non-ACRS mill, the compliance pathway is to be requested for each Mill using TSUBs referencing the guidance provided in Report SCNZ 111:2018.
label | ○ Ref. Figure 3 for CC3 pathway
checkpoint | 1.9 - Steel Supply (Non-Third Party Certified Mill Certs), (Requirements additional to 1.7 above), 100% Independent Third Party Material Chemical and Mechanical Verification testing undertaken in NZ
label | Acceptance Criteria - Third Party Test Reports
label | ○ Chemical, Mechanical and Weldability comparison
label | ○ Testing Accordance with SCNZ 111:2018 Standard Sample & Test Plan
label | Performed - NZ based IANZ, Accredited Laboratory, Independent third Party
label | Records - Steel Mill Certificates, All third party Test Certificates
label | Stage/Frequency - Each Delivery Received - 100% of all heat numbers, Third Party Audits Quarterly
label | INSPECTION BY: GEL - P/R/A
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - Material Certificates & Third Party Test Reports, Included in Manufacturer Data Reports
checkpoint | 1.10 - Material Delivery: Confirm As per the Purchase order, Confirm Heat Numbers as per the delivery docket, Confirm all Steel marked with Heat number & PO number prior to Unloading truck
label | Acceptance Criteria - AS/NZS5131:2016 ISO 3834.2 GEL Procedures
label | Performed - GEL
label | Records - Delivery Notes Steel Mill Certificates
label | Stage/Frequency - Each Delivery Received
label | INSPECTION BY: GEL - H
holdpoint | HOLD POINT
section | 2.0 - Start Fabrication & Welding
checkpoint | 2.1 - Material Traceability: Heat Number of each item is traceable by part, Mark on assembly shop drawing reference back to nesting/cutting schedule, Confirm Heat Numbers as per the delivery docket, Confirm all steel marked with Heat Number, and PO number if possible Prior to Unloading Truck.
label | Acceptance Criteria - AS/NZS5131:2016 - 4.7 ISO 3834.2 GEL Procedures
label | Performed - GEL
label | Records - Assembly shop drawings and nesting/cutting schedules
label | Stage/Frequency - All Parts
label | INSPECTION BY: GEL - P
label | INSPECTION BY: SGS - R
checkpoint | 2.2 - Fabrication - Material Cutting, Shaping, Holing, and Corners, accordance with the Construction Standard, Unless otherwise specified in the drawings/Specification - Supervised by Workshop Supervisors
label | Acceptance Criteria - AS/NZS 3404.1:2009 Section 3
label | ○ AS/NZS 5131:2016 Section 6
label | ○ Approved Fabrication drawings
label | Performed - GEL
label | Records - GEL Procedures & Approved Drawings
label | Stage/Frequency - Every Fabricated Item
label | INSPECTION BY: GEL - P
label | INSPECTION BY: SGS - R
checkpoint | 2.3 - Fabrication Inspection - performed by Workshop Supervisor/RWC
label | Acceptance Criteria - AS/NZS 5131:2016 Section 13.5
label | Performed - GEL
label | Records - QC Fabrication & Weld Summary Reports
label | Stage/Frequency - Every Fabricated Item
label | INSPECTION BY: GEL - H
label | INSPECTION BY: SGS - R
holdpoint | HOLD POINT
checkpoint | 2.4 - Fabrication Tolerances : Shall confirm to the construction standard requirements unless specified in the drawings
label | Acceptance Criteria - AS/NZS 5131:2016 Structural Specification: 6.10.2
label | Performed - GEL
label | Records - Shop Drawings
label | Stage/Frequency - Every Fabricated Item
label | INSPECTION BY: GEL - H
label | INSPECTION BY: SGS - R
holdpoint | HOLD POINT
checkpoint | 2.5 - Weld Access Holes: Weld Access holes shall be accordance with the Construction Standard left open after welding, and the access hole area shall be cleaned to meet Welding Standards, unless otherwise specified on the drawings/specification or confirmed by the design engineer for closure,
label | Acceptance Criteria - AS/NZS5131:2016 Section 6.7.7 Structural Specification: 6.12.5.2 RFI # GEL-QA-5600-001
label | Performed - GEL
label | Records - Approved drawings / Structural Specification
label | Stage/Frequency - All the Access hole members
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | Comments - Weld Access Holes to be Closed on Category 1 and 2 members and Remain Open on Category 3 and 4 Members, As Per RFI#189(GEL-QA-RFI-5600-001)
checkpoint | 2.6 - Welding Procedures - Approved Prior to Welding
label | Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1
label | ○ AS/NZS 1554.1:2014
label | Performed - GEL Welding Supervisor / Inspector
label | Records - QC Summary - Welding Procedure Register
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - A
label | INSPECTION BY: SGS - R
checkpoint | 2.7 - Welding Plan - Qualified Welding Supervisor/Competent Person
label | Acceptance Criteria - AS/NZS 5131:2016 Section 7
label | ○ AS/NZS 1554.1:2014 ISO 3834.2
label | ○ Approved Fabrication drawings
label | Performed - GEL Welding Supervisor
label | Records - QC Fabrication & Weld Summary Reports
label | Stage/Frequency - Every Welding Item
label | INSPECTION BY: GEL - P
label | INSPECTION BY: SGS - R
checkpoint | 2.8 - Welder Qualifications
label | Acceptance Criteria - AS/NZS 5131:2016 Section 7.4.1 ISO9606.1:2017
label | Performed - GEL Welding Inspector
label | Records - QC Summary B39 - Welder Qualification Register
label | Stage/Frequency - All Weld Joints
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - A
label | INSPECTION BY: SGS - R
checkpoint | 2.9 - Welding Traceability to be provided by welders ID Recorded near to the weld joint and on the workshop drawings, this shall then transferred to the welding Fabrication Welding Summary, for submission in the MDR
label | Acceptance Criteria - AS/NZS5131:2016 Section 7.4.2 & Table 7.4 AS/NZS/ISO 3834.2
label | Performed - GEL, Workshop/Welding Supervisor
label | Records - Fabrication & Weld Summary Reports
label | Stage/Frequency - All weld Joints
label | INSPECTION BY: GEL - P
label | INSPECTION BY: SGS - R
checkpoint | 2.10 - Weld Category : All Weld are category SP(Structural Purpose ) Unless Specifically stated on drawings as Category GP
label | Acceptance Criteria - AS/NZS 1554.1:2014 &Structural Spec: 6.12.1
label | Performed - GEL Workshop/ Welding Supervisor
label | Records - Approved Shop Drawings
label | Stage/Frequency - All
label | INSPECTION BY: GEL - P
label | INSPECTION BY: SGS - R
checkpoint | 2.11 - Welding - Clean all Welded Areas, smooth the edges and remove any spatter, AESS - Architecturally exposed structural steel (AESS) Shall confirm to the requirements Construction Standard/Specification
label | Acceptance Criteria - AS/NZS 5131:2016, AESS Structural Specification : 6.15
label | Performed - GEL
label | Records - Approved Shop Drawings
label | Stage/Frequency - As per the specification
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R/A
section | 3.0 - Post weld
checkpoint | 3.1 - Visual Scanning : 100% - Category A,B & C, Visual Examination : 100% - Category A, 25% - Category B & C
label | Acceptance Criteria - AS/NZS 5131 Appendix I Structural Specification: 6.12.5 (Table 6.5 and 6.6)
label | ○ AS/NZS 3404.1:2009 Section 8
label | ○ AS/NZS/ISO 3834.2
label | Performed - Independent third Party
label | Records - QC Fabrication & Weld Summary & NDT Reports
label | Stage/Frequency - All Welds
label | INSPECTION BY: GEL - H
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - P
holdpoint | HOLD POINT
checkpoint | 3.2 - Non Visual Examination NDT Requirements, Non Visual Examination in Accordance with AS/NZs 5131 Table I7 and Table I5 Magnetic Particle Testing (MPI)- AS1171 Ultrasonic test (UT) - AS2207
label | Acceptance Criteria - AS/NZS 5131:2016 Section 13.6
label | ○ AS/NZS 3404.1:2009 Section 8
label | ○ AS/NZS/ISO 3834.2 Structural Specification: 6.12.5 (Table 6.5 & 6.6)
label | ○ AS 2207 & AS1171
label | Performed - Independent third Party
label | Records - NDT Reports
label | Stage/Frequency - Category "A" - MPI to 25% (10%)² of Fillet Welds including 10 of the first 10 joints,
label | ○ Category "A" - UT 50% (25%)²of Butt welds including 10 of the first 10 joints^1
label | ○ & Category "B" - UT - 25% (10%)² of butt welds¹ including 10 of the first 10 joints.
label | INSPECTION BY: GEL - H
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - P
label | Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1
label | ○ Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
holdpoint | HOLD POINT
checkpoint-no-status | Notes: ^1 - Ultrasonic Testing on buttwelds shall include scanning for lamellar defects on plates in excess of 30mm thick. 2 - Extent of testing may be reduced to the figure in brackets once the welding inspector is satisfied is that the contractor is consistently achieving the weld QA requirements.
checkpoint | 3.3 - Weld Defects : All Weld defects revealed by visual or non - visual examination shall be repaired with the requirements of the standard, each weld defect shall be assessed in accordance with the appropriate, clause in the relevant part of the AS/NZS 1554 series,
label | Acceptance Criteria - AS/NZS 5131:2016, AS/NZS 1554.1:2014 Section 5.8 Structural Specification: 6.12.6
label | Performed - GEL
label | Records - NDE Reports
label | Stage/Frequency - Any Weld Repair
label | INSPECTION BY: GEL - P/H
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - P
label | Comments - Weld Inspector Report Required
section | 4.0 - Site Erection
checkpoint | 4.1 - Compile Site Delivery Docket/Load List - Load List/delivery Dockets to be maintained, Fabricated components to be delivered to site - Load and Phase wise
label | Acceptance Criteria - GEL Procedures
label | Performed - GEL
label | Records - Delivery Dockets
label | Stage/Frequency - All Site Delivered Materials
label | INSPECTION BY: GEL - P/M
label | INSPECTION BY: C - R
checkpoint | 4.2 - Site Erection - Drawings and Document Revision Review
label | Acceptance Criteria - AS/NZS 5131:2016 Section 11,12 & Appendix F&AS/NZS 3404.1:2009 Sec 4
label | Performed - GEL
label | Records - IFC Drawings
label | Stage/Frequency - All Structural Steel
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
checkpoint | 4.3 - Erection Tolerances
label | Acceptance Criteria - AS/NZS 3404.1:2009 & AS/NZS 5131:2016 Section 12 Structural Specification: 6.13.2
label | Performed - GEL
label | Records - Site Sign off Reports
label | Stage/Frequency - All Structural Steel
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R/A
checkpoint | 4.4 - Methodology - Installation and Erections tightening of bolts, tensioning of bolts, and all other required methods
label | Acceptance Criteria - AS/NZS 5131:2016, & GEL Procedures Structural Specification: 6.13.3
label | Performed - GEL
label | Records - Site Sign off Reports
label | Stage/Frequency - All Structural Steel
label | INSPECTION BY: GEL - P/R/A
label | INSPECTION BY: C - R/A
checkpoint | 4.5 - Site Welding - Qualified Welders
label | Acceptance Criteria - AS/NZS 5131:2016 Section 7, AS/NZS 1554.1:2014 ISO 3834.2 Approved drawings
label | Performed - GEL
label | Records - Welder Qualification Register
label | Stage/Frequency - All site Welding
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
checkpoint | 4.6 - Site - Visual Scanning : 100% Category A,B & C Visual Examination : 100% Category A, and 25% Category B & C
label | Acceptance Criteria - AS/NZS ISO3834.2 AS/NZS 1554.1:2014, AS/NZS 5131: Section 13.6
label | Performed - Independent third Party
label | Records - Inspection Reports
label | Stage/Frequency - All Welds
label | INSPECTION BY: GEL - P/M/R
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - P
checkpoint | 4.7 - Site - NDT Testing Non Visual: Magnetic Particle Testing AS1171 Ultrasonic Testing AS2207
label | Acceptance Criteria - AS/NZS 5131:2016 Section 13.6
label | ○ AS/NZS 3404.1:2009 Section 8
label | ○ AS/NZS ISO3834.2, AS/NZS 1554.1:2014
label | ○ AS1171,AS2207 & GEL Procedures Structural Spec:6.12.5 (Table 6.5 & 6.6)
label | Performed - Independent third Party
label | Records - NDE Reports
label | Stage/Frequency - Category "A" - MPI to 25% (10%)^2 of Fillet Welds including 10 of the first 10 joints, & Category "B" MPI to 10% of Fillet Welds
label | ○ Category "A" - UT 100% (50%)²of Butt welds^1
label | ○ & Category "B" - UT - 25% (10%)² of butt welds^1 including 10 of the first 10 joints.
label | INSPECTION BY: GEL - P/M/R
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - P
label | Comments - Minimum Hold Times prior to NDT as per AS/NZS 5131:2016, Table 13.6.2.1
label | ○ Where a Welding non - compliance is noted through NDE in addition to reinspection of the weld repair, three additional consecutive joints to be inspected, per AS/NZS3404.1 8.1.14
checkpoint-no-status | Notes: ^1 - Ultrasonic Testing on buttwelds shall include scanning for lamellar defects on plates in excess of 30mm thick. 2 - Extent of testing may be reduced to the figure in brackets once the welding inspector is satisfied is that the contractor is consistently achieving the weld QA requirements.
checkpoint | 4.8 - Bolts,Nuts,Fateners and Screws
label | Acceptance Criteria - AS/NZS1252.1 & AS/NZS 5131:2016 Section 5.5 & Structural Spec: 6.11.4 & 6.11.4.1&2
label | Performed - GEL
label | Records - Material Register with Certs &Site Sign off Reports
label | Stage/Frequency - All the Site connections
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
label | Comments - for Grade info Please see Structural Spec.
checkpoint | 4.9 - Bolting Installation
label | Acceptance Criteria - AS/NZS 3404.1:2009 Section 4 & AS/NZS 5131:2016 Section 8 GEL Procedure : OP022
label | Performed - GEL
label | Records - Site Sign off Reports
label | Stage/Frequency - Each Member
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | INSPECTION BY: SGS - R
checkpoint | 4.10 - Site Final Inspection
label | Acceptance Criteria - AS/NZS 5131 :2016 & AS/NZS 2312
label | Performed - GEL
label | Records - QC Site Sign off Reports/Summary
label | Stage/Frequency - Completion of Each Phase / or As agreed
label | INSPECTION BY: GEL - H
label | INSPECTION BY: C - H
holdpoint | HOLD POINT
section | 5.0 - Documentation
checkpoint | 5.1 - Manufacturer Data Records(MDR) - Compile all the quality documentation as required by the specification and submit to the client
label | Acceptance Criteria - AS/NZS5131:2016 Appendix E Structural Specification: 6.4.2.5 & 6.5(PS)
label | ○ AS/NZS ISO3834.2
label | Performed - GEL
label | Records - Manufacturer Dat Reports (MDR)
label | Stage/Frequency - Completion of Work
label | INSPECTION BY: GEL - P
label | INSPECTION BY: C - R
label | Comments - Including PS3 and EPD Information
checkpoint | Final Signoff
signoff | Add Signature (GEL / CLIENT / TPI)