## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.WP20.ITP
section | 1 - Preliminary
checkpoint | 1.1 - Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 1.2 - Mobilisation of Machinery & Fit for Purpose inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 1.3 - Gravel Compliance
label | Checked By: RSA - Review
section | 2 - Entry Turnout
checkpoint | 2.1 - CH and FDM Clearance
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 2.2 - Set out Entry Turnout dimensions and Delineate Clearance Boundaries
label | Checked By: RSA - Monitor
checkpoint | 2.3 - Clear & Grub
label | Checked By: RSA - Monitor
checkpoint | 2.4 - Box out if required
label | Checked By: RSA - Monitor
checkpoint | 2.5 - Install Invert Table Drain if required
label | Checked By: RSA - Monitor
checkpoint | 2.6 - Gravel cap Entry Pavement
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 2.7 - Install Bitumen Two Coat Seal - 14/10mm C170
label | Checked By: RSA - Monitor
checkpoint | 2.8 - As Built Completed
label | Checked By: RSA - Document
checkpoint | 2.9 - RSA QA Inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | 3 - Access Track
checkpoint | 3.1 - CH and FDM clearance
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 3.2 - Identify extent of work area, clearance boundaries and any required surveying works
label | Checked By: RSA - Monitor
checkpoint | 3.3 - Confirm Dimensions
label | Checked By: RSA - Monitor
checkpoint | 3.4 - Clear & Grub
label | Checked By: RSA - Monitor
checkpoint | 3.5 - Form track profile
label | Checked By: RSA - Monitor
checkpoint | 3.6 - Construct erosion and sediment controls
label | Checked By: RSA - Monitor
checkpoint | 3.7 - Construct water way barriers crossings
label | Checked By: RSA - Monitor
checkpoint | 3.8 - Gravel cap access track (if applicable)
label | Checked By: RSA - Monitor
checkpoint | 3.9 - As Built Completed
label | Checked By: RSA - Document
checkpoint | 3.10 - RSA QA Inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | 4 - Waterway Barrier Works
checkpoint | 4.1 - CH and FDM clearance
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 4.2 - Identify extent of work area, clearance boundaries and any required surveying works
label | Checked By: RSA - Monitor
checkpoint | 4.3 - Set out access road dimensions as per IFC
label | Checked By: RSA - Monitor
checkpoint | 4.4 - Clear & Grub
label | Checked By: RSA - Monitor
checkpoint | 4.5 - Remove Unsuitable Soil and Box out if required
label | Checked By: RSA - Monitor
checkpoint | 4.6 - Fill with Shot Rock & Scalps
label | Checked By: RSA - Monitor
checkpoint | 4.7 - Gravel Cap & Trimming Pavement of WWBW
label | Checked By: RSA - Monitor
checkpoint | 4.8 - RSA QA Inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | 5 - Fencing & Grids
checkpoint | 5.1 - CH & FDM Clearance
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 5.2 - Identify Work Area, boundaries of Fencing
label | Checked By: RSA - Monitor
checkpoint | 5.3 - Inspect fencing materials
label | Checked By: RSA - Monitor
checkpoint | 5.4 - Installation of fencing
label | Checked By: RSA - Monitor
checkpoint | 5.5 - Concrete for base of fencing
label | Checked By: RSA - Monitor
checkpoint | 5.6 - Fence posts caps
label | Checked By: RSA - Monitor
checkpoint | 5.7 - Welding
label | Checked By: RSA - Monitor
checkpoint | 5.8 - Galvanized Painting at Welds
label | Checked By: RSA - Monitor
checkpoint | 5.9 - Gate Chain and Carabiner Clips
label | Checked By: RSA - Monitor
checkpoint | 5.10 - Box Out Grid Footings and Prep Site
label | Checked By: RSA - Monitor
checkpoint | 5.11 - Inspect grid materials
label | Checked By: RSA - Monitor
checkpoint | 5.12 - Compaction for Grid base
label | Checked By: RSA - Monitor
checkpoint | 5.13 - Concrete Abutment / Install Base Slab (if required)
label | Checked By: RSA - Monitor
checkpoint | 5.14 - Position and Install Grid
label | Checked By: RSA - Monitor
checkpoint | 5.15 - Install and Compact Gravel Ramps
label | Checked By: RSA - Monitor
checkpoint | 5.16 - Attach Fence to Box Assembly
label | Checked By: RSA - Monitor
checkpoint | 5.17 - RSA QA inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | 6 - Lease Pads
checkpoint | 6.1 - CH and FDM clearance
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 6.2 - Identify work area, boundaries and survey requirement
label | Checked By: RSA - Monitor
checkpoint | 6.3 - Clear & Grub Topsoil and stack timber
label | Checked By: RSA - Monitor
checkpoint | 6.4 - Lease Entry Construction
label | Checked By: RSA - Monitor
checkpoint | 6.5 - Lease construction
label | Checked By: RSA - Monitor
checkpoint | 6.6 - Compaction of layers in 300mm layers
label | Checked By: RSA - Monitor
checkpoint | 6.7 - Proof roll
label | Checked By: RSA - Monitor
checkpoint | 6.8 - Verification of cross falls/laser set ups
label | Checked By: RSA - Monitor
checkpoint | 6.9 - Final Trim
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
checkpoint | 6.10 - DCP Testing
label | Checked By: RSA - Witness
checkpoint | 6.11 - Gravel Cap (as required)
label | Checked By: RSA - Monitor
checkpoint | 6.12 - Install ESC
label | Checked By: RSA - Monitor
checkpoint | 6.13 - Cellar Installation
label | Checked By: RSA - Monitor
checkpoint | 6.14 - Conductor Installation – Record plumb
label | Checked By: RSA - Monitor
checkpoint | 6.15 - Conductor cemented in place
label | Checked By: RSA - Monitor
checkpoint | 6.16 - 4 x cattle panels to be installed
label | Checked By: RSA - Monitor
checkpoint | 6.17 - Well signage and Pipeline entry mark completed
label | Checked By: RSA - N/A
checkpoint | 6.18 - As Built Completed
label | Checked By: RSA - Monitor
checkpoint | 6.19 - RSA supervisor inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | 7 - Piling
checkpoint | 7.1 - Obtain Senex Excavation Permit
label | Checked By: RSA - Permit Document
checkpoint | 7.2 - Confirm Set out
label | Checked By: RSA - Monitor
checkpoint | 7.3 - Install P3 (control) to 1000mm above ground
label | Checked By: RSA - Monitor
checkpoint | 7.4 - Drive P1, P2 and all remaining Piles to correspond with the control (P3)
label | Checked By: RSA - Monitor
checkpoint | 7.5 - Tug test to client specification to be completed on at minimum two Piles.
label | Checked By: RSA - Monitor
checkpoint | 7.6 - Confirm all Piling Height and Final Location measurements are correct within client specification & Control (P3)
label | Checked By: RSA - Measure
checkpoint | 7.7 - As Built Completed
label | Checked By: RSA - Document
checkpoint | 7.8 - RSA supervisor inspection
label | Checked By: RSA - Hold Point
holdpoint | HOLD POINT
section | Verification of Work Completed
checkpoint | Verification of Work Completed:
note | RSA Supervisor:
textbox | RSA Supervisor - Name:
textbox | RSA Supervisor - Position:
note | Senex Representative:
textbox | Senex Representative - Name:
textbox | Senex Representative - Position:
date | Date:
signoff | Add Signature