## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-097-STR-BRUNT-Precast Kerbs Installation Rev.1 | itp |  |  |  | Yes | ITP-097-STR-BRUNT-Precast Kerbs Installation Rev.1 | 8adadd4f-aeef-43ee-b4b8-295aec4ff88f
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-097-STR-BRUNT-Precast Kerbs Installation
label | ITP Description: Precast Kerbs Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 1
label | Revision Date: 15/12/2023
label | ITP created by: Yasna Naicker
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VR Section 610
checkpoint | 1.2 - Non Dependent
label | Reference - VR Section 620
checkpoint | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries Materials
checkpoint | 2.1 - Grout
label | Reference - IFC Drawings
label | Acceptance Criteria - 40MPa min strength grout or approved equivalent to be used to fill lifting anchor recesses post installation.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Elastomeric Bearing Strip
label | Reference - IFC Drawings
label | Acceptance Criteria - 10mm THK x 100mm wide continuous elastomeric bearing strip to bond to beam flange prior to installation of precast barriers.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Precast Barrier Brackets, M16 4.6/S bolts with nuts and washers, 5mm/10mm glav shim plates
label | Reference - IFC Drawings
label | Acceptance Criteria - Bespoke brackets to suit flange width as per IFC drawings to be inslatted in contact with the underside of the beam flange.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Hold Down Bracket - M20 Nuts, Tapered Plates, 150 x 32mm thick plate Gr350
label | Reference - IFC Drawings
label | Acceptance Criteria - M20 nuts, tapered washers and plates to be installed as part of the assembly of the hold down brackates of precast barriers connection into the precast beams in accordance to IFC drawings.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Documents
checkpoint | 3.1 - Precast Elements
label | Reference - IFC Drawings Section 610
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | These documents are typically stored in a MDR Lot in Team Binder.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP Signed Off
section | 4. Pre-installation Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Survey Set-out of Precast Elements
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.3 - Precast kerbs roughened surface
label | Reference - IFC Drawings Section 610
label | Acceptance Criteria - Roughened surface means concrete surface shall be roughned as construction joint in accordance with IFC drawings and VR Section 610.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Installation Activities
checkpoint | 5.1 - Precast Handling
label | Reference - IFC Drawings Section 620.07 Crane Lift Study
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design.
label | Method - Visual, Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Precast Kerbs Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Precast kerbs shall be placed onto position and orientation and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | ○ Precast barrier brackets installed as per IFC Drawings.
label | ○ The nominal gap between precast elements is as per the IFC Drawings.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Hold-Down Bracket Fastener Tightening - Snug Tight Condition (4.6/S)
label | Reference - IFC Drawings
label | Acceptance Criteria - Place washers, nuts, and plates onto the embedded thread as detailed on the IFC Drawings. Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | Method - Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Precast Traceability
label | Reference - Section 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | Record: The final location of each precast element, showing individual ID and date installed.
label | Attach: Lot Maps showing beam individual IDs
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 6. Post-installation Activities
checkpoint | 6.1 - As-built Survey
label | Reference - IFC Drawings Section 610.47 VR Table 610.472
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - MRPA Quality Management Plan
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP