## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | 8f2d6793-797a-4f3f-b690-1704a2112f2a
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Manufacturing Drawings
checkpoint-status |  |  | checkpoint | PEDS
checkpoint-status |  |  | checkpoint | Secondary lifting
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 50f6562a-2532-5903-8cdc-ef639c8d6955 |  | tickbox | Mould clean with release oil applied correctly
boolean | 18114367-1363-54a5-a7c1-cd8f17b1b385 |  | tickbox | Primary & diagonal dimensions checked
boolean | db26a485-3503-547b-93a8-60425e50c440 |  | tickbox | Openings Checked and Correct
boolean | dc323e81-4c42-5b9e-8ac9-022ac7b83839 |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 8accbe8e-9c14-5ca2-9491-ad503c5a462d |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | 2475ad25-f438-5f19-8ffe-856cc9ddde38 |  | tickbox | Correct Size and Type
boolean | 08f0b557-156a-592c-9e15-4ea132857764 |  | tickbox | Laps and Splices correct
boolean | c44a9709-3cfb-5c6a-8cd5-f511be7558b5 |  | tickbox | Cover Checked
boolean | 0c04c648-c60c-5817-993e-488353aac55c |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | 5ba77e55-ab39-53c9-a04e-83682181211f |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 86695480-7b06-5483-a45d-87923ff3709a |  | tickbox | Starter Bars inserted, checked and correct
boolean | 80d47d44-a379-59eb-922f-689e5b8247a8 |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Upload minimum 4 photos of element ready to pour
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | 1a656695-2ae5-5725-b3fe-3344c5a4e96b |  | tickbox | All Concrete Dockets Attached
text | e628bdc7-f387-5a95-a5fe-4c63be2e2723 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Post-pour dimensional check
boolean | 40a7049d-779f-5aca-8469-1d8f034b9adb |  | tickbox | Primary & diagonal dimensions checked and approved
boolean | a285470d-b7c6-53b3-a1f9-e6e4dbce8e05 |  | tickbox | Lifting anchors checked and approved
boolean | 776ee481-bc18-54ad-8d6a-73bae947b581 |  | tickbox | Critical fitments / fixtures checked and approved
checkpoint-status |  |  | checkpoint | Visual Check - Specified finish achieved
boolean | 8ff5e48c-adf5-5b1d-b9a8-3b9520757a21 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | a06e53bd-2b38-5b49-924c-5d482af95835 |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 63bd3630-01f5-5397-9693-5a182eb74897 |  | tickbox | Openings (formwork removed)
boolean | 22378671-dd2c-53be-a9fa-0fe6b1e404e6 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity & durability
label | 65e5e1f7-a200-58ed-926a-432abc30c5ef |  | note | Raise NCR and notify EP Project Manager to discuss with builder
boolean | f428387a-0f38-5bbe-b22c-40c86e8b78e3 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for stacking delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached (if applicable)
label | 71154732-bfd4-55cd-8cee-59dc031fb75a |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | a5c91ca5-6eb3-4ecc-8ea4-74c39e848786
checkpoint-status |  |  | checkpoint | Details complete
text | 74a9589e-1306-57f5-89a1-a48a5c409d58 |  | textbox | Date:
text | 05b43eca-2009-57ca-b13b-d62cbf181523 |  | textbox | Job/Delivery Address:
text | 53107290-d71d-51db-a446-3de296fd550b |  | textbox | Company name:
text | a57a5082-03a0-5635-bab7-5379d6356a09 |  | textbox | Truck Registration # (Trailer A)
text | 04bf2ad9-4589-5278-84fd-1a02f9ab8934 |  | textbox | Truck Registration # (Trailer B)
select | 0365d57a-cb36-5dac-85c5-be5af35fa42f |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
text | 92ba8e97-1e25-5cbf-a420-cd7ecff7b7fa |  | textbox | Load Number:
checkpoint-status |  |  | checkpoint | Photos of loaded truck
text | 78519544-1d0f-5992-8c5d-394e9c367d3e |  | textbox | Total Units Loaded:
label | f4e785ce-b372-55cb-93d7-a542a8b6a186 |  | note | Trucks are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed.
label | 9f1f108a-2fe5-5b30-81b6-65ea2ef99b3d |  | note | All units\elements have been loaded in a safe manner, with a minimum of one chain used per unit. I understand that the loading of these units is the responsibility of the transport company and should be completed in accordance with the relevant standards and in line with industry best practice.
label | 34d16c9c-60bc-582e-b316-bc5cf57f2cdf |  | note | All safety rules and client requests on the project site will be adhered to at all times. In signing below you agree to abide by these statements.
holdpoint |  |  | signoff | Driver Signature
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | c423bf05-cbaa-4da6-8082-16f10f8d5838
checkpoint-group |  |  | section | Delivery + Prestart
checkpoint-status |  |  | checkpoint | Upload Load list
checkpoint-status |  |  | checkpoint | Upload Birth certificate
checkpoint-status |  |  | checkpoint | Upload Propping Plan
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-group |  |  | section | Hold Point
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (upload copy of builder confirmation)
label | 716555af-da2c-5083-bcfd-f60775e5786d |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (upload photo)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (upload photo)
checkpoint-status |  |  | checkpoint | Toolbox Talk has been completed (upload photo)
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | d7bbf70b-8019-4b20-873d-ddff8e2bb8da
checkpoint-status |  |  | checkpoint | Project details entered below
text | 0faa81c6-be6d-5cbe-99b7-3281a6962089 |  | textbox | Job File Number
text | ea46439b-043b-5e81-a71f-cea71d3848a2 |  | textbox | Project Name
text | cc5aa3aa-145b-5b47-bdc6-1c5174f2d4e6 |  | textbox | Site Address
text | 04cad952-a4bc-5419-ba1f-cc99eb23488f |  | textbox | Main Contractor (e.g. Teak)
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | f2f9afe0-58c1-4b11-bf24-73d25707bbb8
checkpoint-group |  |  | section | Installation Documents
checkpoint-status |  |  | checkpoint | Attach IFC Installation Drawings
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | 94619686-4945-55a4-b4fa-420e2ecb1f61 |  | tickbox | Bedding grout (trowelable) used is as per project specification (upload photo of bag)
boolean | 8a178525-b4c9-52c2-8380-8ab60288045e |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 453cc837-05bf-54e2-975e-18539c2f9d2a |  | tickbox | Grout bed sufficent to ensure full coverage (upload photo of grout bed)
checkpoint-status |  |  | checkpoint | Element installed to:
boolean | 7826b78d-9342-5750-9140-41c462c7ee3d |  | tickbox | Survey Pins
boolean | 6871b5ba-81da-5ff8-a26a-e5a6e16eb99e |  | tickbox | Within 5mm of vertical plumb
boolean | 6227bae5-3394-5ebf-9a24-afc059fae458 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS has minimum two restraint fixings
boolean | f4c57791-ee90-554d-8e0a-974f90060c3b |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand (upload photo)
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 94d4c22f-bbe1-5a1c-af74-4ac680d1c87f |  | tickbox | Dowel tube grout used is as per project specification (upload photo of bag)
boolean | 4d9656d6-c5c6-52e7-933c-5b2a591a1c93 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 47c30420-d1fc-5f6e-91a3-2e4fbad1d99f |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Were there any delays or Site Instructions given
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (upload photos)
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | 5975f92e-72a3-51b1-9459-868845421ce5 |  | tickbox | Caulking product used as per element/project requirements (upload photo of caulking product used)
boolean | 1d4592f1-1d95-5476-a30b-8edacdb6583c |  | tickbox | Open or closed cell backing rod used?
boolean | 7f3442d3-43c6-524c-b12b-d43d2a759afb |  | tickbox | Caulking installed and checked (upload photo)
checkpoint-group |  |  | section | Prop Removal
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (upload)
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (take photo of visible faces of element)
checkpoint-status |  |  | checkpoint | Has the builder signed the Euro Precast Level Sign-off sheet (upload copy) off on the element?