## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Installation Checklist | [5 empty] | Installation Checklist
section | Installation Documents
checkpoint | Attach IFC Installation Drawings
section | Element Install & Grouting
checkpoint | Bedding grout placed and finished as per project requirements
tickbox | Bedding grout (trowelable) used is as per project specification (upload photo of bag)
tickbox | Grout mixed in line with manufacturers recommendations
tickbox | Grout bed sufficent to ensure full coverage (upload photo of grout bed)
checkpoint | Element installed to:
tickbox | Survey Pins
tickbox | Within 5mm of vertical plumb
tickbox | Face alignment within 5mm
checkpoint | Element propped as per Euro Precast PEDS
tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand (upload photo)
checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
tickbox | Dowel tube grout used is as per project specification (upload photo of bag)
tickbox | Grout mixed in line with manufacturers recommendations
tickbox | Dowel tubes filled to top of tubes
checkpoint | Were there any delays or Site Instructions given
checkpoint | Is there any transport or erection damage that needs to be fixed (upload photos)
checkpoint | Area has been cleaned from grout and rubbish
section | Element Caulking
checkpoint | Element caulked as per project requirements
tickbox | Caulking product used as per element/project requirements (upload photo of caulking product used)
tickbox | Open or closed cell backing rod used? (add in comments section)
tickbox | Caulking installed and checked (upload photo)
section | Prop Removal
checkpoint | Has the Builder given us written confirmation that props can be removed (upload)
checkpoint | Upload photo of element after the pros have been removed
section | Basic Patch
checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint | Have the prop points been patching as per project requirements
checkpoint | Have the grout tubes been patching as per project requirements
section | Final Finish
checkpoint | Has all outstanding patching been completed (take photo of visible faces of element)
checkpoint | Has the builder signed off on the element?
checklist-flat | Safe Load Declaration Checklist | [5 empty] | Safe Load Declaration Checklist
checkpoint | Details complete
textbox | Date:
textbox | Project Name:
textbox | Delivery Address:
textbox | Transport Company:
textbox | Truck Registration #
textbox | Trailer Registration
dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint | Upload photo of Load List used for load
checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint | Load Declaration
label | In signing below, you agree and acknowledge that:
label | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
signoff | Driver Signature (must include Company)
checklist | Delivery / Installation Day Checklist | [5 empty] | Delivery / Installation Day Checklist
section | Hold Point
checkpoint | Has the slab reached the minimum strength required (upload copy of builder confirmation)
label | 12MPa for cast-in anchors and 20MPa for post installed anchors
section | Prestart / Start-up
checkpoint | Date of Installation
checkpoint | Exclusion Zone is set up (upload photo)
checkpoint | Plant & Equipment prestart/logbooks filled out (upload photo)
checkpoint | Toolbox Talk has been completed (upload photo)
checklist | Manufacturing Checklist | [5 empty] | Manufacturing Checklist
section | Manufacturing Documents
checkpoint | IFC Manufacturing Drawings
section | Pre-Pour Checks
checkpoint | Mould check
tickbox | Mould clean with release oil applied correctly
tickbox | Primary & diagonal dimensions checked
tickbox | Openings Checked and Correct
tickbox | Rebates, Architectural Grooves Installed Correctly
tickbox | Formwork chamfers installed correctly where required
checkpoint | Reinforcing check
tickbox | Correct Size and Type
tickbox | Laps and Splices correct
tickbox | Cover Checked
tickbox | Spacing Checked
checkpoint | Cast in items check
tickbox | Ferrules/Inserts installed, checked and correct
tickbox | Starter Bars inserted, checked and correct
tickbox | Lifting anchors installed, checked and correct
checkpoint | Check Minimum Cover
checkpoint | ID Tag installed in non-visible face
checkpoint | Pre-Pour checks completed and approval given to pour Element
label | Upload minimum 4 photos of element
checkpoint | Upload photo of signed pre-pour check of shop drawing
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per design
tickbox | All Concrete Dockets Attached
textbox | Date element was cast
section | Post-Pour / Pre Delivery Checks
checkpoint | Post-pour dimensional check
tickbox | Primary & diagonal dimensions checked and approved
tickbox | Lifting anchors checked and approved
tickbox | Critical fitments / fixtures checked and approved
checkpoint | Visual Check - Specified finish achieved
tickbox | Does the finish meet class 2 as per AS3610
tickbox | Chamfers clean, neat and on all required edges
tickbox | Openings (formwork removed)
tickbox | Nailplates / Recesses etc removed
checkpoint | Any Strongbacks Installed where required
checkpoint | Element free from defects that will impact structural integrity or durability?
label | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
tickbox | If NCR raised, take photo of completed approved works
checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
section | Concrete Test Results
checkpoint | Concrete Test Result attached
label | Upload actual test result OR a test result of the same mix design from the same day