## Table 1
INSPECTION AND TEST PLAN
Factory ITP | [6 empty] | ITP No. |  |  | Revision No. | REV02
ITP Name | Factory/manufacture |  | Elevation or Area : building A 5&6
Project | New Footscray Hospital |  | Module. No or Item : CLD-200 perf CW module panel
Building Ref. | Building A level 5&6 |  |  |  | Refer to O&M Manual for Project for maintneance and care proceedures for cladding types
Check / Inspection Required |  | Responsibility | Acceptance Criteria |  | Reference Document / IFC Shop Drawing Number AS1562.1-2018 | Client | Date | Facadex | Date | Comments
IFC shop drawings approved for fabrication |  | MPX | MPX / Architect sign off
Material Approval |  | MPX | MPX / Architect sign off
Check if the pattern is correct to IFC (5005-H34 alloy 51% open area) |  | Facadex | Facadex sign off.
Check carpral extruded profile are jointed with mullion to manufacture's spec (carpral) |  | Facadex | Facadex sign off.
Check 2mm alum is installed to the carpal panel (back of the perf stiffeners), and 2mm alum installed to be back of the carpal utilized panel and insulation to IFC has been installed inside the cavity of the panel |  | Facadex | Facadex sign off.
Confirm and check finish as per approved IFC drawings |  | Facadex | Facadex sign off.
Check panel size and dimensions against IFC drawings |  | Facadex | Facadex sign off.
Check diagonal dimension to ensure odd shape panel are done correctly |  | Facadex | Facadex sign off.
QA has checked delivery docket and receipt from powder coater |  | Facadex | Facadex sign off.
Is fabricated item labelled as per drawing? |  | Facadex | Facadex sign off.
Fabrication complete |  | Facadex | Facadex sign off.
Prevent direct contanct between incompatible materials |  | Facadex | Facadex sign off.
Materials ready to deliver on site |  | Facadex | Facadex sign off.
HOLD POINT- All Criteria above must be signed off before proceeding
Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation. |  | Facadex / Builder | Defect notification via email or chosen coorespondece
Evidence of close out / rectification
(SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
Sign of only once agreed that wall is defect free
AUTHORITY TO PROCEED
Foreman – Checklist Completed |  |  |  | Date / Time
Coordinator – Checklist Completed |  |  |  | Date / Time
In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications. Facadex Construction located at 13-14 Adams Court Sunshine West, VIC 3020