## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | CLG-514 Site Subframing ITP | itp |  |  |  | Yes | CLG-514 Site Subframing ITP | 1deecc07-31df-4e31-8d77-4b082ee73dd9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | ca1cfcea-4710-5f04-bd78-403b7c6f5c3e |  | note | Responsibility: MPX
label | 4281ae9d-6bf0-599a-a102-3ae0f200829b |  | note | – – – – – – – – –
label | 609668aa-6bd5-546f-a956-3a5282c3a54e |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 170f1025-6dc9-5fe2-9cf6-7d0a09197c43 |  | note | – – – – – – – – –
text | 504b8577-ed4e-5020-bab8-a35c3bf44b2e |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e5a061bd-8b11-5a6a-bbc5-ba319dc9435b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | b2448552-d312-5712-8fe9-88571e1a2b71 |  | note | Responsibility: MPX
label | 9706524e-a881-5f43-890c-57b97cf33907 |  | note | – – – – – – – – –
label | c8be18c3-ece9-5114-8200-82433c914211 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 7007f896-f6e9-5b57-a285-dc307db8783c |  | note | – – – – – – – – –
text | d90c2536-f6df-5a60-be0c-cbf64f204fdb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47e16b24-d3bf-5e3b-904d-3808a18b7235 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | 32366e11-72ac-56e7-a9fd-03057491fc33 |  | note | Responsibility: Facadex
label | 302d4b8e-eaca-5e98-ba79-a8b65028fac6 |  | note | – – – – – – – – –
label | 0315af89-1e08-5188-bb70-10cb1b76e018 |  | note | Acceptance Criteria: Facadex sign off.
label | 5efd7e28-4a30-59ee-a50a-bb50e80ea80a |  | note | – – – – – – – – –
text | 256ac7e7-1af0-5eca-83d8-64ab150d947c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fb629c89-f198-5569-838a-30a1ba2b4882 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | f875bd85-fe13-56ee-80d8-e26abddec915 |  | note | Responsibility: Facadex
label | 081d1d7c-4ad2-537b-b9f0-42b936204a3d |  | note | – – – – – – – – –
label | 4e9433d4-f75e-5cfe-930a-ec0ce8eaca2d |  | note | Acceptance Criteria: Facadex sign off.
label | 15609083-7c40-5787-a0b0-2221621f2110 |  | note | – – – – – – – – –
text | d8b62baa-fc43-54ab-8c1a-5fcd83628794 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ed5f3b1b-7b61-5159-bd58-366e8139031d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing underside of the bridge installed as per shop details
label | 2c456287-b374-5d2e-846e-da1e8b927a5f |  | note | Responsibility: Facadex
label | 118b3ef2-c3db-5aca-8fe7-81cf4eec6f72 |  | note | – – – – – – – – –
label | d410e506-d37e-5d70-b9e4-d69f72f4d5b7 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 241a4e09-7be5-5d1f-8f35-9ceccb3c224e |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | d7d2871c-863b-56d3-a40e-9eecb910e0fe |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | f178d5ed-1aaf-59c2-84c8-47843f635639 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 05a1800f-375d-5576-9222-84718c3149b2 |  | note | ○ Expansion & Contraction:
label | 49e104c7-99be-57c0-a2a4-9fff033406f6 |  | note | +/- 3mm @ every 1000mm in length & height
label | 17d6ed1c-8ca5-59a1-b444-9d2c424aa0e8 |  | note | – – – – – – – – –
text | f5f7aab2-dcab-591a-954d-0b00af62f61a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8de09ba2-5a2b-55b5-8e13-c3b945e6042a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing aligned finished level and plumb
label | 1492d3ad-8f04-5dc8-92a3-da7695ec13b0 |  | note | Responsibility: Facadex
label | 87c22a7a-a1dd-5058-b132-aaac6fff3348 |  | note | – – – – – – – – –
label | 3966b101-b897-52cd-a576-116c436bc736 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | ca505238-29a2-5d8f-9479-1d669191a870 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 9078c41d-3889-5475-b12d-b5b342d2d0cc |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | e9749fa5-9733-5129-a9ef-ba0a206aca21 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 41f6d550-403e-5e89-a45f-20039c62b5f5 |  | note | ○ Expansion & Contraction:
label | aaab6584-ebd4-5729-9742-3e3fbfbdc6ca |  | note | +/- 3mm @ every 1000mm in length & height
label | 96bbbb31-4da7-507e-be71-e3dfc3b9b30c |  | note | – – – – – – – – –
text | 432727b7-24a9-5e86-a9f5-2a553ec8918b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e28096f7-c2a3-5ac0-9682-bf237986897d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Top hat to primiry steel (side) or to truss frame (underside) installed and leveled for panel installation
label | f9c1f15a-80eb-578a-9ce2-59afe415e853 |  | note | Responsibility: Facadex
label | 8a98cf86-cc08-55d7-8468-bcaf9e378074 |  | note | – – – – – – – – –
label | 69bbe9aa-aeb7-51d0-ac87-96e597080fa0 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 7013d01f-ac68-5814-977f-e99933e84175 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 3bc206df-23aa-5f18-a97f-cc7285e75caf |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 068d404e-eb57-5047-ac62-8c206a4963bc |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 2f069ec0-b602-52d3-bb84-5d8bddf39009 |  | note | ○ Expansion & Contraction:
label | de3a0032-36a8-5421-bfc5-dafb6b34d250 |  | note | +/- 3mm @ every 1000mm in length & height
label | 87e2703b-84b1-50b6-8a40-a6e24f88bae5 |  | note | – – – – – – – – –
text | 8b13b276-cea1-5d71-9ce8-80b2e3180a96 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 17985dca-f94b-5d25-b726-c1577ccc1ee4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 38fb463c-4e57-5c8b-b0e6-2c5266a5a56f |  | note | Responsibility: Facadex
label | 4a9f54df-d1ee-5876-9e23-34e06ac22e80 |  | note | – – – – – – – – –
label | 677e4a83-2cff-5d07-9679-925fae9546e3 |  | note | Acceptance Criteria: Facadex sign off.
label | d0b1d2e6-cfe0-5321-bf0a-8eabce10ad9c |  | note | – – – – – – – – –
text | 33103e92-79e7-53df-86c4-472c6437ce13 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c5ea2b83-7f9c-5889-b901-d7ed2de7c697 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | f73a52b6-078b-59d5-a715-3f3405f55cd6 |  | note | Responsibility: Facadex / Builder
label | 7d8cdef6-9e57-565e-ba22-1a5e1165a62a |  | note | – – – – – – – – –
label | 0fe48ec3-3ff8-593c-bff6-dc60e142bf71 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 3449ce20-2b41-5bf5-a2df-18d66257c561 |  | note | ○ Evidence of close out / rectification
label | 4592b1d0-238d-5472-a852-eee36230c4c9 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | bf7521b3-14ac-571d-9e69-34c69eabc31b |  | note | ○ Sign off only once agreed that wall is defect free
label | 3a68cd72-1cbc-5da0-8f31-79b01a3fcb73 |  | note | – – – – – – – – –
text | e35239de-e0cd-5464-bd32-237fa0038fc3 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b706439a-2594-5764-b4f8-36163f0427b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 95917769-7c15-5c08-9d1d-b18a691b72e3 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 546d2b4c-9494-500c-a684-70d1dcd8ac87 |  | textbox | Foreman – Checklist Completed:
text | 04873a73-fb3e-5cb7-9c67-d35864ca45cc |  | textbox | Date / Time:
text | 67c2a9d9-0f50-5341-b706-ca5a4e7e9c6c |  | textbox | Coordinator – Checklist Completed:
text | 1e6381cf-b5cc-5c47-9c78-9ef3990c3c36 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Steel Bracket Underside Site ITP | itp |  |  |  | Yes | CLG-514 Steel Bracket Underside Site ITP | 3d078879-0289-4c39-b64c-5e26861ea934
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 446929ec-207e-59b9-a75b-4981ade028d5 |  | note | Responsibility: MPX
label | a846ad6f-59b3-585e-b89f-cfd2995ea844 |  | note | – – – – – – – – –
label | 731eb317-4f80-534c-8382-d8a5dd75b1d6 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 054d0dd8-dcba-5406-a7b1-1306fdae3f36 |  | note | – – – – – – – – –
text | 2586f405-74e6-599b-8a42-bd7476124dae |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 471f77b0-0fac-5db8-9f8c-4a4a376ca753 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 4703acc6-391a-58e4-a072-fe11698ac9ec |  | note | Responsibility: MPX
label | 3dfa898f-e30e-59f9-b597-bacea8ed62a4 |  | note | – – – – – – – – –
label | 22108652-d564-50eb-aee8-826406fa1add |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 0ca97ff6-cfd2-5690-a06c-f944bd6f007e |  | note | – – – – – – – – –
text | e4735e44-f793-5b88-89a9-37056dd63d6f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | caa3d915-459f-5b96-a97a-87969dac0b5d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (steel bracket/Bolts/Washers) delivered to site free of damage and deformation
label | c38aab59-a336-56e6-aed7-68903d235a46 |  | note | Responsibility: Facadex
label | 1e269b30-e967-5cd5-bc47-c15cbcfb5831 |  | note | – – – – – – – – –
label | 29b444ba-add5-5f9b-8716-82c5bd20f5f3 |  | note | Acceptance Criteria: Facadex sign off.
label | 0afcb73f-4181-596e-a755-f14eea67e934 |  | note | – – – – – – – – –
text | d5753630-14e7-5c49-8cde-461e6893ac17 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c2b8e71b-15ef-50b7-80d8-28287fa9f84b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | a060f5e9-c701-5197-bf89-4232bc44d131 |  | note | Responsibility: Facadex
label | d482558e-2b0f-5054-bf02-ac35df439adb |  | note | – – – – – – – – –
label | 1795adbc-d09e-5fce-a25b-bd5f2a377e37 |  | note | Acceptance Criteria: Facadex sign off.
label | 4cda1194-033a-5dcf-ad98-c93ba7a89619 |  | note | – – – – – – – – –
text | 37e160d1-5c93-5fcc-96bd-068f62dc9606 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ae614639-9df8-589f-ad44-542268f09527 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Bracket installed as per shop details and location
label | 3a7440b3-c235-5e52-b25a-626474e238d9 |  | note | Responsibility: Facadex
label | b946e7f8-1fbd-5758-96b8-cf4cb44482f9 |  | note | – – – – – – – – –
label | 33859a26-e662-518b-9558-022d70447ca9 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 238eae00-416f-58de-9faf-5a84a7d5c09b |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | d08b79cb-721e-562d-ac53-cb45ed682e64 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | cb0ced9d-baa3-5fba-80f6-5ae1bccc94be |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | fdce1ccb-bf6b-5646-b114-d1acace66ed5 |  | note | ○ Expansion & Contraction:
label | 24d3f3db-3d55-5adf-af70-07bdf0f19d5c |  | note | +/- 3mm @ every 1000mm in length & height
label | afec86cd-3f19-56ac-b505-910e0ed9b3f5 |  | note | – – – – – – – – –
text | 879889fa-00dd-580d-96bb-55ef6f006da2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 12fb507f-50f7-5cc9-ba37-d598312b8e85 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the correct steel bracket has been installed to the desinated spot along the underside of the pre-camped bridge
label | f8deef29-e2d7-5c60-b3fd-9300c3dd4d14 |  | note | Responsibility: Facadex
label | e281e2f9-9839-5b91-aadf-ab3e8ae6a813 |  | note | – – – – – – – – –
label | 90a9f066-eed3-5f67-b578-46cbf3b5d5a6 |  | note | Acceptance Criteria:
label | 576124df-4b3a-5953-a5b4-fee89cf1b28f |  | note | – – – – – – – – –
text | f7b05487-16af-50d9-a521-ec5d4ef5d50b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c4d748d8-e0a8-5c52-a250-e4ed7c6518a6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the steel bracket installed was not bended or deformed.
label | 9da162dd-2ef0-5043-b2af-94b5669f4f8a |  | note | Responsibility: Facadex
label | 51aa664b-b018-538e-a0b2-87c5919ce540 |  | note | – – – – – – – – –
label | 0c9ffbff-e3da-568e-932f-7432fb267829 |  | note | Acceptance Criteria:
label | 70bc710a-e37d-5d4c-9604-4cfc9fc9bb93 |  | note | – – – – – – – – –
text | 41d3859e-71b4-5d37-a049-08f7dbee44aa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b4339ebf-8a72-58c3-9914-5d3348439ee0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 17fede8f-98b1-577a-9066-81cd12f2596b |  | note | Responsibility: Facadex
label | 25fb70b4-4e49-531c-a0ec-6f729f7342d1 |  | note | – – – – – – – – –
label | 8bba2961-c05e-537c-bbea-a71269e8acda |  | note | Acceptance Criteria: Facadex sign off.
label | 24bd7d45-3714-59d2-a944-d54e0db1c290 |  | note | – – – – – – – – –
text | a152a6de-3626-5131-907c-8a2b5b2dab39 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 89106cfa-cf74-5bf8-bd2e-1e33a8759c50 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | fbf2299e-04e0-5848-a683-66e3e294828c |  | note | Responsibility: Facadex / Builder
label | b4520626-12fd-54d5-b54a-fe3bb2ddca34 |  | note | – – – – – – – – –
label | 609e6090-d775-59ab-9aa0-b49b47fabc01 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ace08c4c-14ae-50f8-8958-bf08d9a66fda |  | note | ○ Evidence of close out / rectification
label | e9cb2343-f464-5e9b-a9a0-5b0b117008fe |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 47c2026e-3650-50e6-9bd9-dd0d37d095bd |  | note | ○ Sign off only once agreed that wall is defect free
label | e34b48b4-8ab0-514e-9156-d948486b4969 |  | note | – – – – – – – – –
text | 216eb731-bab4-5668-bddb-b39f460d0169 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8f3c632e-3b6f-5aec-85b9-ed0151904ae1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 1fc3e133-9d31-57c5-902b-bf91f2353b1b |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 38d322a9-24f5-55ba-8d7a-d5367fecdc23 |  | textbox | Foreman – Checklist Completed:
text | d512c136-19af-5221-b244-f9234c7d7738 |  | textbox | Date / Time:
text | 11611a57-271c-5bab-a228-77c42ffe2aa3 |  | textbox | Coordinator – Checklist Completed:
text | dec1d809-7db8-5295-91a3-e7aa4b4a9843 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D Factory ITP | 4db75297-b146-4025-b6e8-00952c913ad0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | a9a66e95-c9fa-5908-ab13-7265e213e731 |  | note | Responsibility: MPX
label | 2670cf60-7b2a-5baf-8718-a8ccacd43967 |  | note | – – – – – – – – –
label | 53b49f38-b5c1-5430-b6e8-8c396331e5dc |  | note | Acceptance Criteria: MPX / Architect sign off
label | f6512159-0a54-5b30-bba5-9fff542de793 |  | note | – – – – – – – – –
text | 1f6828db-2b4c-5d2c-8f4e-89d05729a77f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c7d5213a-1eb3-5791-b18e-06e74e1c30fe |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 9632c11b-6979-57aa-bfb3-a0f986af9816 |  | note | Responsibility: MPX
label | bdd74657-de38-5fa1-a41d-68fb98230878 |  | note | – – – – – – – – –
label | d8b20b01-8df3-54ae-8507-cf2b9b8d3fa4 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 8bfb0605-588b-5c4d-9f2d-c98e460e656a |  | note | – – – – – – – – –
text | 7d79ffe9-ddd7-5fc4-99c6-762d37dff13d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1a933552-38f6-5ee7-8452-1f21f38d4058 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 0bc3fe8e-1f2a-5d7a-a305-11c48a005d79 |  | note | Responsibility: Facadex
label | 7d8f54c3-f5d6-50de-806b-a36de2013aa0 |  | note | – – – – – – – – –
label | 4914d361-9f83-5c21-94b1-b757a2bbbcc1 |  | note | Acceptance Criteria: Facadex sign off.
label | e83b4e71-ebd9-5428-8168-9c732ab714ba |  | note | – – – – – – – – –
text | 9f565e2d-c408-5aad-8752-db553ef9cc29 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 06b2286d-4028-5462-b5bd-2264e93d5e49 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 516e4076-a3f5-53e7-b1d6-37bd54d18f20 |  | note | Responsibility: Facadex
label | 3f8f7461-69a6-562b-a3be-d32cf8e1cfef |  | note | – – – – – – – – –
label | 46b3e7ec-52f7-52a9-8bc3-2db45e102c6c |  | note | Acceptance Criteria: Facadex sign off.
label | d449f378-52c9-5325-a9af-df38bf61b2cb |  | note | – – – – – – – – –
text | 791b4ad9-8e88-5bf6-b029-dae931b0c6d5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6e7b76b3-04e5-589e-9d14-bb6c642ecf88 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 56d6ecb6-1747-5441-8323-88650be6ec30 |  | note | Responsibility: Facadex
label | ac281623-d9bd-5c11-a8d0-e2ced8edfe1e |  | note | – – – – – – – – –
label | 542c1218-3f90-55a2-8a50-e9ac1f283ef9 |  | note | Acceptance Criteria: Facadex sign off.
label | 33b4205e-192f-5ad6-aa4b-d3d71f3dc9ca |  | note | – – – – – – – – –
text | 513605ca-cc0b-5bc7-85f2-16f9be85f84a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e6edcfd6-356a-52f0-8cb3-b42f09f61002 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 9b739235-ddff-5c00-acd4-3d62cea5814b |  | note | Responsibility: Facadex
label | 688a2c46-b905-59ce-8156-34ba133f174e |  | note | – – – – – – – – –
label | 8743858e-f797-5ca9-9548-b63bdda6e830 |  | note | Acceptance Criteria: Facadex sign off.
label | 1eeeae14-87b4-5278-866c-019de20d68f2 |  | note | – – – – – – – – –
text | 166a798f-b5e8-5cd6-a61a-ab4d06f2013c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 89815d83-92fe-5f8b-9388-bbe781a2988a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 54fba689-f54c-5709-9bed-c430a7688b44 |  | note | Responsibility: Facadex
label | 5b0372b9-f9a6-5a9e-b8e1-f69e04a378ce |  | note | – – – – – – – – –
label | 0b6348a2-88f6-5caf-9fb4-623b594c54a2 |  | note | Acceptance Criteria: Facadex sign off.
label | e8600f6a-0f6f-584a-9fe2-c9a3229f6b4e |  | note | – – – – – – – – –
text | 4348d698-f27e-5a64-8b98-16f12647512d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6406c432-1941-5865-8f27-6c1e6c28da7c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 82c13036-b0be-5cde-b00e-ad29be664813 |  | note | Responsibility: Facadex
label | 23bd7dd1-227c-5e34-ba58-2e22901bf38f |  | note | – – – – – – – – –
label | a4ac351e-465c-528d-bd19-1be7e3b67156 |  | note | Acceptance Criteria: Facadex sign off.
label | 807317d5-abae-54f5-a3f9-a45a53726ab6 |  | note | – – – – – – – – –
text | 319a0117-5468-591b-bbc0-832549afdb25 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 70209290-f1be-5445-b72d-d158ef34bdc7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | 27948ffe-0ee3-5ae3-96a2-e4ffc6f8fbff |  | note | Responsibility: Facadex
label | 39b54c95-bdc4-53f7-a8a0-dcbf26e586a8 |  | note | – – – – – – – – –
label | 58564756-ddb8-590f-9624-ae526143c26b |  | note | Acceptance Criteria: Facadex sign off.
label | 14a5ea5b-0f70-5fcf-b0cf-06775818a362 |  | note | – – – – – – – – –
text | 33e6af0a-450e-5392-9273-55a9d1ab51d7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e7554545-612f-5b54-b0b0-389a2d19c101 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | 325c165c-92d9-5095-a728-83d6457d9eab |  | note | Responsibility: Facadex
label | 81161f0f-d162-52b7-8ece-91c952d54089 |  | note | – – – – – – – – –
label | f2c5956e-51c0-5ea1-9494-517eb4757497 |  | note | Acceptance Criteria: Facadex sign off.
label | ce4d00bd-13aa-5fc7-af63-ff177239bd16 |  | note | – – – – – – – – –
text | b470e367-8238-5850-b490-1fe155152554 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47f19f10-329d-53b6-af1b-25addf7834c4 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 51fe6c08-1ef6-5154-810f-8fbc09068d48 |  | note | Responsibility: Facadex / Builder
label | d9822551-7753-5385-80ff-de961cad0bcd |  | note | – – – – – – – – –
label | df5259f0-2d3c-5916-9445-2a806effb4b0 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ae6f1d72-ba39-5d05-b0bf-6c4f5cbb0fed |  | note | ○ Evidence of close out / rectification
label | ff38436b-99f4-503e-bacc-6e6cfcc7b3d8 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | d7d8571b-8cf3-5c88-a098-fee8ec3e9fc8 |  | note | ○ Sign off only once agreed that wall is defect free
label | 73cb7ca3-6c35-5f43-a901-9c902a186353 |  | note | – – – – – – – – –
text | 2f416b78-3ca0-5a28-80da-33a131a40e89 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c13326a2-cef0-56bb-b962-12232c359f67 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | b0588c1b-3861-509d-82d5-0f40fcb2c8f5 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 1f1003eb-1a50-5b42-95ad-9529456ac2e9 |  | textbox | Foreman – Checklist Completed:
text | eb69e2d8-aa19-542f-add7-ecda0c7b03c5 |  | textbox | Date / Time:
text | 7e218d16-c695-5357-a8e0-56871ccb4179 |  | textbox | Coordinator – Checklist Completed:
text | 58eb3a46-0002-5ab8-b2ca-cc72a0824835 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Z450 Steel Frame ITP | itp |  |  |  | Yes | CLG-506 Z450 Steel Frame ITP | 81f12331-8e8b-46e9-a859-3d15f036f6dc
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 1bcd1a4a-444f-5827-a08b-3226caee2d32 |  | note | Responsibility: MPX
label | 4aa2f3da-ac73-5f26-88de-fcf02317418d |  | note | – – – – – – – – –
label | 4f588a14-b814-59c3-9763-b1d683cf4cfc |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 2ca513aa-2ed0-598d-a4c9-b8718a41cb2c |  | note | – – – – – – – – –
text | df8bf5cd-afeb-54bc-8081-330232dc065d |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7a066aee-8050-5e21-ab75-56e18a23d9a4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | e847074d-6595-507e-8c4b-4429d1bccad5 |  | note | Responsibility: MPX
label | 036ecfca-1a6d-5b6a-a5f7-5462bde9f25c |  | note | – – – – – – – – –
label | 0c5b176d-df3e-5ae6-b099-10bab0bcfb64 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | b5d9ba7d-1c51-575b-bd6b-32017f82acc0 |  | note | – – – – – – – – –
text | 5dd0f348-0b37-54d0-9793-4c25b52956e8 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b008e9d6-a432-5f4a-9d13-7f69981cd1ae |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | 835aa689-24d9-5373-ac41-3dc41cc23ac3 |  | note | Responsibility: Facadex
label | 53acc76a-9fb1-57c1-a326-3e5730bb89da |  | note | – – – – – – – – –
label | 7440e552-c894-5684-8842-384c074ded74 |  | note | Acceptance Criteria: Facadex sign off.
label | f91ca74c-1a1f-540c-b45b-e90fb42235b7 |  | note | – – – – – – – – –
text | 7ccfafb4-fbc5-5b8c-aeb3-99159cd834fa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b038c996-cd8d-5a74-aeda-6965954b6078 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 4b9960c5-6289-5a38-bf6b-c0d6620cd943 |  | note | Responsibility: Facadex
label | 338e2a6e-e91f-55c1-9839-5d0abca62256 |  | note | – – – – – – – – –
label | 3849c1d0-00ff-5ec8-a4c1-4c357885fa22 |  | note | Acceptance Criteria: Facadex sign off.
label | f08d7ece-f180-5c95-a1e2-58dfd89208a4 |  | note | – – – – – – – – –
text | 04be87f9-4513-5230-85a5-296db8913398 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6409af52-542a-553f-b19c-55cefb9fdb65 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing installed as per shop details
label | fb26027a-4667-5c41-8a29-84bd8e54d335 |  | note | Responsibility: Facadex
label | ef186338-6715-52e4-9e42-e760d095c5f2 |  | note | – – – – – – – – –
label | d904b0e8-6a07-5d81-906f-42e85acec713 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e013b175-90f5-52ea-b264-1541e7a7bd8e |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 69e8ab62-85aa-5169-82bc-ea397b344186 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 314cf91c-9e8c-5d07-ae97-26adb4ea9325 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 36bb6bf9-2f32-5f0e-a0ae-67e8dde58be8 |  | note | ○ Expansion & Contraction:
label | 50e0159e-cccd-5022-9b44-e2b347737491 |  | note | +/- 3mm @ every 1000mm in length & height
label | 6dd14948-4cc1-5bad-9d69-d40646fd9692 |  | note | – – – – – – – – –
text | b4c38b14-42da-5cd2-8d50-769242f165a4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c31c14c4-efc8-5938-8485-320a15d8c2ac |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Truss Framing aligned finished level and plumb (height adjusted with deflaction head)
label | 2818d4b6-6170-580b-8bd8-e0a2628b4176 |  | note | Responsibility: Facadex
label | 22348349-ba73-5ca6-85af-ccfa6238bf73 |  | note | – – – – – – – – –
label | bd731a26-32e2-5106-8172-6543f1b6d963 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 66290e86-f56b-5b17-a9e5-fb39566f6573 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 23b5b966-16d3-52cb-8dc5-5252497e87eb |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 87917292-d439-59d0-bf72-1d37b4368eb0 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 667f6e44-e78e-5190-9466-42ab723066de |  | note | ○ Expansion & Contraction:
label | e744c638-3bc0-5715-8997-2ded23f33446 |  | note | +/- 3mm @ every 1000mm in length & height
label | 82f3c13d-9513-547b-ae39-c98154866755 |  | note | – – – – – – – – –
text | 5382816d-ff06-59ea-84a1-65d8c8f01ba1 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 20ebcd94-7cd0-52f7-9657-b74cfb3c9ae7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Top hat to the truss frame installed and leveled for panel installation
label | 199757ef-2d0e-5208-a723-c3627b691f49 |  | note | Responsibility: Facadex
label | cfcc19ea-f9e7-5b45-9972-c8c99595a6c5 |  | note | – – – – – – – – –
label | e4247cd1-ccd7-5e94-8dce-8831aef6c4fb |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 25564ade-69a5-5d58-9ac7-14232e326160 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ba580eb7-0d27-565a-b58f-4131956d2497 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 764ba6f9-c3b5-576f-b672-7c67823d9eef |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 369ce94a-0332-55e1-86ab-f30b0e33eaf8 |  | note | ○ Expansion & Contraction:
label | 76299057-90f4-52b0-a425-7015ae4fa66d |  | note | +/- 3mm @ every 1000mm in length & height
label | 90c9f2ca-325f-5dac-83f6-f7a64e882721 |  | note | – – – – – – – – –
text | 85079f4a-ab95-5302-a215-e9ddb7a9bcb1 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6d8592c7-1fb0-5e55-93e2-cc72720676e3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | f219268c-f22f-5e57-94f7-a88027297a37 |  | note | Responsibility: Facadex
label | dbddcc68-d522-559e-aea9-97671ce77760 |  | note | – – – – – – – – –
label | a9157604-65e7-50d5-89c2-be31a95416f2 |  | note | Acceptance Criteria: Facadex sign off.
label | 29805734-bbe8-546f-ae67-103b23d11c88 |  | note | – – – – – – – – –
text | 6500bd74-ab9e-54f3-8cdf-26e3d0c607f4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | eeefe520-de31-5876-a62b-da6f6910c5e8 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 28cbdfff-d845-5548-94df-f00f0e6b58bf |  | note | Responsibility: Facadex / Builder
label | 3af68ef5-09a4-570a-8118-3a24cb4d9d9c |  | note | – – – – – – – – –
label | c26fafb2-d514-5268-b6eb-74ed55c84027 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 1fa4c526-7ede-5664-af28-4105a5624d42 |  | note | ○ Evidence of close out / rectification
label | 1eb0d537-893b-5b84-85fb-298db8130dc7 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 2ec51d52-0294-5de7-8b66-902fe5770d13 |  | note | ○ Sign off only once agreed that wall is defect free
label | 788506ca-3393-5479-97c8-7a517638a3ab |  | note | – – – – – – – – –
text | c8b9e486-9896-5ac7-8e2b-9ac5de71035c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 4d5654f8-91cf-5311-925b-0332cd0d2aec |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | c9a5e451-e49a-5cee-a41b-2eed3f489a80 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 4b8f878d-2678-5944-bf88-4db598b1257f |  | textbox | Foreman – Checklist Completed:
text | 41dc2d5f-b835-552e-9b67-8bb9aa3ed3bd |  | textbox | Date / Time:
text | 1956e1d4-89e2-5c8e-8aab-91621659840f |  | textbox | Coordinator – Checklist Completed:
text | d6cff3be-93da-54e2-b67e-ecd36d503b49 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Deflection Head Site ITP | itp |  |  |  | Yes | CLG-506 Deflection Head Site ITP | 9e5d96e4-0d48-4fc2-be00-3b1bdbd6926d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | ec42feba-a65a-5f59-b67d-35c151ef6a32 |  | note | Responsibility: MPX
label | 8f20785d-738b-5ba3-a92f-d31ff84b95e8 |  | note | – – – – – – – – –
label | 922942a5-0f7c-5cbb-9023-0e6b51497081 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | be78a95d-27d4-50f7-856b-453fc4f6463f |  | note | – – – – – – – – –
text | acad476a-b342-58b2-a86b-25469884561f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d64120be-932b-5c82-9b7f-94500bd51c19 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 95c319e2-fb97-55d3-9753-28b38f78a9bf |  | note | Responsibility: MPX
label | df61d169-0860-5dd3-be67-130de4223cef |  | note | – – – – – – – – –
label | 0a3a00aa-3979-533d-8681-f140fcb2ccc8 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | ffae6a1f-37f5-52f8-ae05-b323bf97405c |  | note | – – – – – – – – –
text | 36810114-db3a-5ff4-b535-5d71018a084b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fd45bc23-a822-5b4f-ab83-6bdeaea2216f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Deflection head/Bolts/Washers) delivered to site free of damage and deformation
label | 94a35d7c-1339-537f-aa5a-63a374997d9e |  | note | Responsibility: Facadex
label | 3dbd6bfd-96f7-584b-9188-26f1ab6b61fd |  | note | – – – – – – – – –
label | 211c170f-2148-51db-a0eb-d9c3cce53d86 |  | note | Acceptance Criteria: Facadex sign off.
label | dd3892de-5c93-536f-a215-585ccf71ad0d |  | note | – – – – – – – – –
text | 4fbf78d3-9b5a-5b9a-86ae-6e211ce5be92 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6d5a7d22-0e11-50f2-bb10-192e6b8032e0 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 78faedd6-a43b-51cd-af0f-051943d30b78 |  | note | Responsibility: Facadex
label | abaf31bb-0514-54fb-b845-4967acdb630d |  | note | – – – – – – – – –
label | ff9f5e9d-51c3-5e9b-a2f5-b74d43aec660 |  | note | Acceptance Criteria: Facadex sign off.
label | 64d8b4ed-21b2-5a9a-9e6b-7a41c903c983 |  | note | – – – – – – – – –
text | d355f971-3bd3-507e-a3b2-2f3a9551137c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 3acb3171-44f5-590b-b881-071cfb1b06c3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Deflection head installed as per shop details and location
label | 3f834c06-4882-5635-b9f8-c4c2d697a15d |  | note | Responsibility: Facadex
label | 169809e1-b0c3-538e-8d23-311d66566404 |  | note | – – – – – – – – –
label | f171cb1e-6de3-5313-8fe9-2035cad994dd |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e8549b72-6dd0-5936-9189-d01e91754c15 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 066f0883-ee82-5c89-aeca-46511d4087c1 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | a4cdc3a1-5fea-5a25-8a08-3f7ccf0e22f8 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 177cd557-d590-5a21-a4f7-d85b78982055 |  | note | ○ Expansion & Contraction:
label | f6aab044-6dfb-5854-937b-50e3c6a0fbdf |  | note | +/- 3mm @ every 1000mm in length & height
label | 05497910-0055-5323-9fa2-76f00d9762cc |  | note | – – – – – – – – –
text | ec61ee0d-3ad8-5a3e-9728-11f27f09aefa |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 9c2cbe5e-4fce-564f-8a29-591d9ea9559a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Correct size of deflection head has been installed to allow enough depth to outcome the tolerance of the slab.
label | c6a7a73e-9ae8-56dc-b7a2-3f62d2adab1d |  | note | Responsibility: Facadex
label | 303a7430-204d-5f3f-b068-2e9d147ed6ea |  | note | – – – – – – – – –
text | 48a3813d-0cab-5a3d-a6eb-1a4715f00c06 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e3823289-0534-5d7d-b539-ca5846d7a845 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Ensure the deflection head installed was not bended or deformed.
label | 131662df-1f1d-5439-aeb5-f65a51e971de |  | note | Responsibility: Facadex
label | be4668bf-b20f-51d5-a87d-f6cb088fe98a |  | note | – – – – – – – – –
text | 1a3c18e2-aacb-5a73-b7e8-81b79f25ff12 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d7dfb097-d8d1-54da-9736-ef02d9316005 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | f9468045-b91b-5250-bc1e-7f454a44c192 |  | note | Responsibility: Facadex
label | 9ca5e50a-0cac-571d-8e80-e85aacded059 |  | note | – – – – – – – – –
label | 8dcce01d-b651-5f20-aa64-0e065ca2d3aa |  | note | Acceptance Criteria: Facadex sign off.
label | 29ae2819-6c74-5b75-b014-94e65782ac66 |  | note | – – – – – – – – –
text | d17441e7-67e8-5cf8-8c03-3b86a350df67 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | a3d49ec8-1bf1-5fab-a774-51083150b842 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 23d8f660-8de5-5660-ad9c-8ec99cafcc9a |  | note | Responsibility: Facadex / Builder
label | 5c0df33a-e27d-5fa3-9226-2228cf4f5e5d |  | note | – – – – – – – – –
label | 87ab0518-d3d7-550c-91ea-b2ee624fc2fc |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 2e84a30d-0720-5cec-96d6-d8111f338892 |  | note | ○ Evidence of close out / rectification
label | a38d3b23-057c-5157-ae4f-c717716c7158 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | a2aaeeeb-2e7e-51ad-953d-20fcaf0fb2e0 |  | note | ○ Sign off only once agreed that wall is defect free
label | 6cb5e4da-6ab5-5a15-bd67-a27cb3e907a7 |  | note | – – – – – – – – –
text | 2c5fcd4e-5fc8-5bf4-a72c-bd3d9d80d9a7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 630b2b71-a7ee-5afd-9d2e-de8067c7367c |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 2ab3abc8-c304-59b2-b339-9a743dfc3782 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 07522270-9d02-5537-9151-0c0dfe128e17 |  | textbox | Foreman – Checklist Completed:
text | 219f08ee-29dc-53a5-a085-e5fc76475309 |  | textbox | Date / Time:
text | 2f48276e-c352-5978-9787-94dadb9e7a30 |  | textbox | Coordinator – Checklist Completed:
text | 1418abac-12c8-5a7d-9e8b-fde49106f9e6 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-flat |  |  | checklist | FADX-ITP-009 (FTC-05) FACTORY FABRICATION | itp |  |  |  | Yes | Factory ITP | a6095cd7-b3eb-40f2-9e85-f02de0de3b78
checkpoint-status |  |  | checkpoint | Check the delivery docket and compliance certificate is available upon receiving raw material
label | 625a6472-170b-5b8a-b1d8-bd1b14a74db4 |  | note | Responsibility: FACADEX
label | e12f7655-b4b4-5b16-8a90-f92f1308b256 |  | note | – – – – – – – – –
label | e693ceb0-08e7-5e0a-8c24-5386ecc817fd |  | note | Acceptance Criteria: Production manager to sign off
label | 148dd441-5bbb-58e1-9ef0-33ae5fa7e88a |  | note | – – – – – – – – –
text | 9e6a368e-157b-594a-b5b9-7de7cb2ab33e |  | textbox | Shop Drawing number:
text | d03267a3-eca2-55a5-b14f-25a89466a084 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Shop Drawings/Engineering and Samples approved for fabrication
label | c095b0a7-1ea3-5f3a-b0d2-dd0adadb5333 |  | note | Responsibility: FACADEX
label | f2bc06a8-7a19-5410-975b-4da196add95c |  | note | – – – – – – – – –
label | e1fc7442-3a21-5b66-b181-76d459ec5517 |  | note | Acceptance Criteria: Production manager to sign off
label | c6a00730-1d67-5e6f-a7b3-e278aef71ac2 |  | note | – – – – – – – – –
text | 82fbf331-9419-5a72-bc22-99a12bbc9f4d |  | textbox | Shop Drawing number:
text | bcb1fab9-06dc-5f78-97cf-824fa170af2d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections as per approved shop drawings
boolean | df63a612-63eb-537b-95ad-7982b2e4fe7e |  | tickbox | (1) Welded (need to provide welding documents
boolean | 146eb661-9a86-5f78-bfd0-08a3224cb073 |  | tickbox | (2) Bolted, classify the bolt type (nug, TF or TB)
boolean | 012f7906-72c6-593e-ac23-ce283c4f7a34 |  | tickbox | (3) Other
text | 03bb9270-8b12-5082-b43e-5d40bf4b40d1 |  | textbox | Other - Please specify:
label | 5448e12d-6ae1-5582-b516-e9a0293fcbbd |  | note | – – – – – – – – –
label | c71b2087-fc4b-5279-80c6-09cdf4870df7 |  | note | Responsibility: FACADEX
label | 12a8cd21-d0ac-539b-bc84-68b6ca68a221 |  | note | – – – – – – – – –
label | 87653685-391f-5b7d-9ad1-407b00f71bbf |  | note | Acceptance Criteria: Production manager to sign off
label | f06ff1ae-cdb4-5678-b844-519bd9e1376f |  | note | – – – – – – – – –
text | a6aedff2-80d2-52f8-9abf-0336a22ec233 |  | textbox | Shop Drawing number:
text | f2880cc8-fcf3-5426-99c5-9c32bbb67596 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm & check finish as per approved Shop Drawings
boolean | 2e11a29b-de07-58c3-ab4c-bea6470cf6d7 |  | tickbox | (1) Paint (check TDS)
boolean | f00db8d0-c784-5027-8dd3-9d70aafc33c3 |  | tickbox | (2) Powder coat (check warranty certificate)
boolean | 31d709c0-9080-50a2-bd2b-f0fc64be6e7b |  | tickbox | (3) Other
text | f50cfc1f-45cb-56c8-bfb0-1a143258277d |  | textbox | Other - Please specify:
label | 84197aa8-0b8e-5173-9082-d7788330ff73 |  | note | – – – – – – – – –
label | 5acde4d6-e455-5089-adb9-018f9d579791 |  | note | Responsibility: FACADEX
label | 9a7c2926-1949-5b80-87f7-33b87c53ba83 |  | note | – – – – – – – – –
label | 01d7b329-6531-5ba2-bb0f-3bde7478939c |  | note | Acceptance Criteria: Production manager to sign off
label | 0d949a47-3f81-5cd3-8ca9-6339638f3db7 |  | note | – – – – – – – – –
text | a77c9985-e79a-5321-a9e8-10b4a55020fd |  | textbox | Shop Drawing number:
text | 5f4b51c9-82a6-59a9-98c5-1572b5b6c05e |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Panel size and dimensions against drawing
label | 089915be-6a44-5ea8-a3b5-78598a0bcabc |  | note | Responsibility: FACADEX
label | c9c3c6da-bb8d-5be8-b8bf-866bf66376f1 |  | note | – – – – – – – – –
label | 844a8e96-a882-5230-8989-840db35a7b46 |  | note | Acceptance Criteria: Factory QA to sign off
label | 46e8cb6d-c406-59a6-affe-21786eb9b0d4 |  | note | – – – – – – – – –
text | 64f99acc-9937-5d51-a8c0-72901eaf8500 |  | textbox | Shop Drawing number:
text | 02456bf1-2136-5b3f-aa60-6029454b810a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Diagonal dimension to ensure odd shape panel are done correctly
label | 2b5026e7-58c1-5ec8-98c0-b77138403305 |  | note | Responsibility: FACADEX
label | 9bc09515-0f24-5576-8e6e-4671498ba077 |  | note | – – – – – – – – –
label | 632381a2-e2dd-53d2-8a71-6dd0636185ba |  | note | Acceptance Criteria: Factory QA to sign off
label | e585d8ef-2ef4-507a-8abd-9fc43fd3cff6 |  | note | – – – – – – – – –
text | 6bc488d3-bed5-52f1-9dbe-9cab7a5d6786 |  | textbox | Shop Drawing number:
text | ce95dc34-0e5f-54b5-be2c-6fa349d5a6d1 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA check delivery docket and receipt from the painter
label | 3c6b7ea5-d9d3-5e7d-a361-c3ed557707e3 |  | note | Responsibility: FACADEX
label | caa27e4a-b513-5943-b441-20a7058e182a |  | note | – – – – – – – – –
label | 94c2b28f-cb9e-5813-8a98-d9b809877e7d |  | note | Acceptance Criteria: Factory QA to sign off
label | c404aae8-ad8a-548c-b5ac-f933f97bf1ef |  | note | – – – – – – – – –
text | 325ee6ad-59b8-5de7-a5dd-364581f24100 |  | textbox | Shop Drawing number:
text | fbf0cff9-9fee-5730-aca7-9bde59f3027d |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Check Frame dimension against Shop Drawings check Factory QA to sign off
label | 1fca1036-de02-5c97-af8b-4652d3b5ce1d |  | note | Responsibility: FACADEX
label | 95b618f2-cf1a-5742-9094-73ce83d5a560 |  | note | – – – – – – – – –
label | 78dfa871-7fad-5fb5-948b-5be63042328a |  | note | Acceptance Criteria: Factory QA to sign off
label | a76a9cdd-54b2-5011-94d0-54ce84296956 |  | note | – – – – – – – – –
text | d046c2c9-fc9b-5ef2-a111-cfb615af71b3 |  | textbox | Shop Drawing number:
text | 26da131b-33e0-5136-81a6-850897c34f09 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check the finished frame is Square and plumb with bracket attached (if applicable)
label | cf0ffb69-97e4-5225-a3bb-a93f6be914ed |  | note | Responsibility: FACADEX
label | c62e1012-c334-5cdd-ae06-337e60e7c830 |  | note | – – – – – – – – –
label | d13cb2ba-1efb-58a6-81e4-65f304ff62a7 |  | note | Acceptance Criteria: Factory QA to sign off
label | a5ed0f30-c5d0-5106-9a85-cae2f9114042 |  | note | – – – – – – – – –
text | 108a7134-20e9-545c-98aa-07f98dad7819 |  | textbox | Shop Drawing number:
text | a082d7a3-da1b-528b-a7a5-d81a6c2fe852 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if the Crash rail has been fabricated to drawing and attached to the frame of the module
label | b626b1d5-263e-5d73-a155-1e0221dba21c |  | note | Responsibility: FACADEX
label | ed39c058-b5ad-5a73-93a0-60a6e386d25c |  | note | – – – – – – – – –
label | 4257a763-d50c-5a4a-9ddd-36dbf4215ec9 |  | note | Acceptance Criteria: Factory QA to sign off
label | 36ff2fb9-7c03-571f-97b6-817b856c23d5 |  | note | – – – – – – – – –
text | 36fdb0e0-4547-559c-ab46-80a25463113b |  | textbox | Shop Drawing number:
text | af0abd3f-00a8-5054-93c5-13efeebc75b7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check if external grow cable has been installed into the correct location (if applicable)
label | aa8e7e88-695f-5929-ab6a-fa0349d62f4e |  | note | Responsibility: FACADEX
label | f1aa88ed-3fb4-5a1a-90c6-5f40e9fa8487 |  | note | – – – – – – – – –
label | 451dd017-d135-57c2-8ef7-bc428f692c8a |  | note | Acceptance Criteria: Factory QA to sign off
label | fa0e2c84-533d-52d2-af03-2b8d59a86b87 |  | note | – – – – – – – – –
text | d85d2319-2534-52d4-95c6-0b177c231847 |  | textbox | Shop Drawing number:
text | fbfc3207-36bc-58ea-9672-bd84517ec7b1 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Installed finished panels to the frame, and spilt batten been locked with silicone
label | 32ddbfb1-9744-5283-bfb1-c205323f3bba |  | note | Responsibility: FACADEX
label | 7272fdf1-bb74-504b-ac35-06a153da4d43 |  | note | – – – – – – – – –
label | 476b4383-cadb-5d4d-b1f3-834388fa22cb |  | note | Acceptance Criteria: Factory QA to sign off
label | d4c32353-24af-596d-8e8c-3d8b5d06bc56 |  | note | – – – – – – – – –
text | 9a69d348-7c57-5136-87b4-bcdb3c541a53 |  | textbox | Shop Drawing number:
text | 97b91c12-e470-5e46-a683-12099655090b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Horizontal cladding shall have a minimum slope of 1:15 and shall be sloped away from visible vertical façade areas to prevent staining
label | 5d5c9719-5188-5782-9c36-9ee7a673505d |  | note | Responsibility: FACADEX
label | 024029c0-dbb7-5e3d-afd7-ac021e849a08 |  | note | – – – – – – – – –
label | 52a96a66-2b6e-5440-9d9b-f6faf4eb3d90 |  | note | Acceptance Criteria: Factory QA to sign off
label | 6f6ebbcd-275f-5266-993a-81cd07b82652 |  | note | – – – – – – – – –
text | 8458c018-434a-5534-a1e6-a61b51043315 |  | textbox | Shop Drawing number:
text | de605846-770f-5e4e-a4fa-9416064223f8 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | No defects/scratch/dents/distortion/crack (visual) on the finish
label | ce1d0570-8d41-546c-b52d-81a071196868 |  | note | Responsibility: FACADEX
label | 7fe1ddbc-dee5-5131-967b-716a359439c5 |  | note | – – – – – – – – –
label | 6f4522e7-6909-5cf6-a386-118f73f0eead |  | note | Acceptance Criteria: Factory QA to sign off
label | c948b176-d30d-56cb-bf80-b613ff574d73 |  | note | – – – – – – – – –
text | 2fb185a6-b2f7-5735-8fb7-2025d2491f9f |  | textbox | Shop Drawing number:
text | d8de6fb4-0dc7-5c14-a771-71e9a94e0b36 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is Fabricated item labelled as per drawing
select | 20fb3171-6c7f-59e0-94d7-cb88ce7ba0c6 |  | dropdown |  | YES - Label ID, NO
label | b043ddd2-3573-5dde-b93e-a2deeb10acd8 |  | note | – – – – – – – – –
label | 7ce2282e-a2f2-5c7e-a878-3d759cba29cd |  | note | Responsibility: FACADEX
label | d7828805-0d4b-5859-a906-6198046fa530 |  | note | – – – – – – – – –
label | 1b2f77cc-77c5-5e32-9e70-f3fcd9c04e4b |  | note | Acceptance Criteria: Factory QA to sign off
label | d4602960-64ae-5d8c-bb23-f37771debccb |  | note | – – – – – – – – –
label | 7b4af7a0-7de9-55e5-b052-b663a9b59d96 |  | note | Shop Drawing number: N/A
text | ec97bdeb-3b0f-5aac-85c1-5e9dfd0c617e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
select | c1860120-9306-58d3-afbb-2a2ff7a1b148 |  | dropdown |  | Yes,No
label | 58ac6d08-91c8-57cd-936f-5a212c386a77 |  | note | – – – – – – – – –
label | a276da2a-0639-5dc7-b5be-5009a98412cf |  | note | Responsibility: FACADEX
label | fb6ec0bd-7a2e-5830-af06-424f60d1b536 |  | note | – – – – – – – – –
label | 329d8472-32c6-5b4d-97e2-6fec6c509d6b |  | note | Acceptance Criteria: Factory QA to sign off
label | d6bf0815-a081-5261-8ba5-c74060a73751 |  | note | – – – – – – – – –
text | 461f8763-466d-5661-9a5c-0d07fa6e0a32 |  | textbox | Shop Drawing number:
text | 11c3db2d-bde7-59dc-85e6-4f650bed8ad2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Lifting Lugs holes has been drilled on the frames
label | f86ee5e6-322c-580e-8aac-806d0c70ff65 |  | note | Responsibility: FACADEX
label | 215a0cbf-6b97-550c-8213-378e2146daa9 |  | note | – – – – – – – – –
label | 6b57f1ad-da9c-52d7-bfc4-a1afe1a0dbd9 |  | note | Acceptance Criteria: Factory QA to sign off
label | f1a5213d-ade9-5e05-9200-522300c16399 |  | note | – – – – – – – – –
text | 36c42502-437b-5fe1-8db8-105aa10d658d |  | textbox | Shop Drawing number:
text | c53dbe18-d384-523a-b512-258efdfe101c |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Prevent direct contact between incompatible metals, and between green hardwood or chemically treated timber and aluminium or coated steel
label | cc6414b1-ef97-5183-b60c-f569709e4505 |  | note | Responsibility: FACADEX
label | 178967f4-8405-5156-821a-f1b4b1e081fa |  | note | – – – – – – – – –
label | 7d6df5ea-4aaa-5fe8-a078-79681f7b4394 |  | note | Acceptance Criteria: Factory QA to sign off
label | bab38f7d-a826-5282-abb9-077e36e9250b |  | note | – – – – – – – – –
text | d673a6e3-fd6b-576f-9363-dfb99f6febff |  | textbox | Shop Drawing number:
text | 48b973ef-3200-5236-95c6-b51f159b01b4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Pack onto the stillage for delivery after completion of all above
label | e8dbe55d-be3d-5b32-906b-b1e269c63e8e |  | note | Responsibility: FACADEX
label | 51e0af72-5d6a-515f-8bf2-5a206c9ba063 |  | note | – – – – – – – – –
label | 9d3ebd54-b35f-5c69-8678-30e54fb5b6b4 |  | note | Acceptance Criteria: Factory QA to sign off
label | 187c4d8e-f37a-5f98-b6c5-b902a335751b |  | note | – – – – – – – – –
text | fdc320c1-52b6-5b0e-9937-4c4e57a70fd4 |  | textbox | Shop Drawing number:
text | d7bbeb39-b321-56e7-af21-d1a70f4ce70d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 6e59265d-a5ff-5a6d-a194-30dc5b3231e2 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
label | 27b00249-4140-5af4-8451-a0333b378eab |  | note | Ensure the product was done base on the design complying AS standards including the following where applicable
label | 0f4db547-3000-5a9d-9a8e-f12f988c4276 |  | note | • AS1562.1 Clause 5.5 (Resistance to wind pressures)
label | 09d3fd3c-903b-5ecc-8a36-3d824afdd48c |  | note | • AS1530.1 (Combus􀆟bility)
label | 446bd1f4-0dce-54db-ad0d-83488b2b9ed4 |  | note | • AS5637.1 (Fire Hazard Proper􀆟es)
label | 30b50adb-99aa-51ae-8a94-d9ea489c3e78 |  | note | • A S1530.4 (Fire resistance level)
label | ef5424ba-fbe8-571d-9949-751778ee698a |  | note | • A S2904 (Flashings)
text | f9a7d293-3a48-530f-b1f0-0f7749099f2c |  | textbox | Lead Fabricator – Checklist Completed:
text | 6c95c88e-4636-5f50-a655-2d40bdb28650 |  | textbox | Date / Time:
text | e302f4b5-7212-5a71-b527-a59f6ea25cda |  | textbox | Factory Manager – Checklist Completed:
text | 0d48b999-7129-5b8a-8231-1fe84ea1838b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Factory ITP | itp |  |  |  | Yes | CLG-506 Factory ITP | a8d8a701-b9f9-4e55-ab7c-75f5479594ea
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 70d823a2-bf8e-5990-b9c0-b1204af298b8 |  | note | Responsibility: MPX
label | c7249360-6dfb-5d42-86e0-86361e912a11 |  | note | – – – – – – – – –
label | 5412c742-5de5-56c5-bf50-87c0159147b1 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 99a80e88-7f5a-5d30-9eff-25803eb81248 |  | note | – – – – – – – – –
text | e35c7fa5-0716-560e-9af8-0a39d16c8c57 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0f0c66a2-c12b-5d90-a888-6413f0161391 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 40ae0912-3a96-5059-abb0-cc0066a6ab97 |  | note | Responsibility: MPX
label | 57bc53bf-fd9a-55ca-9f5b-e3efaf67f3f8 |  | note | – – – – – – – – –
label | f6b46f22-9c74-50a9-a29f-206a3a8b293d |  | note | Acceptance Criteria: MPX / Architect sign off
label | 99e86514-6695-5392-9e8d-73c71987f1c0 |  | note | – – – – – – – – –
text | 5c34e264-f1c9-5187-b019-b7154da5f892 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 563fa043-8857-542d-b7e4-bc6510729f71 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | 346d58ab-c4f9-58ad-880b-e50dbde2e4e2 |  | note | Responsibility: Facadex
label | 0a5ddfa6-6e70-5e3a-8aaf-388f30121df0 |  | note | – – – – – – – – –
label | 0f409032-86b1-5187-9e59-5457bfbd4aba |  | note | Acceptance Criteria: Facadex sign off.
label | 849126ad-a1de-5363-a727-259f032caa4a |  | note | – – – – – – – – –
text | 7a17b7b6-e320-5549-812d-cbf09cf11ea2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0e3e8104-6d74-564a-8058-c849520589ce |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 8f19cf8d-7a2b-515c-9919-195a505d99f6 |  | note | Responsibility: Facadex
label | 52ca2005-a6de-53a8-a9d1-73be3873cf6c |  | note | – – – – – – – – –
label | c9d1f4ae-d4ab-5ab7-bf45-1dabdf832062 |  | note | Acceptance Criteria: Facadex sign off.
label | 70ad9ff0-0fcd-59c6-acc6-13b98df358f5 |  | note | – – – – – – – – –
text | ba8384a4-410a-5fb9-b714-9ba5157c7541 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 62956516-fd29-55ed-8fbd-118d9707a640 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | 082e9df3-6659-5fa4-b334-94d1c279401c |  | note | Responsibility: Facadex
label | 9ca1d378-0d2f-55c9-bf16-648e604c3bf5 |  | note | – – – – – – – – –
label | a55d51c4-4651-5f04-a071-368c1155668c |  | note | Acceptance Criteria: Facadex sign off.
label | a8b5e172-77a0-5aa2-b630-6ae79ce51059 |  | note | – – – – – – – – –
text | 9a89897a-7f53-5cd0-a9ae-9f59bea95de4 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5cc2bbc8-9adc-54b7-a6cd-ef8f1438c026 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | 2c0769c4-2576-58f8-8a36-6921c041ecbc |  | note | Responsibility: Facadex
label | f62cf42d-8dde-591b-a6ac-2ff20a6cb337 |  | note | – – – – – – – – –
label | 2333e8fa-679e-512c-a06d-9638a26af206 |  | note | Acceptance Criteria: Facadex sign off.
label | 10bebae7-42d7-5efa-9e5d-7eed6da0018a |  | note | – – – – – – – – –
text | fc1c2daa-14ad-58f7-b48f-35ca568e61ad |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0ea041ac-61e9-5686-bce4-f7114926d2b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 1cff9b89-a192-55ef-93b0-d92fb47d57d9 |  | note | Responsibility: Facadex
label | fd05bf36-81de-5664-8f4b-23e1b139deeb |  | note | – – – – – – – – –
label | c1f857c1-b2da-5430-a195-27b1520f9055 |  | note | Acceptance Criteria: Facadex sign off.
label | b1e2f302-f212-5d83-985e-58ff357383c7 |  | note | – – – – – – – – –
text | 6e016355-55e2-551b-87e8-a6b0637877f2 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 2d19e15e-e745-5f4a-8f5b-09f511d51a23 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 0e35ebe2-b56b-551b-9cb4-1bba5503182e |  | note | Responsibility: Facadex
label | 6921f94f-a584-5e80-9c66-58bda8a11e51 |  | note | – – – – – – – – –
label | bb7805b9-959e-5661-99e6-12e903cdbaeb |  | note | Acceptance Criteria: Facadex sign off.
label | 71f27e52-65ba-53d9-bd20-394bdb4ae353 |  | note | – – – – – – – – –
text | d810d8e2-0cd8-5782-a647-a65c99bd6417 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | de409ba8-d030-5967-ad8f-b620194b757d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | e45d48a8-d3f4-5ca1-b45d-6835414a0de9 |  | note | Responsibility: Facadex
label | d3e07e01-e355-5f79-bb03-9ef7d6513162 |  | note | – – – – – – – – –
label | ce198fa2-ca97-5401-8e31-50081deba2e0 |  | note | Acceptance Criteria: Facadex sign off.
label | 46fb2aa4-dc2f-5031-9f95-511a60d9194b |  | note | – – – – – – – – –
text | 5ff982e3-22dd-50fa-b233-34c8b5a5b9b5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1b9e6ba0-f21b-5c5b-9fe4-39d93dd40fcd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | cf01892c-7b94-5646-9484-31e8f22af958 |  | note | Responsibility: Facadex
label | 212910b4-aa7b-5140-b234-277bf7850697 |  | note | – – – – – – – – –
label | dd90abdd-3574-54e6-8d5e-63939561e8fe |  | note | Acceptance Criteria: Facadex sign off.
label | ca79efe9-0837-565e-8bfc-dc851f156c27 |  | note | – – – – – – – – –
text | 7665a709-76f3-5599-9213-a7db575df216 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | df8c175e-3d98-5e4f-8158-fc7f2d036506 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 76f90667-7f46-54e8-97cb-e2809ceb2458 |  | note | Responsibility: Facadex / Builder
label | b8124c35-7677-5ddb-abae-ded8afd0a971 |  | note | – – – – – – – – –
label | d7bca593-d191-5149-a727-85ff3572a0e5 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 81473786-2d9b-5385-b6b3-f58edcaee6a8 |  | note | ○ Evidence of close out / rectification
label | 920f2859-b3cb-53e6-affd-17bf1f55db2a |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 1081add7-1428-5e22-9e65-50b4f7facca6 |  | note | ○ Sign off only once agreed that wall is defect free
label | 397e1602-5882-57dd-b4bb-c1d1d874c6c5 |  | note | – – – – – – – – –
text | fa79b4b8-9a32-521f-ae24-32b7c5078619 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 38705878-1805-556c-853a-16168b7affb7 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 37bcad73-cbe2-52be-be33-498c2ba42c05 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 9adc8865-56d9-5d00-afe6-30bf76b4938f |  | textbox | Foreman – Checklist Completed:
text | d1fdeca0-eaa1-5a8d-b09a-d3b371b223bf |  | textbox | Date / Time:
text | d2009e41-99b1-53ee-a2b3-2f98eab2e744 |  | textbox | Coordinator – Checklist Completed:
text | c4e64cd1-2580-55dc-8057-6ca78fafbadc |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-flat |  |  | checklist | FADX-ITP-008-2 (FTC-05) SITE INSTALLTION - CLADDING | itp |  |  |  | Yes | Site ITP | b397a6d7-cca5-48f1-8861-bed4b54052ac
checkpoint-status |  |  | checkpoint | Multiplex - IFC Drawings Shop Drawings Approval
label | 375dc2e4-6c4c-5cb2-bc5d-8534b49a3c3f |  | note | Responsibility: Multiplex
label | 42a48771-55c5-598d-91b6-863e2cbfd6c6 |  | note | – – – – – – – – –
label | 9b1ac2f3-630a-591b-b466-d18bf4ecd894 |  | note | Acceptance Criteria: Multiplex Sign Off
label | 82d0d0d1-5db8-5fc9-9184-0e7540cb4f53 |  | note | – – – – – – – – –
text | 7db3fb7a-af22-5372-bd7a-e96d2a57a759 |  | textbox | Reference Document AS1562.1-1992
text | 1b9f4d29-1c4e-555a-82cf-7183d1831882 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Material Approval
label | a3ca32ff-d6ad-5c41-9098-cfbc48d55b0f |  | note | Responsibility: Multiplex
label | 2ad41f74-9e3d-5ac4-8cdc-d86ec848ba74 |  | note | – – – – – – – – –
label | b0d84d74-d2f5-5e71-b91f-ea86c01fcb3b |  | note | Acceptance Criteria: Multiplex Sign Off
label | 5ffcd931-5cf4-5f1f-b19e-f82fd74792d6 |  | note | – – – – – – – – –
text | 3b9a6dc3-ee0d-53ce-9dbd-a05be19b048b |  | textbox | Reference Document AS1562.1-1992
text | e41fa686-4e5c-5469-82ac-17f62c0e5fdd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials - check materials meet Aust Stand AS1562.1-1992 and are supplied as ordered and specified for the project
label | 2262002c-4168-5315-aafc-d96c04ab95ee |  | note | Responsibility: Facadex
label | 0246b43e-2645-572e-8fb7-d153169ab1ea |  | note | – – – – – – – – –
label | 77aaccf4-d297-58aa-9003-644689b85104 |  | note | Acceptance Criteria: Facadex sign off - Site Supervisior
label | a177932d-c09e-5da4-8839-c6952480f31a |  | note | – – – – – – – – –
text | 4a75fa36-531d-5ffb-8c2c-96c8b9622192 |  | textbox | Reference Document AS1562.1-1992
text | c96f8371-4a3b-59a0-8aa4-d33f19088f91 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Multiplex - Materials inspection upon delivery and prior to installation
label | 75d6e21b-8588-542f-b3d2-a64dc2634d08 |  | note | Responsibility: Multiplex
label | 7b596a9a-24a6-5e22-9966-d352fa30a225 |  | note | – – – – – – – – –
label | 8b2747ab-71fd-5502-8a22-d0ef77f635fe |  | note | Acceptance Criteria: Multiplex Sign off AS1562.1-1992
label | 79bf3255-45d5-573a-9031-70d59fca297d |  | note | – – – – – – – – –
text | f246091e-d37d-5552-9c12-0252deebe8df |  | textbox | Reference Document AS1562.1-1992
text | 60735879-4169-58e1-88e8-f40dde0616af |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check Structure is level and plumb prior to commencing subframing for wall cladding
label | 9524b9c7-63bc-5c7b-818f-c32a0dc32f2f |  | note | Responsibility: Facadex/MPX
label | 74e66e39-2c89-5f87-9b82-5fc62dd3ce87 |  | note | – – – – – – – – –
label | f1a13bb0-f134-5c80-beac-9fc83f6e1228 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | a89e956f-5906-5a75-a9ab-495a5a3c2489 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 434e3cd0-53f3-52e5-abf5-984563f51355 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 871f8509-3732-5463-9bd6-0cba8fbe1cb3 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | b0ca7f48-f976-52fd-a4fb-0bd7836c1976 |  | note | Expansion & Contraction:
label | a54c81c2-8e5b-5d19-8bd8-582956a98abc |  | note | +/- 3mm @ every 1000mm in length & height
label | 9977885a-32d2-5d09-82c7-4cc130a1470d |  | note | – – – – – – – – –
text | 12d2166e-c7a8-5128-9fa2-2700f3668593 |  | textbox | Reference Document AS1562.1-1992
text | d9a13fbf-14b6-53c7-ba26-f01c8a126c4a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Grid lines established and RL by MPX
label | 10de62b0-d21a-5b66-b826-4f9de2a8880f |  | note | Responsibility: Facadex
label | 8e748471-2120-5f17-a2ed-98aa7c94a094 |  | note | – – – – – – – – –
label | c1030b1c-1ef5-5c7c-a5b2-db4a71e3524f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 0f123567-9b21-5878-955f-884a2e069b84 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ef6ee5d4-83da-5b6e-b165-2751a3d79cf2 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | f540c3f1-39b0-5001-a9c7-dd1786455fb2 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5e6634a7-c085-5f37-9e0d-94ad957b4bbd |  | note | Expansion & Contraction:
label | 91654a4f-f42f-5dc3-b6ef-db9c1506acc0 |  | note | +/- 3mm @ every 1000mm in length & height
label | fde3cd3d-7199-5ca4-8cd6-c7b71b6a0d10 |  | note | – – – – – – – – –
text | a5232d9b-6440-549c-8cef-c1fff5d0a899 |  | textbox | Reference Document AS1562.1-1992
text | 26129f59-0496-5e3f-b967-88cb6f00ecb2 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Site Installation – Installation: SHS framing and Cladding including all capping and flashings Sealing and Cauking
label | 2027faa3-75b2-50e2-aafc-ab30106d4128 |  | note | Responsibility: Facadex/MPX
label | aeeaf1e1-bb26-5445-b45c-3c02a173c7cb |  | note | – – – – – – – – –
label | 9e2e4995-f43f-596d-a712-f11b61b2cb0f |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | b8609cdc-42af-5c25-912a-b5ef31aeb78b |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 2a3ad29b-8465-5c5d-a49d-baec46460396 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 3238d4ba-b63a-55b7-9ef7-f8d3b4e1a351 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 4b0b18fd-d4dd-572b-b41d-68a29845a115 |  | note | Expansion & Contraction:
label | 47377dd8-c21c-51d2-bf28-797274ccddb6 |  | note | +/- 3mm @ every 1000mm in length & height
label | 2001a949-448b-5498-991e-18679c6789fb |  | note | – – – – – – – – –
text | 8e7bf28a-b761-5401-ac45-883b0b3e2531 |  | textbox | Reference Document AS1562.1-1992
text | f7bed550-c060-5c8d-82e7-4656733ee043 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Site Installation – Ensure the internal crash rail and external Grow cable are installed correctly
label | 134c248f-2736-5444-a497-bc4641c18556 |  | note | Responsibility: Facadex/MPX
label | 709803c3-6dc8-5aa0-baf2-2426e13ebabf |  | note | – – – – – – – – –
label | 1015d656-9055-5ade-8df0-3bb0f9be9bc2 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 788c1ff0-057a-57cc-8604-d1ede3a3f3a7 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 01f6c101-fa8c-51d4-8812-896233ea2a24 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | e718c60e-6e6b-5edb-bb5f-c17fcf1ca434 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 5d797ec5-f75a-5672-b6e0-fc4c1e9ea78c |  | note | Expansion & Contraction:
label | feaee893-ab8e-5e2a-8662-7cca3ee5b017 |  | note | +/- 3mm @ every 1000mm in length & height
label | a3f528e7-8f80-5efd-9b7a-643152d5df96 |  | note | – – – – – – – – –
text | 684c500e-4435-5381-af49-636b08eb7934 |  | textbox | Reference Document AS1562.1-1992
text | 9012a517-235f-5637-acfb-4ecca4dfd618 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed wall with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 6f834f74-6fa6-5a9e-8995-5b9f698b95a6 |  | note | Responsibility: Facadex /MPX
label | 114e2e95-8358-5f71-8ab5-f8912cdbe934 |  | note | – – – – – – – – –
label | 556c8d59-28c7-51f1-a3e4-e42f5fd1b22a |  | note | Acceptance Criteria: Defect notification via Teambnder or Builder email
label | eb2c966a-429e-5d1a-ac6f-1952c0eb8a4c |  | note | Evidence of close out / rectification.
label | 2b806cf2-9380-52aa-ae43-d239d9021d89 |  | note | (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type).
label | 6b9f4dff-268f-52cd-8adc-55a0451e224c |  | note | – – – – – – – – –
text | 9928bf78-7a90-5c53-bcc3-06b651c83fcf |  | textbox | Reference Document AS1562.1-1992
text | ec61ee3d-70f5-5daa-8085-b0bb913c9e79 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | d89b27f3-504f-5ba3-bdb9-656dcb803596 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 24abdced-38bb-585e-9c5c-536d049a75d1 |  | textbox | Foreman – Checklist Completed:
text | 96623418-9a82-5076-8999-415ce8fe869d |  | textbox | Date / Time:
text | 8abc786a-1847-505a-ad0e-f29b38a5f540 |  | textbox | Coordinator – Checklist Completed:
text | 76a9a240-b5c4-59dc-ace1-25efc7d609c3 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-506 Cladding ITP | itp |  |  |  | Yes | CLG-506 Cladding ITP | de399ecb-aee7-452f-8bfe-df88497160f6
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 5f6f4285-f19c-5011-865e-dd9e044d5f6a |  | note | Responsibility: MPX
label | 98375baf-1005-5401-9a1e-a3e7eb8bc2e7 |  | note | – – – – – – – – –
label | e7c86bea-4afc-530b-a37a-93f276d7dd2f |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | f70b0eef-4b8f-5c85-b5db-e6c247e9b0da |  | note | – – – – – – – – –
text | b5250417-424e-5a7c-9447-520d883cb7df |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ccae36cc-4050-5c30-896f-01c0f9c1af38 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 2cc762cc-dc69-5dd5-9895-ba07b5e1d63c |  | note | Responsibility: MPX
label | 94c93a6a-af68-5e0f-b4a5-3e7a7ea62cba |  | note | – – – – – – – – –
label | 3739a6d1-e6e3-5449-87cb-1f74adcdce96 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 1d887525-1261-5882-93d4-b45c2464b4d3 |  | note | – – – – – – – – –
text | 23a69d7d-a03a-5251-bb52-e3d7084ddd51 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fcda84b1-fad0-5835-b5e1-20e96b73fc06 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | cb9d9f9d-9f64-5905-943d-95635b276926 |  | note | Responsibility: Facadex
label | 267ba891-555c-5e12-a8c9-0c2a10471ad2 |  | note | – – – – – – – – –
label | 30b6eaa1-d18a-59a5-b853-aac63d6e9ca1 |  | note | Acceptance Criteria: Facadex sign off.
label | 5d144fe3-619f-5ede-ab4a-f4c0512a444c |  | note | – – – – – – – – –
text | e913cd93-4d78-5f7d-a168-156b7ffb7fd9 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 3c4602c1-cfed-55e9-af73-b5d4df443498 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | d248b3ba-4fd1-5ec2-89a1-2e32a006e6cc |  | note | Responsibility: Facadex
label | a15aa5bb-c99b-5076-b8d9-c2cf8ffdb2de |  | note | – – – – – – – – –
label | 5ca814a9-292f-5bb1-8d6a-d62bd09db0ae |  | note | Acceptance Criteria: Facadex sign off.
label | 5a645ef8-65b7-53c6-86ef-f130c2d3ad58 |  | note | – – – – – – – – –
text | 1ea372fe-6e60-53c6-b912-97fb304b425f |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c5f3a40f-4c66-5db2-8bc3-57d019c68635 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 5940f548-fb36-56fe-9512-a36d77390075 |  | note | Responsibility: Facadex
label | efddc738-0853-51e8-a4e7-20c2db8a7eb9 |  | note | – – – – – – – – –
label | 75f7d676-3bfa-5f1c-aaa9-aeb0f4a4ae67 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | e85d038e-8bae-5476-832c-6a162e9b98c6 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 2aa745a3-5b5a-5871-9df0-775c1afbf92c |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 04a1623c-bfae-5956-8094-be39716eb220 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 279aac89-6815-5ae6-be87-3ebe33b15bfd |  | note | ○ Expansion & Contraction:
label | 6fb721ee-423d-5b8e-9370-25f85512c815 |  | note | +/- 3mm @ every 1000mm in length & height
label | 1e1a6156-1e2b-527e-8044-ed680e8fc21b |  | note | – – – – – – – – –
text | 121afddb-5b20-5b02-a6a4-5b9e26edde44 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dfc4c476-06e1-52c1-ae37-51cc86d209d2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | a781b6b6-5ac9-5463-94ad-6d740e34c850 |  | note | Responsibility: Facadex
label | 5e6d4e24-fc43-549f-88be-bc7eeb7eaafc |  | note | – – – – – – – – –
label | 842b0910-b149-5518-8100-e0859cf6dcf9 |  | note | Acceptance Criteria: Facadex sign off.
label | a6c855dc-9354-5906-a8d7-fa568c71cad3 |  | note | – – – – – – – – –
text | 273677db-9ca9-5e09-b960-ab2eabd44ccc |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 99eae1c0-4bb9-516b-a0b8-6dc89073788e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 61f16030-ea70-5484-982f-d83f9338e487 |  | note | Responsibility: Facadex
label | 3a0c0a63-a4ca-597c-866f-e329997ec265 |  | note | – – – – – – – – –
label | 75fbf5d8-f8a8-5bfa-8b8d-04d28e7798bc |  | note | Acceptance Criteria: Facadex sign off.
label | cc47b8a9-093c-5813-84c8-10e27284a3d5 |  | note | – – – – – – – – –
text | b0dfe4a6-83af-5d82-a71b-961009526c78 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 0116b09c-b15e-5677-8a08-4cb1a803b0ed |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c29c0bef-7c21-546a-bfb1-8b3e0efff759 |  | note | Responsibility: Facadex / Builder
label | 1733e048-404c-5578-b489-f4705e1bd06b |  | note | – – – – – – – – –
label | faf83cda-6852-5b98-8842-baf4553b4e05 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 06211ab2-08a1-5277-88f2-fd61bdf2c30b |  | note | ○ Evidence of close out / rectification
label | f53411b8-3cd4-5bdb-95cb-e5e09b753a4a |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 9f5ad69e-4544-5408-b9c9-510a36fb89ca |  | note | ○ Sign off only once agreed that wall is defect free
label | 1b8ab8b7-5bd4-58bf-8b07-0000795bc201 |  | note | – – – – – – – – –
text | 130f0521-930d-5dfc-b7dd-771fd6e23e76 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 07f556d5-762e-5f08-8ad4-c605dbcc9cb3 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 9dcfeaa4-90f6-59b2-8e5c-e26def4dce4e |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | de0a336c-d0cd-52e5-8b80-5bb75845aebd |  | textbox | Foreman – Checklist Completed:
text | 97fa2ca8-7f28-5e47-9285-8c129fdc38b2 |  | textbox | Date / Time:
text | be0ab724-3589-5fad-97a0-7425526bd1a4 |  | textbox | Coordinator – Checklist Completed:
text | 5922c136-2de2-57bc-a1b2-9e99e51eb966 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D Panel Site ITP | e16e4de4-78d5-44c8-84c1-c9fbaf306d36
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | b4150456-3ed5-5a63-9302-093e557fb2c6 |  | note | Responsibility: MPX
label | fc7cc962-8490-579a-b824-a932693c5176 |  | note | – – – – – – – – –
label | 0f8d0e20-a622-52cf-a570-c49bf4541794 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | f2137cfb-2740-5bd0-ad7f-1388a7cd7072 |  | note | – – – – – – – – –
text | 908ac15b-171b-5090-bc20-c3765925d1ab |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 93103c55-93fe-57b7-acd5-893e38265eb2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 1d13cd05-8366-57e1-85ac-f6e3faf8f3de |  | note | Responsibility: MPX
label | 05c641fd-9bfa-53b8-a12d-88af255132cd |  | note | – – – – – – – – –
label | e96917ec-885d-5531-b44f-e576591fa3e4 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 064cffd5-763c-5b0f-874e-6530be9535be |  | note | – – – – – – – – –
text | f8cb318a-f91a-52de-9c92-cce7bc6c5a4b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dc980dd7-28b3-5997-a68c-84064a35f252 |  | textbox | Date:
label | 0c708364-5e77-5654-b016-ec14f3bc9143 |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 9a4559fe-c27d-5e6c-b529-2ad8b0b1284f |  | note | Responsibility: Facadex
label | 30b73aac-441a-5f17-91bf-190ba73b05fc |  | note | – – – – – – – – –
label | 79d7692e-d52b-5586-970c-829465f44c22 |  | note | Acceptance Criteria: Facadex sign off.
label | 5badd85b-66be-572f-8b64-fab771380241 |  | note | – – – – – – – – –
text | 379b68df-ce6c-59f7-aaab-73ff680968c8 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | ea08a7e0-aca9-53b6-bb5e-f655328039e5 |  | textbox | Date:
label | d4642ac5-7989-5407-8221-62947d5fa91b |  | note | Comments: Check colour is correct as per shop drawings
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | af4d51de-b144-567c-b02d-4465158ba38c |  | note | Responsibility: Facadex
label | cbced650-d5fe-5b82-8245-999bb4620fa6 |  | note | – – – – – – – – –
label | ec14dd7d-d5cb-567d-9175-0a59aeb65d3f |  | note | Acceptance Criteria: Facadex sign off.
label | 77fab674-ae76-54d8-96be-bb14db4c28b9 |  | note | – – – – – – – – –
text | c14d3fdd-b671-59a1-9585-9b6696b4e160 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | fead856f-2531-5021-b3a8-730c881e8d45 |  | textbox | Date:
label | 05487ae0-1ee8-57cf-baff-b256a89b95d5 |  | note | Comments: If installed off site no gridline available
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | 13b52dd0-3403-5fdc-abf2-a86f3b2f5981 |  | note | Responsibility: Facadex
label | 185a39fa-afdf-5bd0-8d8f-8096e339fc37 |  | note | – – – – – – – – –
label | fb36864a-0181-58f8-b5bd-e418bad7a426 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 2c0f6635-000f-5918-aa60-cc75599aac27 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | 60a95d28-2d3b-51dd-b3f8-be6bc6adcf8b |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | a6637f52-3e27-59ac-8960-84cf1cb3ad7d |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 48b2f667-8bfe-54c0-9513-a64ac3debef3 |  | note | ○ Expansion & Contraction:
label | 4ba2c230-7f64-5990-9f3d-6b2b900842e8 |  | note | +/- 3mm @ every 1000mm in length & height
label | 857e50c8-becf-54e6-a73b-5483859da822 |  | note | – – – – – – – – –
text | 2da06415-a650-545e-9925-d5c54c354d62 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | f5e3113d-3524-5616-b969-2e3d8b5aa429 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | 877ce7c9-9b85-54f3-bd2f-b5045cfddbe3 |  | note | Responsibility: Facadex
label | 4c39de45-6cac-5aac-b906-790f8a849a27 |  | note | – – – – – – – – –
label | 46f28669-8595-5b0d-b092-eff38025e617 |  | note | Acceptance Criteria: Facadex sign off.
label | dec237a6-b184-54a4-9114-7e21e716786b |  | note | – – – – – – – – –
text | 67411235-ec7a-50fa-a8f0-d3b0ee0fe256 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | e975ebbe-3397-5075-b6b4-531e3c92950e |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 0.55mm colorbond flashing has been installed to the gap to the strcutrue
label | 1c739fd9-0a7f-5774-b819-67847da6b8d2 |  | note | Responsibility: Facadex
label | 07a55766-475f-5716-a8d7-10c7a475fb92 |  | note | – – – – – – – – –
label | 8d638472-63c1-5188-9e32-e0f05d6ba2de |  | note | Acceptance Criteria: Facadex sign off.
label | 0bd30aac-06ee-5c50-9da7-d24f89e27cc7 |  | note | – – – – – – – – –
text | 1c8acdf0-6f6f-5507-a402-ac8dfd5b6ce5 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 37f7b321-7251-564f-8184-4500919a3752 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | aeec4294-e64e-5573-be90-146a3bf2bdb6 |  | note | Responsibility: Facadex
label | 6f231f8a-c613-5ffa-8e42-4690d548b86d |  | note | – – – – – – – – –
label | d5c60fd6-e8fd-52dd-b60a-29dfefcabf40 |  | note | Acceptance Criteria: Facadex sign off.
label | 26591fca-4c8e-5dfb-9d8d-755153d07bd9 |  | note | – – – – – – – – –
text | 5224dda1-eb01-56c8-bd29-4fe26406463c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 2483ed47-8b24-54b7-803a-d5387c54127b |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 556e6aa5-2927-54e5-b2ad-1f2971cbac14 |  | note | Responsibility: Facadex / Builder
label | 0b00aa0b-f33f-5ee4-86cd-71986fa89ac9 |  | note | – – – – – – – – –
label | fbb1cc6a-f5af-5a7b-8854-eae02c9a887d |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | c7319a63-1a51-5ae8-aaf4-b7dc07cc0636 |  | note | ○ Evidence of close out / rectification
label | 9f721e35-db67-5f46-bd4b-cf062c7654d1 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | 0d09b1db-102e-511a-8a23-f50147aef28b |  | note | ○ Sign off only once agreed that wall is defect free
label | 94df5da6-c327-53e0-a5ec-67831a741395 |  | note | – – – – – – – – –
text | 49cc48d6-7656-534c-be3d-a938ce217e0c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 41e84972-a26e-5b09-b093-ffa372592ff2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 461f9585-463d-5154-a2b4-7a7e7b799844 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | a17649d0-1d94-5f4c-bc0b-47052ad71f42 |  | textbox | Foreman – Checklist Completed:
text | 058bae9f-fe88-5ee7-b3e5-8154390916d7 |  | textbox | Date / Time:
text | 242cc59b-af70-5daa-a3db-bbb02fd52363 |  | textbox | Coordinator – Checklist Completed:
text | 60df72ae-1d78-53d1-815d-ef52df4ebf78 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP | itp |  |  |  | Yes | CLD-214 Lysaght Spandek - Cladding Building D (North Wall Double 50 Top Hat) ITP | e8f11401-8638-4bf2-8848-a391884ddbb4
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | 5837d270-3395-50e6-8eae-3e716d83e28b |  | note | Responsibility: MPX
label | a6200d96-52d9-56f3-8db7-6c735318aa8f |  | note | – – – – – – – – –
label | 2bcaea4b-8735-558d-8577-633930f11f5e |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | c1eda768-a23f-5f6b-8c71-6ad56a2f1c2a |  | note | – – – – – – – – –
text | 523c5b71-39c0-501e-a6e5-e4b978458e9c |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 8f2ce768-f128-5759-b170-7ba78d443d1f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | 60eea480-c8e6-59e8-8cc6-e786070bdf93 |  | note | Responsibility: MPX
label | 61c99aac-8848-53af-9678-133da49858db |  | note | – – – – – – – – –
label | 17ca968e-c506-5cac-9c3e-fa41f7a5c07c |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | c2178b19-1790-5077-a10e-77a0b49bf1c2 |  | note | – – – – – – – – –
text | adffc657-d3e3-5d34-9300-afbb39448de9 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | a706c50d-5ff9-5f71-8258-cb8c4e212f2f |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | 220fbf5d-db26-57d5-85f2-065cef0770d9 |  | note | Responsibility: Facadex
label | 34c78161-b60e-5232-881e-eab917571a88 |  | note | – – – – – – – – –
label | d95f2e25-f245-54d1-8ac1-fca49f147d96 |  | note | Acceptance Criteria: Facadex sign off.
label | e4c55a17-270d-5128-8700-bf0c12fb6a07 |  | note | – – – – – – – – –
text | 09a20709-54e0-51c6-a357-9f57b7a357af |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | b192a2f0-6109-5845-83f6-b0784073e60b |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | 0a0b7dee-4b9b-5eca-89f9-39d55ef31385 |  | note | Responsibility: Facadex
label | 88127bfd-4d5c-5f46-a128-c19e468c1aed |  | note | – – – – – – – – –
label | 5670b3d7-e1b4-513f-994b-af872576b1f4 |  | note | Acceptance Criteria: Facadex sign off.
label | ef3ad88d-204b-5f07-9d37-b60a2c6b285f |  | note | – – – – – – – – –
text | 4c9b9369-f0ef-570a-9a34-63c5b9d7bdfb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 08b09617-9055-5028-98ef-266b4c6406d4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm vertical top hat has been set out and installed to steel frames with #12 tek screws@500 crs
label | 39eaf64b-247e-5a65-bd7e-c5679eeaf8a4 |  | note | Responsibility: Facadex
label | 455d9b88-b7b9-546d-907c-3df986a82500 |  | note | – – – – – – – – –
label | 1b4f5cbf-9a83-5322-b2ad-3ba120318af1 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 8ad9164c-d115-5601-9fa3-02480ebff8c9 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | e433c447-9d6d-5463-a897-c33a5408f388 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 4a74ea4f-1aee-57d9-b06f-d4f5f2d32543 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 6a8c5213-68ce-5443-bd8d-e6a819bd80f4 |  | note | ○ Expansion & Contraction:
label | bcb9f650-bfec-5b2d-afbe-b9a5fb710969 |  | note | +/- 3mm @ every 1000mm in length & height
label | 616843eb-c541-54ef-8cfb-bdcb596b92c8 |  | note | – – – – – – – – –
text | 027e10cb-3d48-509c-9435-e68952d1f666 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 667d9249-d77e-5b1a-aac6-f881c487e038 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | 50mm horizontal top hat has been set out and installed to vertical top hat with #12 tek screws@500crs
label | afa1f4ed-b7e9-5c27-a067-ce1ed2c4edc1 |  | note | Responsibility: Facadex
label | ba7be4fe-48ef-5a2e-bd96-c50780d9970a |  | note | – – – – – – – – –
label | e02af6ab-8370-5da2-9c6e-c3a39dbdd6ef |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 3cd857c3-5d5e-5b34-b25f-43fc20a2b14f |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | b37b7ad5-c894-5505-865c-3a3aef6c5ac4 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 6764c146-1241-578d-84c0-2eb8501ef4af |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | 7b506317-f4ca-5b4e-987f-67e05717245c |  | note | ○ Expansion & Contraction:
label | 181541a4-db6d-5e5c-9b59-adf2f1708a4f |  | note | +/- 3mm @ every 1000mm in length & height
label | 5621de11-66ec-5654-a8e3-fe5383c50605 |  | note | – – – – – – – – –
text | 01725c67-c7f5-55d5-b450-37273cf9622a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 6ad38011-eec9-5066-a16c-820b9dd15867 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Packers has been used to ensure the top hat frame is plumb for lysaght spandek panels to be cladded on.
label | 8a59bb72-ed65-5761-b30d-4f28f0e93a29 |  | note | Responsibility: Facadex
label | 38e3b736-b8ef-5b16-9781-d686cda881cd |  | note | – – – – – – – – –
label | e74f6555-3f16-589c-8a92-17a9d238f340 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | d7d6b560-4c2e-50a1-aadc-d040e6e35688 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | e5c42b63-0582-5c4f-9255-459115e97d7f |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | bdd76b05-91ac-5daa-93b4-0fa37b0f0a66 |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | fb59c45f-227a-5ede-9830-c5abf08292f3 |  | note | ○ Expansion & Contraction:
label | 870f65eb-2d84-53e3-84b8-488ef6fe419c |  | note | +/- 3mm @ every 1000mm in length & height
label | aa0ef785-69fc-5668-9039-045e9a366654 |  | note | – – – – – – – – –
text | ff822f31-af11-5ecb-b85a-bc0e289be9bb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | cd9a947d-3984-59b8-b297-5d6b27c51300 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 5f3c1911-f6f5-5fae-9130-b673db78debd |  | note | Responsibility: Facadex
label | ce6c873e-d0e2-5207-b5e9-277f2f5daddf |  | note | – – – – – – – – –
label | 3d1e071a-d39c-5279-a44d-f6b5d45ee2a4 |  | note | Acceptance Criteria: Facadex sign off.
label | 3d8710b9-ebb8-5195-8ee4-cbc27e3ca433 |  | note | – – – – – – – – –
text | 9e58e814-4fb2-5847-836e-2f5ab0446b57 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | c32609bc-3bbd-5ca7-bc8c-905e6edb4af4 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | 39d0b46a-bc8a-54fe-8f67-81ff538b69eb |  | note | Responsibility: Facadex / Builder
label | f1bec923-7f70-5c93-8f00-d571f5c23e57 |  | note | – – – – – – – – –
label | b523639e-c932-5d49-9ed5-5d81810a9b8c |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | eecd0be0-6299-570a-bb6e-4c5d5526c1d9 |  | note | ○ Evidence of close out / rectification
label | 3d614c97-47ff-56a8-9b42-351ce1a16431 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e4e9d3b1-993f-5bc7-a308-f4943f977794 |  | note | ○ Sign off only once agreed that wall is defect free
label | 7f2ec965-2f75-5c7d-8a0a-dca33758e632 |  | note | – – – – – – – – –
text | 847d4fe4-62b6-514d-849f-28c5a1319fae |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 1b18296f-3c51-5bd6-a41f-abe6b1fd15cd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | c25bddeb-8e48-594a-9f33-0c25f2686120 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | d2566bf7-8700-53b6-a987-255a57536e63 |  | textbox | Foreman – Checklist Completed:
text | bf69485e-df8f-5773-9423-5cb861bef633 |  | textbox | Date / Time:
text | e328b04f-0668-5a6b-8df3-979622f23a79 |  | textbox | Coordinator – Checklist Completed:
text | 01393da7-b237-51e6-9600-49bf29120849 |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Cladding Panel ITP | itp |  |  |  | Yes | CLG-514 Cladding Panel ITP | f1d10fed-f60d-466e-af9a-736da54a6f20
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC Shop Drawings Approved
label | fbe4df89-8d53-5c29-93a6-7467672400f9 |  | note | Responsibility: MPX
label | 01a05e89-803d-5848-a6bc-6cb08a941684 |  | note | – – – – – – – – –
label | 887dd132-f8ba-525c-894f-fbfd516ae3c8 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | b7464148-1c64-513a-8e63-92d0fe26e1ef |  | note | – – – – – – – – –
text | 118ba8fc-d8af-5043-b5ea-50978f405789 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 685fec29-64c1-5ee7-80c2-6c5922ccfbcd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | dc123a4a-bac7-5f15-9172-825406bc6eee |  | note | Responsibility: MPX
label | 5b46eac3-e6bc-5ad5-bdaf-28eac94458be |  | note | – – – – – – – – –
label | cc3cfce8-3853-5a75-9992-53f386004f84 |  | note | Acceptance Criteria: MPX / Architect Sign Off
label | 7d7a8b0f-25f0-5fcc-8c87-2f6cefd1d436 |  | note | – – – – – – – – –
text | ac14f261-53a1-5546-992e-3eb6e50133ba |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | bf35d39d-310c-5300-a043-bec61a21c020 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | 3bc2fcba-df67-5b91-b87c-7a21afa1362b |  | note | Responsibility: Facadex
label | d0f70131-e2cc-53b3-80d9-b516d47f1fd7 |  | note | – – – – – – – – –
label | f6c4c312-d3dc-5b7a-84df-1da894b7e261 |  | note | Acceptance Criteria: Facadex sign off.
label | 4a90a6b8-906f-5e0e-84ab-401558bae593 |  | note | – – – – – – – – –
text | 7d08682b-f0d7-5861-b290-aec15c3e7703 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | f4e0a783-9516-5762-b2b2-189f27c6ec54 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Grid lines established and site set out complete
label | c91aedcb-0e85-5a66-a1ef-0e1f4243e9ec |  | note | Responsibility: Facadex
label | 007b77a6-3d07-5d61-9fb4-e00f7750fc5a |  | note | – – – – – – – – –
label | 7d54c103-2550-54b1-8e24-5bf6f5c9386b |  | note | Acceptance Criteria: Facadex sign off.
label | 7e885d1b-4928-50dc-91b5-7bc13314b54b |  | note | – – – – – – – – –
text | b98c93cd-aa0e-52dc-8927-a2242335d6c3 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7d7cf7b9-ec14-59bd-9562-2b4be7021a65 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels installed to manufacturers specifications
label | de87f544-baa2-56aa-ab4a-7caedf924e35 |  | note | Responsibility: Facadex
label | 2d17f104-bd65-5151-a540-59c61f128d90 |  | note | – – – – – – – – –
label | 91b0771f-7f8f-529b-a1de-ea42be823621 |  | note | Acceptance Criteria: Standard Cladding Tolerance:
label | 4edc45f5-6df7-5fd6-afbf-66d26781bba4 |  | note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | fe2079ef-4225-5a42-922c-5edb78d615b2 |  | note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | 76424888-1788-5b9f-a2ae-b0781db1ab8b |  | note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
label | b5d69799-2ad4-5394-b982-6f1ed9230f63 |  | note | ○ Expansion & Contraction:
label | 9f32c86e-b40e-535c-b44a-890cc100e049 |  | note | +/- 3mm @ every 1000mm in length & height
label | c525990a-e8a0-556f-a620-0f59551351e9 |  | note | – – – – – – – – –
text | c6d7801e-d61f-5e70-9689-761e4d8afd95 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 9d25b892-1f09-5a2b-96ec-081e93b947b2 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Cladding Panels checked for paint scratches post installation
label | 64d89e3b-2dbe-557a-88e5-f8546ab6d5a3 |  | note | Responsibility: Facadex
label | e1b242c2-cf49-5c03-a005-21945ff03463 |  | note | – – – – – – – – –
label | 854f67d5-b288-5cf9-8344-06e0be039132 |  | note | Acceptance Criteria: Facadex sign off.
label | 516ed053-a3f7-5d24-91df-7297f6b83ad2 |  | note | – – – – – – – – –
text | 06bba872-8594-5670-a12a-1b624936f856 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d1ffa5f8-8d18-5c06-b0dc-59df751fb432 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Connections (bolts/washers/screws) checked for damages
label | 4fce2f7b-3bbf-55fc-ad84-3d539e4ab26b |  | note | Responsibility: Facadex
label | 43cc3701-c383-556f-bc3f-ac1757ab0c00 |  | note | – – – – – – – – –
label | 42f94883-77ac-5b5a-9ac3-6e9a6b62dc41 |  | note | Acceptance Criteria: Facadex sign off.
label | ce1f1d29-eab8-5ec2-a773-d20d483a0f96 |  | note | – – – – – – – – –
text | ff712268-6f13-5581-9c0f-11010538ee7a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 47ac07d5-fbb9-5722-8d4a-7bedabe85497 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | c2d8a077-8733-5ed9-b096-327d1d360087 |  | note | Responsibility: Facadex / Builder
label | 0943f684-7fe3-5d23-bade-0b913ab2b922 |  | note | – – – – – – – – –
label | ac17b521-cf41-5b41-b796-a1174befa54e |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | 1ee5967b-edd5-5803-a9f4-ea3f95eb8e11 |  | note | ○ Evidence of close out / rectification
label | b8d8562b-aaed-531b-b759-332cf5e013ad |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | fb988245-3462-5219-85f5-901f17800ec8 |  | note | ○ Sign off only once agreed that wall is defect free
label | 26e4c2f7-34fd-5573-8936-cc99b7bb0ab7 |  | note | – – – – – – – – –
text | 0e517345-2091-5893-8a73-4780ea54254e |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5dfebb07-b2d8-5d2e-a624-d986d5e1000d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | 84473391-6ff2-5a23-ba6d-2aaad0f15c9f |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 4efcc13d-b4ae-5061-8514-4a3ba188b14d |  | textbox | Foreman – Checklist Completed:
text | 38b1ed22-b454-56a6-bfd0-c178b1455377 |  | textbox | Date / Time:
text | 39b55d60-d11b-5db0-9b45-a89aa05e4114 |  | textbox | Coordinator – Checklist Completed:
text | 26f4bfd8-d07b-55d9-80e0-d214e659fd9b |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed
checklist-sectioned |  |  | checklist | CLG-514 Bridge Factory ITP | itp |  |  |  | Yes | CLG-514 Bridge Factory ITP | fdf1bd05-918e-4474-94a3-a65c6b38a6ed
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | IFC shop drawings approved for fabrication
label | 3472d786-3577-5339-893e-00d264086464 |  | note | Responsibility: MPX
label | 52e8877a-7a94-5368-9280-9c96b35cf427 |  | note | – – – – – – – – –
label | 5c225f3d-0a70-5371-a353-81b5f7cf7841 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 55065371-5271-562a-be35-192a667fa702 |  | note | – – – – – – – – –
text | 97727bcf-286d-531f-96fc-0ab574f135da |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 83472bb3-50af-5768-a2c8-69f0f1c65103 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Material Approval
label | b5186b0a-1ce0-5d47-941c-a6039bb48f80 |  | note | Responsibility: MPX
label | fe82d1b2-ac63-5a27-9318-edb2973ebd61 |  | note | – – – – – – – – –
label | e074db5b-9cf7-5624-a05b-5e5c03070ea8 |  | note | Acceptance Criteria: MPX / Architect sign off
label | 2a8336f5-8148-58bf-bd85-3553f483ab18 |  | note | – – – – – – – – –
text | 68bdba1c-79b0-55d4-9585-2acc6d21a22b |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | afee839d-cb9c-5919-9969-dedb9cf5d080 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Confirm and check finish as per approved IFC drawings
label | e32315e8-125a-5244-8f93-09e0908a7245 |  | note | Responsibility: Facadex
label | c900e971-7434-58ff-8d39-ec5753cadd4c |  | note | – – – – – – – – –
label | 0930aed9-4b0b-5f75-876e-3077704b9558 |  | note | Acceptance Criteria: Facadex sign off.
label | 18afb700-892f-5632-952d-ff054c733c32 |  | note | – – – – – – – – –
text | 216fee86-3f93-5202-b8a0-f73237e72a90 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | d86e04e1-353a-509c-8556-24a514bd3574 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check panel size and dimensions against IFC drawings
label | 4576243d-aa3e-5164-b411-5f917ff46f9e |  | note | Responsibility: Facadex
label | c010f2fa-29e9-5535-93fb-41d82884745c |  | note | – – – – – – – – –
label | b91f5714-4c8a-5dfb-9e7f-497d5c728cd1 |  | note | Acceptance Criteria: Facadex sign off.
label | 1d719952-714a-5683-8d8a-a765e81ba49d |  | note | – – – – – – – – –
text | f75a716a-76fa-5fb2-bca4-5bb7d4dc1662 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 7f2b62b7-cd7f-5127-96e7-8c9cb03b6d67 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | abc549ad-b369-50b2-a1c8-b704ac8421ea |  | note | Responsibility: Facadex
label | ba993840-e52f-5521-8253-a881be337c5d |  | note | – – – – – – – – –
label | 3515fff1-f180-58f4-8866-a49e3f20f435 |  | note | Acceptance Criteria: Facadex sign off.
label | 2f8d1ba2-06df-519e-8dbb-90688ff42aec |  | note | – – – – – – – – –
text | f2c8fad0-733a-5fed-aafa-dd9f39515429 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 06558924-62c3-599e-9650-dcdad531a9c6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | QA has checked delivery docket and receipt from powder coater
label | dd19dfba-85a1-5f84-b29b-fab7ba6e3811 |  | note | Responsibility: Facadex
label | a595deb6-5a83-5275-b579-aefe3d39e0e0 |  | note | – – – – – – – – –
label | d088346c-623f-5147-9d12-f7b5e657e6aa |  | note | Acceptance Criteria: Facadex sign off.
label | aa72cd7d-d3a3-5c5a-b11a-b6638f9b8e45 |  | note | – – – – – – – – –
text | 9a591110-f7d1-58ad-a69d-483286c55ef7 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 21796ba6-e575-5cc4-b365-ddf89420d06d |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Is fabricated item labelled as per drawing?
label | 0083a231-1587-5614-80be-97a5d4fe5a37 |  | note | Responsibility: Facadex
label | f8121108-f7c7-51f9-ad3c-97fe6edee3be |  | note | – – – – – – – – –
label | 21fe6a80-a6de-59e9-8fac-544d0f417a04 |  | note | Acceptance Criteria: Facadex sign off.
label | 2eeccd4f-a8ec-5ee3-9b7a-4af8826e9cc3 |  | note | – – – – – – – – –
text | 853098a6-c5be-5519-bcc7-9d0d2231ea2a |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 4e8a4b00-f091-5814-b93b-4f64d89c38f4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Fabrication complete
label | 6efe71d3-420a-5ae2-ada3-60ef9b1b8385 |  | note | Responsibility: Facadex
label | 181a4dad-d213-5541-ba02-6e393b21ccbe |  | note | – – – – – – – – –
label | d8396307-1bbe-51d3-988d-1bf566166af0 |  | note | Acceptance Criteria: Facadex sign off.
label | 698c3664-22fd-592c-a4e1-3b9be2854f85 |  | note | – – – – – – – – –
text | 8e088db0-2d33-5eeb-a207-9bf788d22d75 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 5f2b8c56-9e86-5995-9c03-f9c04536df3a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Prevent direct contanct between incompatible materials
label | bfc817d2-c9ed-5e3f-bb57-6d4f4b148ad7 |  | note | Responsibility: Facadex
label | 3e2675cd-327d-5384-a2b4-f648df7e983d |  | note | – – – – – – – – –
label | 2d6ad526-9161-5908-912e-a05210dc1d94 |  | note | Acceptance Criteria: Facadex sign off.
label | d4075b0d-1191-52e5-b750-46dc45e6c218 |  | note | – – – – – – – – –
text | ecffe366-095a-5c03-9742-ce0c0d9feead |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 867286b3-f8a2-5c6c-a518-473f39fe533a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Materials ready to deliver on site
label | d0e11353-d060-57e3-bb8a-0bd8fc9ef84b |  | note | Responsibility: Facadex
label | 974f4781-c7cb-5505-82e3-3b5235615711 |  | note | – – – – – – – – –
label | 57b26c75-4c8f-5e86-8bcc-b603e226eb9a |  | note | Acceptance Criteria: Facadex sign off.
label | 7dee31e7-8e35-5ba3-808a-0cc7f33b2b1c |  | note | – – – – – – – – –
text | 68955439-61d1-54e5-94b3-ab080b443087 |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | 924e8b2d-fb1a-5d80-8895-5658f9bd0ea1 |  | textbox | Date:
holdpoint |  |  | signoff | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint-status |  |  | checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | dd4252fa-a12b-5c93-877a-9356ffde3132 |  | note | Responsibility: Facadex / Builder
label | 7a419d16-8286-5c9f-ba8b-bb2e348847a4 |  | note | – – – – – – – – –
label | 6e01c34a-d655-5735-80a5-0bfc986c1df5 |  | note | Acceptance Criteria: Defect notification via email or chosen correspondance
label | ef9264ee-c3ac-512d-91c1-2e3a9296be4a |  | note | ○ Evidence of close out / rectification
label | c555d2e1-8d27-58aa-a9de-bde35bf71544 |  | note | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | e25b5ede-4678-57cf-a85c-71a440e94d38 |  | note | ○ Sign off only once agreed that wall is defect free
label | 4c304724-7c51-516f-8611-51ff66c429d7 |  | note | – – – – – – – – –
text | 6aa057a6-7cdf-531f-ac4d-97383e89bebb |  | textbox | Reference Document / IFC Shop Drawing Number AS1562.1-2018:
text | dbdaea4d-42c4-55ce-a69e-458bd50a4ba6 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | AUTHORITY TO PROCEED
label | d431e8d1-5ea1-535f-9f9a-73256256b245 |  | note | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
text | 0874111d-0197-52d3-a070-07efa067cbed |  | textbox | Foreman – Checklist Completed:
text | 79470d1f-4f68-5c94-bc57-22f0ba418feb |  | textbox | Date / Time:
text | 68f300b9-4dec-58c7-b5af-3ce4a88573b6 |  | textbox | Coordinator – Checklist Completed:
text | 57c88e2a-a3b4-5dc2-9001-06709efcbffc |  | textbox | Date / Time:
holdpoint |  |  | signoff | Checklist Completed