## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CLD-100 Lysaght Interlocking - Cladding Building D Panel Site ITP | itp |  |  |  |  | CLD-100 Lysaght Interlocking - Cladding Building D Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 0.8 BMT Raw interlocking sheet has been cut and installed in situ to the size required by site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-100 Lysaght Interlocking - Cladding Building E Panel Site ITP | itp |  |  |  |  | CLD-100 Lysaght Interlocking - Cladding Building E Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 0.8 BMT Raw interlocking sheet has been cut and installed in situ to the size required by site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building A) - Panel Site ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building A) - Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Module (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | 250x50x6mm Alum angles spanning at the back of the module has been secured and fastened to the L brackets for haning the module.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | ensure the 40x40x3mm SHS horizontal rail 450crs fixed to the C channels at the back of the module
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | ensure the Subsill has been installed with the support 250x100x3mm alum angles at the bottom.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | bottom Shelfangles chemset fix to concrete slab has been installed for the module to be sit on where ther is a louvre behind.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 0.48BMT colourbond flashing has been installed for the weather proof to IFC
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Perf with CW frame Panels checked for paint scratches and dents post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Perf Cladding Panels installed to IFC specification
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (screws/rivets) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building D) - Factory ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building D) - Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check if the stiffeners has been installed @450mm Crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building D) - Panel Site ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building D) - Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Perf Cladding Panels installed to IFC specification
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Perf Cladding Panels checked for paint scratches and dents post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Perf panel fixed with 4.8mm diameter x 11.4mm Rivets @300crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (screws/rivets) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building D) - Subframing Site ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building D) - Subframing Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 75x254x75x3mm thk folded Z has been set out and installed to steel purling @1500 crs and fixings @900crs as per IFC
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | 50x50x3mm alum SHS/EA horizontal has been set out and installed to vertical folded Z with #12 tek screws@600crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Packers has been used to ensure the subframe is plumb for perf panels to be cladded on.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building E) - Factory ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building E) - Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check if the stiffeners has been installed @450mm Crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building E) - Panel Site ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building E) - Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Perf Cladding Panels installed to IFC specification
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Perf Cladding Panels checked for paint scratches and dents post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Perf panel fixed with 4.8mm diameter x 11.4mm Rivets @300crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (screws/rivets) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf (Building E) - Subframing Site ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf (Building E) - Subframing Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 75x254x75x3mm thk folded Z has been set out and installed to steel purling @1500 crs and fixings @900crs as per IFC
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | 50x50x3mm alum SHS/EA horizontal has been set out and installed to vertical folded Z with #12 tek screws@600crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Packers has been used to ensure the subframe is plumb for perf panels to be cladded on.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf CW Frame Panel (Building A) - Factory ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf CW Frame Panel (Building A) - Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Check if the pattern is correct to IFC (5005-H34 alloy 51% open area)
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check carpral extruded profile are jointed with mullion to manufacture's spec (carpral)
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check 2mm alum is installed to the carpal panel (back of the perf stiffeners), and 2mm alum installed to be back of the carpal utilized panel and insulation to IFC has been installed inside the cavity of the panel
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-200 3mm Alum Perf CW Module Subframe (Building A) - ITP | itp |  |  |  |  | CLD-200 3mm Alum Perf CW Module Subframe (Building A) - ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 50mm vertical top hat has been set out and installed to the primary purlin strcuture where needed.
label | Responsibility: Facadex
textbox | Date:
checkpoint | L-hook on bracket has been set out and installed to location on top of the UB with M12 bolts and carpal bracket washer
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Packers has been used to ensure the top hat sub-frame is plumb and bracket has been leveled for module to land and installed.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-208 Stramit Sharpline (Building A) - Factory ITP | itp |  |  |  |  | CLD-208 Stramit Sharpline (Building A) - Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-208 Stramit Sharpline (Building A) - Panel Site ITP | itp |  |  |  |  | CLD-208 Stramit Sharpline (Building A) - Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Screw/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Stramit Sharpline Cladding Panels installed to IFC specification
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Sharpline Cladding Panels checked for paint scratches and dents post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 0.48BMT colourbond flashing has been installed and sealed the bottom and top.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (screws/rivets) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-208 Stramit Sharpline Sub-Frame (Building A) - ITP | itp |  |  |  |  | CLD-208 Stramit Sharpline Sub-Frame (Building A) - ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (top hat/screws) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 50mm vertical top hat has been set out max 900 crs and installed to Structural Girts with #12 tek screws@600 crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | 50mm horizontal top hat has been set out and installed to vertical top hat with #12 tek screws@600crs
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Packers has been used to ensure the top hat frame is plumb for 0.55 BMT stramit sharpline panels to be cladded on.
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-214 Lysaght Spandek Cladding - Building E Factory ITP | itp |  |  |  |  | CLD-214 Lysaght Spandek Cladding - Building E Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLD-214 Lysaght Spandek - Cladding Building E Panel Site ITP | itp |  |  |  |  | CLD-214 Lysaght Spandek - Cladding Building E Panel Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | 0.55mm colorbond flashing has been installed to the gap to the strcutrue
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-513 Bridge Factory ITP | itp |  |  |  |  | CLG-513 Bridge Factory ITP
section | Details
checkpoint | IFC shop drawings approved for fabrication
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect sign off
textbox | Date:
checkpoint | Confirm and check finish as per approved IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check panel size and dimensions against IFC drawings
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Check diagonal dimension to ensure odd shape panel are done correctly
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | QA has checked delivery docket and receipt from powder coater
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Is fabricated item labelled as per drawing?
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Fabrication complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Prevent direct contanct between incompatible materials
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Materials ready to deliver on site
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-513 Steel Bracket Underside Site ITP | itp |  |  |  |  | CLG-513 Steel Bracket Underside Site ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (steel bracket/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Bracket installed as per shop details and location
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | ensure the correct steel bracket has been installed to the desinated spot along the underside of the pre-camped brdige
label | Responsibility: Facadex
textbox | Date:
checkpoint | Ensure the steel bracket installed was not bended or deformed.
label | Responsibility: Facadex
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | CLG-513 and SCN-125 Cladding Panel ITP | itp |  |  |  |  | CLG-513 and SCN-125 Cladding Panel ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Materials (Panels/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: Check colour is correct as per shop drawings
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
label | Comments: If installed off site no gridline available
checkpoint | Cladding Panels installed to manufacturers specifications
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Cladding Panels checked for paint scratches post installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist | Site Subframing for CLG-513 ITP | itp |  |  |  |  | Site Subframing for CLG-513 ITP
section | Details
checkpoint | IFC Shop Drawings Approved
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Material Approval
label | Responsibility: MPX
label | – – – – – – – – –
label | Acceptance Criteria: MPX / Architect Sign Off
textbox | Date:
checkpoint | Materials (truss frame/Bolts/Washers) delivered to site free of damage and deformation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Grid lines established and site set out complete
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
checkpoint | Truss Framing underside of the bridge installed as per shop details
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Truss Framing aligned finished level and plumb
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Top hat to primiry steel (side) or to truss frame (underside) installed and leveled for panel installation
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Standard Cladding Tolerance:
label | ○ +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
label | ○ +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
label | ○ +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm Expansion & Contraction:
label | ○ +/- 3mm @ every 1000mm in length & height
textbox | Date:
checkpoint | Connections (bolts/washers/screws) checked for damages
label | Responsibility: Facadex
label | – – – – – – – – –
label | Acceptance Criteria: Facadex sign off.
textbox | Date:
holdpoint | HOLD POINT- All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed product with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
label | Responsibility: Facadex / Builder
label | – – – – – – – – –
label | Acceptance Criteria: Defect notification via email or chosen correspondence
label | ○ Evidence of close out / rectification
label | ○ (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type)
label | ○ Sign of only once agreed that wall is defect free
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed