## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | TMR-RCP Installation | itp |  |  |  |  | TMR-RCP Installation
section | Details
checkpoint | 1 - Lot Boundaries
label | Acceptance Criteria - Lot Number established with the Lot boundaries of the works clearly defined for traceability
label | Item Check - Check and Verify
checkpoint | 2 - Construction Procedure
label | Acceptance Criteria - Approval of Construction Procedure
label | ○ Submitted during Traffic Application.
label | Reference - MRTS03 CL11.3.1
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | 2 - Materials
label | Acceptance Criteria - Bed Zone Material: 10mm Drainage Aggregate screenings Haunch Zone Material: 10mm Drainage Aggregate screenings
label | ○ Overlay Zone Material: 10mm Drainage Aggregate screenings - Dispensation Sought Backfill Material: Select Fill
label | ○ Pavement Reinstatement: Leanmix 300mm - Tac Coat - 50mm Asphalt
label | Reference - MRTS04 CL19.2.7 CL19.2.2 CL9.2.13
label | Item Check - Check and Verify
checkpoint | 3 - Excavation
label | Acceptance Criteria - Excavations shall be constructed to the shapes, lines, dimensions, and other requirements shown on the drawings
label | Reference - MRTS04 Cl13.3.3.1
label | Item Check - Check and Verify
checkpoint | 4 - Unsuitable Trench Foundation
label | Acceptance Criteria - Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, Hold Point notify the Administrator,
label | Reference - MRTS04 Cl13.3.2
label | Item Check - Hold Point
holdpoint | HOLD POINT
checkpoint | 5 - Trench Foundation
label | Acceptance Criteria - Testing: Bottom of Excavation
label | ○ Minimum Compaction 95%.
label | ○ 1 test per 20LM / Per Drainage line
label | Reference - MRTS04 CL13.3.7
label | Item Check - Check and Verify
checkpoint | 6 - Drainage of Bedding Materials
label | Acceptance Criteria - Upstream of each headwall, manhole, or gully (other than an end of line gully), a 3.0 metre length of 100mm diameter sub-soil drainage pipe has been laid in the bedding material
label | Reference - Note 1 IPEA STD DRW DS-030
label | Item Check - Check & Verify
checkpoint | 7 - Pipe Laying
label | Acceptance Criteria - Where spigot and socket joints are used, the thickness of bedding material under each socket shall not be less than 50 mm. Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet.
label | ○ Where the word ‘TOP’ is marked on pipes or where lifting holes are provided, the pipes shall be laid with the word / hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
label | ○ Spigot and socket joints shall be made using the appropriate rubber rings
label | Reference - MRTS03 CL11.3.5
label | Item Check - Check and Verify
checkpoint | 8 - Survey
label | Acceptance Criteria - Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Reference - MRTS03 CL11.3.10
label | Item Check - Hold Point 4
holdpoint | HOLD POINT
checkpoint | 9 - Geometric Tolerances
label | Acceptance Criteria - Vertical: +- 10mm Horizontal +- 100mm
label | ○ Difference in Grade between actual and specified 1% (Absolute)
label | Reference - MRTS03 Cl8
label | Item Check - Survey
checkpoint | 10 - Pipe Embedment Zone
label | Acceptance Criteria - Pipe backfill (Embedment zones) shall be uniformly graded 10mm Drainage Aggregate screenings to: TMR: 300mm above top of pipe min
label | Reference - SD1359
label | Item Check - Check and Verify
checkpoint | 11 - Pipe Backfill - Road Reserve
label | Acceptance Criteria - TMR Road Reserve: Pipe backfill (Above Embedment Zone) - Select Fill
label | ○ Minimum Compaction Top 300 mm below Subgrade Level 97%.
label | ○ > 300 mm below Subgrade Level 95%
label | Reference - MRTS04 Table 15.3b
label | Item Check - Testing
checkpoint | 12 - CCTV
label | Acceptance Criteria - The contractor shall conduct inspections of the pipe culvert using CCTV in accordance with WSA 05-2013 Conduit inspection Report Code of Australia Reports shall be submitted to the Administrator, and any rectification works completed, prior to acceptance of the culvert
label | Reference - MRTS03 CL11.3.5
label | Item Check - Hold Point 3
holdpoint | HOLD POINT
checkpoint | Final Verification
note | Name of Cient's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | TMR Pavement Reinstatement | itp |  |  |  |  | TMR Pavement Reinstatement
section | Details
checkpoint | 1 - Lot Size
label | Acceptance Criteria - Define lot size. Completion of works within the shift - single or double lane reinstatement.
label | Item Check - Check & Verify
checkpoint | 2 - Material Incorporation into Works
label | Acceptance Criteria - The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
label | ○ Pavement - Leanmix as submitted under concrete mix design approvals. - 300mm Seal - CRS60 Primer seal
label | ○ Asphalt - AC10 or AC14 - 60mm
label | ○ Downer - Brendale:
label | — TMR AC10 - D:AC10H/24/4208 (15R) (S) – Expiry 08/07/2027
label | — TMR AC14 - D:AC14H/24/4210 (15R) (S) – Expiry 24/07/2027
label | ○ Fulton Hogan - Narangba:
label | — TMR AC14 - FH : AC14H/24/3250(15R) – Expiry 11/03/2027
label | Reference - RS170
label | Item Check - Check & Verify
checkpoint | 3 - Submission of production procedure
label | Acceptance Criteria - The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
label | Reference - Check & Verify
checkpoint | 4 - Leanmix Pavement - 300mm Thick
label | Acceptance Criteria - Excavation to step 300mm past outside of trench to allow leanmix to bridge stormwater trench
label | ○ Layer Thickness between 100mm and 150mm in accordance with table 8.3.3
label | Reference - Check & Verify
label | Item Check - MRTS04 table 8.3.3
checkpoint | 5 - Asphalt Surfacing - 60mm Thick
label | Acceptance Criteria - Transverse joints are to be sawcut
label | ○ Final joints against existing asphalt are to be 1m outside of edge of stormwater trench. Primerseal to be sprayed and allowed to "Break" prior to asphalt placement.
label | Reference - RS170
label | Item Check - Check & Verify
checkpoint | 6 - Geometric Tolerances in accordance with RS-170 - Final layer only
label | Acceptance Criteria - Note 6. The vertical deviation from a 3m straight edger parrallel to the centreline of the existing road is not to exceed 5mm.
label | Reference - RS170
label | Item Check - Check & Verify
checkpoint | 7 - Visual Inspection
label | Acceptance Criteria - The finished surface of any pavement layer shall:
label | — be hard and homogenous in apperance
label | — not have any loose, segregated or contaminated areas
label | Item Check - Check & Verify
checkpoint | Final Verification
note | Name of Cient's Representative
textbox | Print Name:
date | Date:
note | Name of Contractor's Representative
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off