## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency |  |  |  |  | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 |  |  |  |  | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | F2TG |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[6 empty] | E | Examine | QM | QA Manager | Diliban Sengottian | DS
ITP Number: | DS2681-SH58-ITP-C-033 |  | Version: | 1 |  | H | Hold Point | SV | Surveyor | Jim Robbins | JR
ITP Description: | Pavements - Chipseal |  |  |  |  | I | Inspection | PS | Project Supervisor | John Masters | JM
Discipline: | Civil - Pavements |  |  |  |  | M | Monitor on Random Basis | ST | Superintendent | Craig Maloney | CM
Specification: | M2TG - Project Specification NZTA: M6, P3, Q/1 |  |  |  |  | O | Operation | PE | Project Engineer
[6 empty] | R | Review | SE | Site Engineer
Drawings: | No Drawings provided for the F2TG section |  |  |  |  | S | Subcontractor | EM | Environmental Manager | Ross Glubb | RG
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Collinson |  | Date: | 2025-09-01 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: expand this with document numbers and drawing numbers

## Construction
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Exisiting surface preparation | Prior to sealing surface is to be swept clean | Pre seal inspection and Engineer sign-off: Inspect exisiting surface is clear of grit, dust and debris. | Engineer Sign-off on ConQA | Per shift | H | ER
4.2 | Spray tackcoat | Observe correction application rate applied, monitor for issues such as blocked nozzles or streaking | Tack coat spray truck correctly calibrated to design residual spray rate. | Delievery dockets, site photos | Per shift | W | SE
4.3 | Apply chip | Witness chip spreading to match binder application, ensuring coverage before cooling of tack coat. | Chip application to match design chip rate. For multilayer seals the whole sealed area shall have a uniform double retained layer of chips with the second chip fitting inside the interstices of the chip used for the first layer. Hand brooming or drag brooming for even distribution. Sealed area to meet performance requirements of NZTA P17 7.1, 7.2 and 7.3 | Delievery dockets, site photos | Per shift | W | SE
4.4 | Compaction of chipseal | Monitor rolling operations | Compaction of aggregate is satisfactory with no overlapping chips or unbound areas. | Site photos | Per shift | W | SE
4.5 | Traffic management | 48 hour post seal traffic management | Avoid stop-start traffic. Traffication of the seal. Linemarking prior to removal. | Site photos | Post sealing | W | SE
4.6 | Visual inspection | Conduct visual inspection of the completed seal, checking for uniformity and chip adhesion. Also verify no loose chips or defects remain before lifting temporary speed restrictions | Seal quality meets NZTA P17 Table 2. Reseal Performance Criteria and NZTA P17 Section 9 - Compliance Assesment. | Site Photos, Check Sheet | Per site | H | SE
4.7 | Survey As-built | Surveyor to use Drone to as-built completed section once linemarking has been completed | Drone survey of completed surface and line marking | Site photos, survey as-builts | Per site | H | SV