## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency |  |  |  |  | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 |  |  |  |  | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | F2TG |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[6 empty] | E | Examine | QM | QA Manager | Diliban Sengottian | DS
ITP Number: | DS2681-SH58-ITP-M-010 |  | Version: | 1 |  | H | Hold Point | SV | Surveyor | Jim Robbins | JR
ITP Description: | Pavements - Chipseal Materials |  |  |  |  | I | Inspection | PS | Project Supervisor | John Masters | JM
Discipline: | Civil - Pavements |  |  |  |  | M | Monitor on Random Basis | ST | Superintendent | Craig Maloney | CM
Specification: | M2TG - Project Specification NZTA: M6, P3, Q/1 |  |  |  |  | O | Operation | PE | Project Engineer
[6 empty] | R | Review | SE | Site Engineer
Drawings: | No Drawings provided for the F2TG section |  |  |  |  | S | Subcontractor | EM | Environmental Manager | Ross Glubb | RG
[6 empty] | V | Visual Verification
Prepared By: (Name) | Tyler Collinson |  | Date: | 2025-09-01 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: expand this with document numbers and drawing numbers

## Material
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Design Approval | Seal design report to indicate type of seal, binder/chip rates and site acceptance. | Design is to meet NZTA P17 Table 2. Reseal Performance Criteria. | Confirmation from Stantec representative | Per design | Holdpoint | H | ER
3.2 | Emulsion Binder Approval | Approval of IANZ test results for site use | Bituminous binder to shall comply with NZTA P17 8.3 and NZTA M1 specification. | Testing report, Confirmation from Stantec representative | Prior to Sealing | Witness Point | W | SE
3.3 | Aggregate Approval | Approval of IANZ test results for site use | Chip shall comply with NZTA P17 Section 8 | Testing report, Confirmation from Stantec representative | Prior to Sealing | Witness Point | W | SE
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tyler Collinson please discuss with me on this
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design and application rates TBC