## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-033 Pavements Chipseal | itp |  |  |  |  | DS2681-SH58-ITP-C-033 Pavements Chipseal
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Exisiting surface preparation
label | Inspection Point: Quality Control Activity - Prior to sealing surface is to be swept clean
label | Acceptance Criteria - Pre seal inspection and Engineer sign-off: Inspect exisiting surface is clear of grit, dust and debris.
label | Verifying Document - Engineer Sign-off on ConQA
label | Frequency - Per shift
label | Inspection Type (Visual, other) - H
label | Inspection: Key - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Spray tackcoat
label | Inspection Point: Quality Control Activity - Observe correction application rate applied, monitor for issues such as blocked nozzles or streaking
label | Acceptance Criteria - Tack coat spray truck correctly calibrated to design residual spray rate.
label | Verifying Document - Delievery dockets, site photos
label | Frequency - Per shift
label | Inspection Type (Visual, other) - W
label | Inspection: Key - SE
checkpoint | 4.3 - Apply chip
label | Inspection Point: Quality Control Activity - Witness chip spreading to match binder application, ensuring coverage before cooling of tack coat.
label | Acceptance Criteria - Chip application to match design chip rate. For multilayer seals the whole sealed area shall have a uniform double retained layer of chips with the second chip fitting inside the interstices of the chip used for the first layer. Hand brooming or drag brooming for even distribution. Sealed area to meet performance requirements of NZTA P17 7.1, 7.2 and 7.3
label | Verifying Document - Delievery dockets, site photos
label | Frequency - Per shift
label | Inspection Type (Visual, other) - W
label | Inspection: Key - SE
checkpoint | 4.4 - Compaction of chipseal
label | Inspection Point: Quality Control Activity - Monitor rolling operations
label | Acceptance Criteria - Compaction of aggregate is satisfactory with no overlapping chips or unbound areas.
label | Verifying Document - Site photos
label | Frequency - Per shift
label | Inspection Type (Visual, other) - W
label | Inspection: Key - SE
checkpoint | 4.5 - Traffic management
label | Inspection Point: Quality Control Activity - 48 hour post seal traffic management
label | Acceptance Criteria - Avoid stop-start traffic. Traffication of the seal. Linemarking prior to removal.
label | Verifying Document - Site photos
label | Frequency - Post sealing
label | Inspection Type (Visual, other) - W
label | Inspection: Key - SE
checkpoint | 4.6 - Visual inspection
label | Inspection Point: Quality Control Activity - Conduct visual inspection of the completed seal, checking for uniformity and chip adhesion. Also verify no loose chips or defects remain before lifting temporary speed restrictions
label | Acceptance Criteria - Seal quality meets NZTA P17 Table 2. Reseal Performance Criteria and NZTA P17 Section 9 - Compliance Assesment.
label | Verifying Document - Site Photos, Check Sheet
label | Frequency - Per site
label | Inspection Type (Visual, other) - H
label | Inspection: Key - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Survey As-built
label | Inspection Point: Quality Control Activity - Surveyor to use Drone to as-built completed section once linemarking has been completed
label | Acceptance Criteria - Drone survey of completed surface and line marking
label | Verifying Document - Site photos, survey as-builts
label | Frequency - Per site
label | Inspection Type (Visual, other) - H
label | Inspection: Key - SV
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2681-SH58-ITP-M-010 Chipseal Materials | itp |  |  |  |  | DS2681-SH58-ITP-M-010 Chipseal Materials
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Design Approval
label | Inspection Point: Quality Control Activity - Seal design report to indicate type of seal, binder/chip rates and site acceptance.
label | Acceptance Criteria - Design is to meet NZTA P17 Table 2. Reseal Performance Criteria.
label | Verifying Document - Confirmation from Stantec representative
label | Frequency - Per design
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Emulsion Binder Approval
label | Inspection Point: Quality Control Activity - Approval of IANZ test results for site use
label | Acceptance Criteria - Bituminous binder to shall comply with NZTA P17 8.3 and NZTA M1 specification.
label | Verifying Document - Testing report, Confirmation from Stantec representative
label | Frequency - Prior to Sealing
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 3.3 - Aggregate Approval
label | Inspection Point: Quality Control Activity - Approval of IANZ test results for site use
label | Acceptance Criteria - Chip shall comply with NZTA P17 Section 8
label | Verifying Document - Testing report, Confirmation from Stantec representative
label | Frequency - Prior to Sealing
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE