## 1145-C200-FUL-QAC-ITP-0001
|  |  | Inspection and Test Plan - Stripping Topsoil, Clearing and Grubbing | [7 empty] | Document DOT35734 - ITP 001
Revision : 00
Client: Department of Transport & Planning |  |  |  | Construction Process: Stripping Topsoil, Clearing and Grubbing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 176, 201, 700, 720 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Construction footprint |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman Contractor | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP | Document review & Site inspection | This ITP Signed | IP | Site Engineer | N/A |  | N/A
1.2 | Ground Penetration Permit (GPP) issued |  | Prior to Commencing Work | Current GPP signed and specific for the area where works will be executed. Services in the work area are identified | Vicraods Spec.700.1, GPP | Document review & Site inspection | Excavation Permit Signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Extent of Clearing and Grubbing |  | Prior to Commencing Work | Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones. | Project Spec. 176.I1 & Vicroads Spec.201 | Site Inspection | Extent of Clearing and Grubbing reviewed by Superintendent | HP | Site Engineer/ Superintendent |  |  | N/A
1.4 | Extent of Clearing and Grubbing |  | Prior to Commencing Work | The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation. | Vicroads Spec.720.07 | Document review | Copy of issued permits | HP | Site Engineer/ Superintendent | N/A |  | N/A
1.5 | Identification of Cultural Heritage sites and areas of Cultural Significance |  | Prior to Commencing Work | Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Immediately stop work and notify the Superintendent if any Cultural Heritage is discovered or identified during construction. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage. | Relevant EMP | Document review & Site inspection | Cultural Heritage approval (when required) Signed ITP | HP* AP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Stripping of topsoil and grubbing of vegetation |  | Prior and after commencement of any ground disturbing activities | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material | VicRoads Specification 201.05 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.2 | Removal of abandoned services |  | Prior to commencing this work | Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done. Verify service is not likely to contain a hazardous material (sewage, asbestos pipe) Decommissioned services to be disposed of in a suitable manner. Decommissioned pits have been broken back to 0.3 metres below subgrade level. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95% | VicRoads Specification 201.05 | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
2.3 | Clearing of Trees and Vegetation |  | During clearing works | Clearing work shall not be undertake outside of the specified and approved limits of work. Tree branches extending over the carriageway shall be trimmed by a suitably qualified arborist to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used. | VicRoads Specification 201.04 | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
3 | Completion
3.1 | Disposal of vegetation |  | At completion of works | Tree trunks and large branches shall be removed from the site. Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch. Disposal of noxious weeds shall be in acordance with the CaLP permit | VicRoads Spec. 201.07 CaLP Permit | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent