## ITP
|  |  | Inspection and Test Plan - Pavement Excavation and Subgrade Preparation | [7 empty] | Document DOT35734 - ITP 002
Revision : 00
Client: Department of Transport & Planning |  |  |  | Construction Process: Pavement Excavation and Subgrade Preparation |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 173, 204 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Construction footprint |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
1.3 | Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, Site Induction | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
1.4 | Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Coordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer | N/A |  | N/A
2 | Excavation Works
2.1 | Survey set-out |  | Prior to Excavation | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used. The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line. | VicRoads Specification Cl.204.03 | Site Inspection | Survey records & pegs on the ground | SCP | Site Engineer & Surveyor | N/A
2.2 | Site Excavation |  | Prior to (and during) Excavation of any new areas | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04. | VicRoads Specification Cl. 204.06(c) | Site Inspection | Area reviewed by Superintendent and Contractor Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.3 | Ground water |  | Prior to Construction of Subbase Layer | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | VicRoads Specification Cl. 204.06(h) | Site Inspection/ Document Review | Area reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.4 | Acceptance of Rock Subgrade (when applicable) |  | Prior to Construction of Subbase Layer | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. The Contractor shall submit details of any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces to the Superintendent for review. No adjustment to the Contract Sum will be considered for the treatment of a rock subgrade, or for the construction of the regulating layer in lieu of capping or selected material, or for any modifications to the subsurface drainage. | VicRoads Spec. Cl. 204.06(f) | Site Inspection/ Document Review | Superintendent acceptance Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.5 | Proof Roll - Cut Floor |  | Prior to Construction of Subbase Layer | Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling. Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling. No fill or subbase materials are to be placed on the prepared areas until the the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent | VicRoads Specification Cl. 204.12 Cl.173.03 Cl. 204.10(b) Cl. 204.07(d) Cl.204.11 | Site Inspection | Area visually reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.6 | Survey Pickup |  | Prior to Construction of Subbase Layer | Ensure the Cut Floor Level is recorded by survey | VicRoads Specification Cl. 204.03(f) Cl. 204.03(g) Table 204.031 | Document Review | Survey As-Built | SCP | Site Engineer & Surveyor | N/A
2.7 | Re-Use of insitu material |  | Prior to Placing fill | If exacavated material is to be reused as Type A or B material, the Superintendent and the Contractor shall inspect the material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04. Type B Material shall meet the following requirements: CBR ≥ 1.5% Swell < 2.5%. Attach: Test Certificates | VicRoads Specification Cl. 204.04 Cl. 204.06 | Site Inspection | TestResults Material Category agreed with Superintendent | HP | Site Engineer & Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent