## ITP
|  |  | Inspection and Test Plan - Underground Stormwater Drainage | [7 empty] | Document # DOT35734 - ITP 004
Client: Department of Transport & Planning |  |  |  | Construction Process: Underground Stormwater Drainage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 610, 619, 701, 705 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Pavements |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman GPP Coordinator | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Work | Ensure that all employees and subcontractors are using the correct, complete and most up-to-date set of drawings. | IFC Drawings, Drawing Register | Visual Inspection | This ITP signed | HP* | Site Engineer/Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Work | All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, TMP, OHSCP, SWMS. | QMP, EMP, ECP, TMP, OHSP, SWMS | Visual Inspection | This ITP signed | HP* | Site Engineer/Site Foreman | N/A |  | N/A
1.3 | Precast Pit & Pipe Compliance |  | Prior to Commencing Work | A complying test Certificate shall be provided to the Superintendent at least 5 days prior to installation, certifying that pit access covers have been tested and certified by a NATA accredited laboratory as complying with the requirements of AS 3996 and DTP. Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058. Drainage Pits are supplied in accordance with 705.07. | VicRoads Spec 705.04, 701.04, 701.05, 705.07 | Document Review | This ITP signed | HP IP | Site Engineer |  |  | N/A
1.4 | Drainage Bedding Material |  | Prior to Commencing Work | Bedding Materials comply with Table 701.081 and 701.082. Material Approved by client. | Table 701.081, Table 701.082 | Document Review | This ITP signed | AP | Site Engineer | N/A |  | N/A
1.5 | Drainage Backfill Material |  | Prior to Commencing Work | Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082 Material Approved by client. | Table 701.081, Table 701.082 | Document Review | This ITP signed | AP | Site Engineer | N/A |  | N/A
1.6 | Material Inspection |  | Each Delivery | Material inspection to be completed for all precast pits, pipes, beaching and culverts. | Order Acceptance Form | Document Review | This ITP signed | IP | Site Engineer/Site Foreman | N/A |  | N/A
1.7 | Ground Penetration Permit (GPP) issued |  | Prior to Commencing Work | Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer/Site Foreman | N/A |  | N/A
2 | Installation of Drainage
2.1 | Confirm position of culverts |  | Prior to commencing drainage line | Prior to commencement of excavation for the culverts and stormwater drainage, confirm the position with the Superintendent. | VicRoads Spec. Cl. 701.10 IFC Drawing | Site Inspection | Design and survey setout postion confirmed with Superintendent. | HP | Engineer / Foreman / Superintendent |  |  | N/A
2.2 | Excavation |  | Each trench | Ensure trench is excavated to prepare culvert foundation and specified depth of bedding. Pipe culverts: - the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm. Pits: - Clearance from external faces of the pit to each face of the excavation to be not less than 400mm | VicRoads Spec. Cl. 701.15 Table 701.151 Cl. 705.05(b) | Site Inspection Measurements of trench | ITP signed | IP | Engineer | N/A |  | N/A
2.3 | Bedding |  | Each trench | Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be: - minimum 100mm for pipes of D< 1500mm - minimum 200mm for pipes with D ≥ 1500 mm 'D' is the nominal pipe diameter or culvert width. Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. | VicRoads Spec. Cl. 701.16 Cl. 701.20(a) | Site Inspection | Test Report | IP | Engineer | N/A |  | N/A
2.4 | Laying of Pipes |  | Each culvert | Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream) The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length. Where applicable, the top of the pipe as marked shall be within five degrees of the vertical axis of the culvert. Spacing of multiple rows of culverts to reflect Table 701.171. | VicRoads Spec. Cl. 701.17(b) | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
2.5 | Jointing |  | Each culvert | Rubber Ring Joints (RRJs) jointed with rubber rings which have been kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately. RRJs assembled and prepared in accordance with the manufacturer’s recommendations. | VicRoads Spec. Cl. 701.18 | Document review/ Site Inspection | Manufacturer’s recommendations ITP signed | IP | Engineer | N/A |  | N/A
2.6 | Survey |  | Each Lot | The location of each run of underground drainage has been verified by a survey pickup prior to backfill and form the as constructed survey. Tolerances that apply: (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade. (d) Departure from design grade of pipe runs +/-10mm in 10m provided minimum grade is not less than 1:250 | VicRoads Spec. Cl.701.10 | Survey | Survey Report | SCP | Engineer / Surveyor | N/A |  | N/A
2.7 | Backfilling |  | Each culvert | Culvert Under Area to be Paved: Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material. Where the trench is excavated from below design subgrade level the trench is filled with selected backfill material. Culvert Under Area not to be Paved: The trench is backfilled with selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level. | VicRoads Spec. Cl. 701.19(a) | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
2.8 | Construction of Rock Apron at Concrete Headwalls |  | Each Headwall | Rock for Type 1 beaching shall consist of field or quarry rock. All rocks shall have a mass of between 20 and 70 kg and at least 60% by number shall be over 40 kg. Rocks shall be of such size that the layer of beaching is not less than 225 mm thick. Rock apron to be installed as per design drawings. | VicRoads Spec. 703 | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
3 | Testing and Inspection
3.1 | Inspection of Drainage Lines (CCTV) |  | Each culvert prior to construction of pavement layers | All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisaiton using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. | VicRoads Spec. Cl. 701.30 | Site Inspection | Inspection Report ITP signed | HP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
3.2 | Repairs to Damaged Pipes |  | As Required | The Contractor shall submit details of proposed rectification treatments including manufacturer's product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans. No repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures. | VicRoads Spec. Cl. 701.31 | Document Review/ Site Inspection | Latest IFC Drawing ITP signed | HP | Site Engineer / Site Foreman / Superintendent |  |  | N/A
3.3 | Bedding Compaction Requirements |  | Each Lot | Bedding assessed for compaction and /or moisture in lots. Bedding compacted to refusal with handheld mechanical equipment with a mean moisture ratio of 92%. | VicRoads Spec. Cl. 701.20 (a) | Site Inspection | Compaction and moisture Test Records ITP signed | TP | Engineer | N/A |  | N/A
3.4 | Backfill Compaction and Moisture requirements |  | 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls) Min. 20% of all lots for each culvert shall be tested. | Backfill assessed for compaction and or moisture in lots. Backfill material which will have a nominal size after compaction of 40mm or < less compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater > than 2.5% maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. | VicRoads Spec. 701.20 (b) | Site Inspection | Compaction and moisture Test Records ITP signed | TP | Engineer | N/A |  | N/A
3.5 | Flushing System |  | Each culvert | Each culvert flushed clean from end to end on completion and maintained in proper working order. | VicRoads Spec. Cl. 701.28 | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
#