## ITP-012
|  |  | Inspection and Test Plan - Subsurface Drainage | [7 empty] | Document # DOT35734 ITP-005
Revision : 1
Client: Department of Transport & Planning |  |  |  | Construction Process: Subsurface Drainage Installation |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification Section 702, Standard Drawing SD1621 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Civils |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, ERA, SWMS | QMP, EMP, ECP, ERA, SWMS | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Submission of Quality Procedures |  | Prior to works commencing | Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures | VicRoads Spec 702.09 (g) | Verify | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
1.4 | Material Classification |  | Each Lot | Subsurface drainage pipes: - 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2. Granular filter material for bedding and backfill: - Trench backfilled with no fines concrete filter medium complying with Cl 702.05 No Fines Concrete - No fines concrete shall consist of Type GP cement, water and coarse aggregate. The quantity of cement used shall be 4.0% by volume. Type GP Cement, water and coarse aggregate shall comply with the requirement of Section 703. Geotextiles: - Shall comply with Cl 702.06. Subsurface drain pits: - All subsurface drain pits shall be Type S1 to the specification of SD 1611 Pit Lids: - Type M3 circular lid (as per SD 1051) for Type S1 pit Flushout risers: - Constructed to the detail of SD 1631 | VicRoads Spec 702.04 702.05 702.06 | Verify | This ITP signed off | HP* | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Survey and Set Out |  | Each lot | Subsurface drains, whether pipe or geocomposite systems, shall be constructed true to line, level and depth, as shown on the drawings. | Design Drawings | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2.2 | Excavation of Trench |  | Each Lot | Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. The base of the trench shall be inspected by the Superintendent prior to placing bedding in completed excavations. | VicRoads Spec 702.08 | Visual Inspection | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
2.3 | Placement of bedding |  | Each Lot | Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level | VicRoads Spec 702.09 (c ) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.4 | Placing pipes and geofabric (if required) |  | Each Lot | Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm | VicRoads Spec 702.09 | Visual Inspection | This ITP signed off | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.5 | Placement of backfill |  | Each Lot | Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. No-fines concrete is to be placed and compacted within one hour of mixing and is to be compacted in accordance with the approved quality procedure. | VicRoads Spec 702.09 (g) | Visual inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.6 | Compaction of backfill |  | Each Lot | The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent. | VicRoads Spec 702.9 | Document review | This ITP signed off | HP | Site Engineer / Superintendent |  |  | N/A
2.7 | Install Pits and Flushouts |  | Each Lot | Installed in accordance with drawings and Cl 702.10 | VicRoads Spec 702.1 | Verify | This ITP signed off | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.8 | Flushing Test |  | At completion of stage | Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture. | VicRoads Spec 702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | WP | Site Engineer/ Superintendent |  |  | N/A
2.9 | CCTV |  | At completion of stage | Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent. | VicRoads Spec 702.09(i) | Site inspection | Signed ITP/ Record of flushing tests | HP | Site Engineer/ Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent