## ITP-006
|  |  | Inspection and Test Plan - General Concrete Paving | [7 empty] | Document # DOT35734 - ITP 006
Client: Department of Transport & Planning |  |  |  | Construction Process: General Concrete Paving |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 610, 703 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Concrete pavements |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.3 | Submission & Approval of Concrete Mix Design |  | Prior to first concrete pour | The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes. | 610.07(b) | Verify | ITP Signed Mix design approval | HP | Site Engineer/ Superintendent |  |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | 703.17 | Verify | ITP Signed | HP | Project Engineer/ Superintendent |  |  | N/A
2.2 | Excavation Permit |  | If Required | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation Permit | Visual inspection | ITP Signed | WP | Project Engineer/ Site Foreman | N/A |  | N/A
2.3 | Excavation |  | Each Lot | Excavation completed to required depth to allow placement of the bedding layer | 703.2 | Verify | ITP Signed | IP | Site Engineer | N/A |  | N/A
2.3 | Bedding |  | Each lot | All bedding material used shall be as follows: - Pavement Type 5 Footpath: 100mm layer of 20mm Class 3 Crushed Rock - Pavement Type 6 Concrete Median: 100mm layer of 20mm Class 3 Crushed Rock - Pavement Type 7 Concrete Path: 100mm layer of 40mm Class 3 Crushed Rock | Cl 703.21 Design Drawings | Visual inspection | ITP Signed | WP | Project Engineer/ Superintendent | N/A |  | N/A
2.5 | Formwork |  | Each Lot | Formwork shall comply with the requirements of AS 3610 | 703.12 AS 3610 | Verify | ITP Signed | IP | Site Engineer | N/A |  | N/A
2.5 | Reinforcement |  | Each Lot | All steel reinforcement used shall be: - Pavement Type 5 Footpath: SL72 Steel Mesh - Pavement Type 6 Concrete Median: SL72 Steel Mesh - Pavement Type 7 Concrete Path: SL82 Steel Mesh Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm | AS/NZS 4671 | Visual inspection | ITP Signed | IP | Project Engineer | N/A
2.4 | Concrete Placement |  | Each lot | Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Concrete shall be thoroughly compacted via continuous tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings. Where fresh concrete is being placed against concrete which has taken intial set, a properly formed construction joint must be used. | Cl 703.08 | Verify | ITP Signed Ambient Temperature..... °C Concrete Temperature...... °C | HP*/ WP | Project Engineer/ Superintendent | N/A
2.7 | Surface Finish |  | Each Lot | Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanenelty hidden surfaces in accordance with AS3610/ | 703.25 | Visual inspection | ITP Signed | IP | Site Engineer/ Site Foreman | N/A
2.8 | Joints |  | Each joint | Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Expansion joints shall be placed at intervals not exceeding 10 m, on either side of vehicle crossings, at junctions with existing footpaths and shared use paths, at junctions with bridges and around all abutting structures such as pits, utility services, power poles, kerbs and other such features. | 703.26 | Verify | ITP Signed | IP | Project Engineer/ Site Foreman | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent