## ITP-010
|  |  | Inspection and Test Plan - Hot Mix Asphalt Placement | [7 empty] | Document # ITP-007
Client: Department of Transport & Planning |  |  |  | Construction Process: Installation of Hot Mix Asphalt |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 407, 408 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Sealed Pavements |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Construction Works
1.1 | Submission of Mix Designs |  | Prior to commencing paving | The Contractor shall submit the details of the trackless tack coat or tack coat application system proposed to be used in the works. All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport and Planning as ‘General’, unless otherwise approved by the Department of Transport and Planning. The registration for all mixes incorporated into the works shall be current at the time of their use. The Contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use. | VicRoads Spec. Cl.407.08 Cl.407.09 | Correspondence of receipt of mix design | VR approval ITP Signed | HP | Site Engineer/ Asphalt Supervisor / Superintendent |  |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A
1.3 | Site Inspection and Base Condition |  | Prior to commencing paving | Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials. | VicRoads Spec 407.14 AS2150 10.1 AS2150 10.3 Completed ITP-008/009 | Visual Inspection | ITP Signed | WP | Site Engineer/ Asphalt Supervisor | N/A
1.4 | Ambient Conditions for Placing |  | Prior to commencing paving | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs If specified temperatures are unachievable, prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review. | VicRoads Spec. 407.13 | Verify | Thermometer reading | HP | Site Engineer/ Asphalt Supervisor / Superintendent
1.5 | Planning of Joints |  | Prior to commencing paving | Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. | VicRoads Spec 407.17 (b) & (c) Pavement Drawings | Measure and mark out runs by tape measure or survey | Paving Plan | WP | Project Engineer/ Asphalt Supervisor | N/A
2 | Asphalt Placement works
2.1 | Commencement of Placing |  | Prior to commencing Paving | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client. Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the design rates of application to those provided under clause 408.13(a). (Sprayed Bituminous Surfacings only) Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the design rates of application to those provided under clause 408.13(a). | VicRoads Spec 407.18 408.04 | Visual Inspection Written Confirmation | ITP Signed | HP | Site Engineer/ Asphalt Supervisor / Superintendent
2.2 | Delivery of Mix |  | Each load | Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | VicRoads Spec 407.16 Table 407.081 | Visual Inspection | Delivery Docket | WP | Site Engineer/ Asphalt Supervisor | N/A
2.3 | Traceability |  | Each lot | Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | Fulton Hogan Quality Plan | Verify | Daily Lot Record | IP | Site Engineer/ Asphalt Supervisor | N/A
2.4 | Layer Thickness and Level Control |  | Regularly during paving | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | VicRoads Spec 407.20 (a) & (b) Drawings | Verify | Dips using ruler or dip stick | WP | Site Engineer/ Asphalt Supervisor | N/A
2.5 | Surface Finish of Wearing Course |  | During paving and after final roll | The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent. | VicRoads Spec 407.23 (a)(i) 407.29 | Visual Inspection | ITP Signed | WP HP | Site Engineer/ Asphalt Supervisor | N/A
2.6 | Kerb and Channel |  | During paving and after final roll | The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | VicRoads Spec. 407.23 (a)(ii) | Visual Inspection | ITP Signed | WP | Site Engineer/ Asphalt Supervisor | N/A
2.7 | Alignment of layers not placed against concrete edge |  | During paving and at completion of work | The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m | VicRoads Spec 407.23 (a)(iv) Drawings | Visual Inspection | ITP Signed | IP | Site Engineer/ Asphalt Supervisor | N/A
3 | Testing
3.1 | Compaction |  | Per Lot | For layers <50mm, if characteristic density ratio is: - 94.0% or greater Accept lot - 91.0% to 93.9% Lot may be accepted at reduced rate For layers ≥50mm, if characteristic thickness is: - 96.0% or greater Accept lot - 91.0% to 95.9% Lot may be accepted at reduced rate | VicRoads Spec Table 407.221 | Verify | Test Report | TP | Site Engineer/ FH Lab Technician | N/A
3.2 | Level Conformance |  | Per Lot | Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm | VicRoads Spec Table 407.232 | String Sheet | Survey Conformance | SCP | Site Engineer/ Supervisor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent