## 1145-C200-FUL-QAC-ITP-0001
|  |  | Inspection and Test Plan - Drilling and Setting of Dowel Bars | [7 empty] | Document DOT35734 - ITP 008
Client: Department of Transport & Planning |  |  |  | Construction Process: Stripping Topsoil, Clearing and Grubbing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: Skenes Creek Bridge Upgrade Structural Drawings |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Construction footprint |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Existing Bridge Deck |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Work | Ensure that all employees and subcontractors are using the complete set of the correct and most current drawings. | Design IFC Drawings | Document review | This ITP Signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Safety measures are in place, SWMS undertaken |  | Prior to Commencing Work | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Coordination Plan | Document Review | SWMS(s) signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Confirm understanding of current EMP & ECP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, ECP | Document review & Site inspection | This ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Ground Penetration Permit (GPP) issued |  | Prior to Commencing Work | Current GPP signed and specific for the area where works will be executed. | GPP | Document review & Site inspection | Excavation Permit Signed | HP* | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Set Out |  | Prior to Drilling | GPR Scan concrete deck to locate the upper bent of the existing shear ligatures of the existing RC beam. The scan shall mark also the deck reinforcement on top of concrete deck. Spacing of dowel bars can be adjusted by 25mm from specificied locations in the drawings to avoid cutting existing bars. | Design IFC Drawings | Document Review & Site Inspection | This ITP Signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
| Drilling of Pilot Hole |  | Each Lot | Drill an initial pilot hole 10mm nominal diameter at specified location from beam end. If reinforcement encountered, stop drilling immediately and attempt another pilot hole approximately 25mm longitudinally and laterally away from the first pilot hole in parallel direction to the existing beam. If reinforcement is still encountered, use the same offsets in the opposite direction until a clear hole is obtained. A succesful pilot hole is obtained when a 150mm drill hole does not enounter reinforcement. Once a successful pilot hole is obtained, drill hole to required depth and diameter shown on the drawings and use for the first dowel bar. | Design IFC Drawings Dowel Hole Drilling Procedure | Site Inspection | This ITP Signed | HP* | Site Engineer / Site Foreman | N/A
| Drilling of Dowel Holes |  |  | Locate subsequent drill holes in the same longitudinal alignment as first dowel bar. If reinforcement is encountered, repeat procedure stated in item 2.2. Use percussion drills only for dowel hole. Coring is strictly prohibited. | Design IFC Drawings Dowel Hole Drilling Procedure | Site Inspection | This ITP Signed | HP* | Site Engineer / Site Foreman | N/A
| Cleaning of Holes |  |  | Ensure all holes are cleaned in accordance with the manufacturer's installation instructions. This must include the following as a minimum: • Air flush twice at the specified pressure. • Brush clean twice. • Air flush twice at the specified pressure. • Fingertip test the hole surface for dust, and if dust is still present, brush clean and air-flush until all dust is removed. Ensure hole is clean and free of debris, dust particles, oils and other contaminants over its full depth. | VicRoads Spec. 680.08 Manufacturer's Specification | Site Inspection | This ITP Signed | HP* |  | N/A
2.2 | Trial Installation |  | Each Lot | Prior to proceeding with the installation of all dowels bars, the trial system installation shall be witnessed by the superintendent and the outcomes reviewed and approved by the Superintendent. | VicRoads Spec. 680 | Site Inspection | Signed ITP | WP | Site Engineer/ Superintendent |  |  | N/A
2.3 | Installation of Dowels Bars |  | Prior to commencing this work | Ensure materials being used are in accordance with standard specifications and design drawings. Installation to be undertaken in accordance with manufacturer's specifications. Seal all unused drill holes prior to constructiing deck concrete by filling with 'Hilti' HIT-RE 500 as per manufacturer's specifications. | Manufacturer's Specification Design IFC Drawings | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent