## ITP-002
|  |  | Inspection and Test Plan - Bored Cast-In-Place Piles (Without Permanent Casing) | [7 empty] | Document # ITP-009
Client: Department of Transport & Planning |  |  |  | Construction Process: Bored Cast-In-Place Piles (Without Permanent Casing) |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 602, 606, 610, 611 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Bored Piles |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Pedestrian Bridge |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Document Review | ITP Signed | HP* | Site Engineer/ Supervisor | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS, CMS, ECP, CASS MP. | QMP, TMP, SWMS, CMS, ECP, CASS MP | Visual inspection | ITP Signed | HP* | Site Engineer/ Supervisor | N/A |  | N/A
1.3 | Excavation Permit Issued |  | 4 weeks prior to commencement | The Contractor shall submit for review by the Superintendent a quality procedure / work method statement for the construction of the piles not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent. | VicRoads Sec.610.18 Quality Procedure | Document Review | ITP Signed | HP | Project Engineer / Superintendent
1.4 | Excavation Permit Issued |  | Prior to commencing any activity | Current Excavation Permit signed and specific for to the area where works will be execxuted. | Excavation Permit | Document Review | ITP Signed | IP | Site Engineer | N/A
1.5 | Materials |  | Prior to commencing any activity | The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing. Ensure that materials on-site are sufficient for the completion of works. | Design Drawings, VicRoads Standard Section 610 & 611 | Visual Inspection/ Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP | Site Engineer |  |  | N/A
2 | Construction Works
2.1 | Indentification of Services |  | Prior to commencing any activity | Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works. | DBYD | Visual inspection | ITP Signed | HP* | Site Engineer | N/A |  | N/A
2.2 | Concrete Blinding |  | Each Lot | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Design Drawings & Survey Data | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.3 | Set Out of Piles |  | Each Lot | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Design Drawings & Survey Data | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.4 | Protection of Adjacent Piles |  | Each Lot | No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa. | VR Section 608.05 | Visual Inspection | ITP Signed | WP | Project Engineer | N/A |  | N/A
2.5 | Geotechnical Supervision |  | Each Lot | The construction of the bored piles shall be carried out in the presence of a geotechnical engineer with appropriate experience to confirm that the founding materials at the piling locations are of a strength to satisfy the design assumptions. The geotechnical engineer engaged by the contractor shall be independent of the piling sub-contractor. | Design Drawings | Visual Inspection | ITP Signed | HP* | Site Engineer | N/A
2.6 | Inspection of Pile Excavation |  | Each Lot | The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions. | VicRoads Section 606.05 | Visual inspection | ITP Signed | HP | Project Engineer/ Geotechnical Engineer/ Superintendent |  |  | N/A
2.7 | Casting Piles |  | Each Lot | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent. | VicRoads Section 606.06 (a) | Document Review | ITP Signed | HP | Project Engineer |  |  | N/A
2.8 | Casting Under Water |  | Each Lot | Concrete placed under water shall be self compacting concrete (SCC) in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c). The outlet of the tremie pipe or pump discharge hose shall not be lifted from the bottom of the hole until the hole has been filled with a minimum of 2m depth of concrete. Thereafter, concreting shall be kept a minimum of 2m below the top surface of the concrete at all times and the Contractor shall continuously monitor and ensure that the 2m depth of embedment is to be maintained at all time. | VicRoads Section 606.06 (b) | Visual Inspection | ITP Signed | HP* |  | N/A |  | N/A
2.9 | Placement of Concrete |  | Each Lot | Concrete shall not be placed in bored piles, under water or in a dry bore until the propose method of placement of concrete has been approved by the Superintendent. | VicRoads Section 610.18 | Visual inspection | ITP Signed | HP | Project Engineer |  |  | N/A
3 | Quality Control Testing
3.1 | Concrete Testing |  | Each Lot | All testing shall be undertaken by a prequalified consultant in accordance with the VicRoads scheme for prequalification and approval of the Superintendent. The consultant shall be independent of the piling contractor. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing. | VR Section 610.16 | Test Point | ITP Signed | HP | Project Engineer |  |  | N/A
3.2 | Pile Integrity Testing |  | First six piles followed by every third pile thereafter. | All testing shall be undertaken by a prequalified consultant in accordance with the VicRoads scheme for prequalification and approval of the Superintendent. The consultant shall be independent of the piling contractor. Raw data of pile integrity testing shall be provided to the Superintendent within 48 hours of request of the Superintendent, | VR Section 606.07 | Test Point | ITP Signed | HP | Project Engineer/ Superintendent |  |  | N/A
3.3 | Concrete Cracking |  | Ad Hoc | The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures. | VR Section 610.24 | Visual Inspection | ITP Signed | IP | Project Engineer/ Superintendent / Technical Specialist
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent