## ITP-001
|  |  | Inspection and Test Plan - Rock Beaching | [7 empty] | Document # ITP-011
Client: Department of Transport & Planning |  |  |  | Construction Process: Rock Beaching |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 713 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Beaching / Rock Amour |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP | QMP, TMP, JSEA, SWMS, WP | Visual inspection | ITP Signed | HP* | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 | Materials |  | Prior to commencing any activity | Prior to the commencement of work, the Contractor shall nominate the source of the proposed materials, supply specified test results and provide a representative sample for approval by the Superintendent. Rock for Type 1 beaching shall consist of field or quarry rock. The rocks shall be uniform in colour. All rocks shall have a mass of between 20kg and 70kg and at least 60% by number shall be over 40kg. Rocks shall be of such size that the layer of beaching is not less than 225mm thick. | 713.03 | Test certificates, material data sheets and health and safety data sheets | ITP Signed | HP | Project Engineer/ Superintendent
1.3 | Submission of Safety Documentation |  | Prior to commencing any activity | The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review. | 713.05 | Job Safety Sheet, SWMS | ITP Signed | HP | Project Engineer/ Superintendent
2 | Construction Works
2.1 | Preparation of Underlying Surface |  | Each Lot | Surface compacted and trimmed to design levels. Scours filled with Class 4 crushed rock. No loose or soft spots. | Sec713.04 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Geotextile Placement |  | Each Lot | Nonwoven geotextile (>250 g/m²) laid evenly, buried 300 mm at edges, overlapped 300–500 mm, no folds or kinks. | Sec713.03(b) | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.3 | Placement of Type 1 Beaching |  | Each Lot | Rocks placed mechanically (≥12 kg), tightly interlocked, gaps ≤60 mm average, surface deviation ≤100 mm over 3 m straight edge. | Sec713.05 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.4 | Toe Wall Construction |  | Each Lot | Toe walls 600 mm x 600 mm, lined with geotextile, filled with hand-packed rock and smaller stones in voids. | Sec713.07 | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.5 | Topsoil Filling |  | Each Lot | Voids filled to mid-height with topsoil. Where planting is required, topsoil flush with rock surface and adjacent ground. | Sec713.05(b) | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent