## ITP-001
|  |  | Inspection and Test Plan - Anti-Graffiti Protection and Graffiti Removal | [7 empty] | Document # ITP-012
Client: Department of Transport & Planning |  |  |  | Construction Process: Anti-Graffiti Protection and Graffiti Removal |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 685 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Concrete Structures |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1
1.1 | Submission of materials and procedures |  | Prior to commencement | Superintendent must review and accept proposed coatings, removers, methods, and equipment. Evidence of product performance and test results (≤24 months old) must be provided. | Sec685 5.doc – Clause 685.04 | Document review | Approved submission | HP | Contractor / Superintendent
1.2 | Trial application of coating |  | 7 days before full-scale works | Coating must meet performance criteria: adhesion, thickness, appearance, and environmental compliance. Superintendent must approve trial outcome. | Sec685 5.doc – Clause 685.11 | Visual inspection and test panel | Trial report | HP | Contractor / Superintendent
1.3 | Surface preparation |  | Before coating | Surface must be free of graffiti, shadows, contaminants, and curing membranes. Must meet AS 1627.1 and AS 1627.4 standards. | Sec685 5.doc – Clause 685.05 | Visual inspection, solvent wash | Preparation checklist | WP | Contractor / Site Supervisor | N/A
1.4 | Environmental condition monitoring |  | Every 4 hours during application | Ambient temp: 10–35°C, RH ≤85%, substrate dry and ≥3°C above dew point. No windborne debris or rain spatter. | Sec685 5.doc – Clause 685.09 | Hygrometer / psychrometer readings | Environmental log | IP | Contractor / Site Supervisor | N/A
1.5 | Application of anti-graffiti coating |  | During works | Coating must be smooth, uniform, defect-free, and meet WFT ≥175 µm, DFT ≥100 µm. Must be compatible, UV-resistant, and impermeable to water, CO₂, and acid rain. | Sec685 5.doc – Clause 685.07 | Visual inspection | Coating records | WP | Contractor / Site Supervisor | N/A
1.6 | Testing of coating (bond strength, WFT, DFT, penetration) |  | Per 50 m² | Bond strength >0.75 MPa (AS 1580.408.5), WFT ≥175 µm (ASTM D4414), DFT ≥100 µm (AS 1580.108.2). Penetration must meet manufacturer specs. | Sec685 5.doc – Clause 685.12 | NATA lab testing | Test reports | TP | Contractor / NATA Lab | N/A
1.7 | Graffiti removal (maintenance or construction) |  | As required (within 24–48 hrs) | No visible markings on coated surfaces. Uncoated surfaces may retain shadows if not intelligible. Sensitive graffiti removed within 24 hrs. | Sec685 5.doc – Clause 685.18–19 | Approved cleaning methods | Removal report with photos | WP | Contractor / Site Supervisor | N/A
1.8 | Coating repairs and reinstatement |  | As needed | Repairs must restore original spec. Causes include yellowing, adhesion loss, colour change, graffiti penetration. | Sec685 5.doc – Clause 685.14–15 | Visual inspection | Repair records | WP | Contractor / Superintendent
1.9 | Final inspection and documentation |  | At completion | All records complete. Coating meets spec for appearance, thickness, adhesion, and durability. | Sec685 5.doc – Clause 685.13 | Inspection checklist | Final report | SCP | Contractor / Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent