## ITP-001
|  |  | Inspection and Test Plan - Fencing | [7 empty] | Document # ITP-013
Client: Department of Transport & Planning |  |  |  | Construction Process: Fencing Installation (CB10 Standard Balustrade) |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – 700, 717 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Fencing |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Service locating prior to excavation or post installation |  | Before any ground disturbance | All underground services identified and marked; clearance obtained from relevant authorities | Dial Before You Dig records, utility maps, project drawings, GPP | Visual confirmation of markings; review of service location reports | Service location report; clearance documentation | HP | Foreman / Contractor / Superintendent
1.2 | Supply of tubular steel posts and rails |  | Each delivery | Steel complies with AS 1074, AS/NZS 1163, AS 1397 or AS 1450; yield strength ≥ 195 MPa | Sec707 - Tubular Steel Posts, Rails and Stays | Material certification and visual inspection | Material certificates | IP | Contractor | N/A
1.3 | Galvanizing of steel components |  | Each batch | Hot dipped galvanized to AS/NZS 4680 or pre-galvanized to AS 1397 Z275 | Sec707 - Tubular Steel Posts, Rails and Stays | Visual inspection and coating thickness verification | Galvanizing certificate | IP | Contractor | N/A
1.4 | Repair of damaged galvanized coating |  | As required | Repaired using organic zinc-rich primer to AS 3750.9 | Sec707 - Tubular Steel Posts, Rails and Stays | Visual inspection and primer application check | Repair log | IP | Contractor | N/A
2 | Installation
2.1 | Installation of posts in concrete footings |  | Each installation | Footings comply with N20 concrete grade and specified dimensions | Sec707 - Steel Post and Welded Mesh Fences | Site inspection and measurement | Installation checklist | TP | Contractor | N/A
2.2 | Attachment of welded mesh panels |  | Each installation | Panels securely fixed with galvanized fittings | Sec707 - Steel Post and Welded Mesh Fences | Visual inspection and fitting verification | Inspection report | IP | Contractor | N/A
3 | Completion
3.1 | Submission of Certificate of Compliance |  | Prior to use | Certificate includes relevant test reports and product certification | Sec707 - Certificate of Compliance | Document review | Certificate of Compliance | IP | Contractor | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent