## ITP-xxx
|  |  | Inspection and Test Plan - Linemarking Works | [6 empty] | Document # ITP-014
Revision : 1
Client: Department of Transport & Planning |  |  |  | Construction Process: Stripping Topsoil, Clearing and Grubbing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 176, 201, 700, 720 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Construction footprint |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Redundant Linemarking Removal |  | Visual Inspection | Markings removed via approved method (jet blast/Black grit). No visible ghosting. | Jet blast or black grit spray minimum 20% wider than existing lines. | This ITP, Photographic record | HP | Superintendent
1.02 | Surface Preperation |  | Visual and manual check | Surface clean, dry, and dust free before application | Manual brooming, air blowing, and drying where needed. | Supervisor sign off | IP | Site Engineer | N/A
1.03 | Linemarking and RRPM set out |  | Measurement review | Set out conforms to drawings.Symbols in correct orientation and location. | Measure up, mark with paint/chalk, verify spacings as per plan. | This ITP, Photographic record | HP | Superintendent
1.04 | Linemarking Installation |  | Visual inspectioon, dry film thickness check, reflectivity. | Thickness per spec (≤2.0mm for thermoplastic), reflectivity to AS 1742. | Apply materials as per spec, black grit as required. | Thickness guage, luminance/reflectivity test records. | IP | Site Engineer | N/A
1.05 | RRPM installation |  | Visual inspection | Correct colour, spacing, aligned with edges/centrelines. | install with approved adhesive per manufacturer; must not be dislodged with hand pressure. | RRPM placement log with spacings and colour coding noted. | IP | Site Engineer | N/A
1.06 | Completion insoection - Linemarking & RRPMs |  | Joint inspections with superintendent | Works complete, complient, free from defects, overspray or misaligned markings. | Walkhrough audit with reference to drawings and spec. punch list created and rectifies if needed. | Final sign off form, defect rectification log if neededn | HP | Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent

## ITP-014
|  |  | Inspection and Test Plan - Linemarking Works | [7 empty] | Document DOT35734 - ITP 014
Revision : 00
Client: Department of Transport & Planning |  |  |  | Construction Process: Linemarking Works |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 721 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Civils |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman Contractor | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Construction Works
1.1 | Redundant Linemarking Removal |  | Prior to Commencing Work | Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence. | Vicroads Spec.721.A12 | Visual Inspection | Signed ITP | HP | Site Engineer / Superintendent / Contractor
1.2 | Surface Preperation |  | Prior to Commencing Work | Surface clean, dry, and dust free before application | Vicroads Spec.721.A06 | Visual Inspection | Signed ITP | HP* | Site Engineer / Foreman | N/A |  | N/A
1.3 | Linemarking and RRPM set out |  | Prior to Commencing Work | Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent | Vicroads Spec.721.B05 | Visual Inspection | Signed ITP | HP | Site Engineer/ Superintendent |  |  | N/A
1.4 | Linemarking Installation |  | Prior to Commencing Work | Thickness per spec (≤2.0mm for thermoplastic), reflectivity to AS 1742. | Vicroads Spec.720.07 | Visual inspectioon, dry film thickness check, reflectivity. | Thickness guage, luminance/reflectivity test records. | HP* | Site Engineer | N/A |  | N/A
1.5 | RRPM installation |  | Prior to Commencing Work | Correct colour, spacing, aligned with edges/centrelines. | Relevant EMP | Visual inspection | RRPM placement log with spacings and colour coding noted. | HP* | Site Engineer | N/A |  | N/A
1.5 | Completion insoection - Linemarking & RRPMs |  | Prior to Commencing Work | Works complete, complient, free from defects, overspray or misaligned markings. | Relevant EMP | Joint inspections with superintendent | Final sign off form, defect rectification log if neededn | HP* | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent