## ITP-018
|  |  | Inspection and Test Plan - Landscaping | [7 empty] | Document DOT35734 - ITP 018
Revision : 00
Client: |  | DTP |  | Construction Process: Landscaping |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Skenes Creek Bridge Strengthening & Associated Works |  | Specifications: VicRoads Standard Specification – Section 720 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: |  | DOT35734 |  | Structure / Component: Landscaped areas |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Project Wide |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman Contractor | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Supply of plant stock and materials |  | Each delivery | Complies with AS 2303 and VR 720 | Sec720.03 & Sec720.04 | Visual inspection; certification review | Inspections, samples & records as per 720.03, 720.04 | IP | Site Engineer | N/A
1.2 | Site ripping, topsoil application, and cultivation verification |  | Before mulching or planting | Ripping depth, topsoil depth, and cultivation meet specifications outlined in table 720.071 | Sec720.07(b)-(e) | Site inspection; visual inspection | Superintendent signature | HP, WP | Site Engineer / Superintendent
2 | Construction Works
2.1 | Planting of trees and shrubs |  | Each planting event | Planting holes, staking, and watering meet specification | Sec720.09 | Site inspection | Photographic evidence | IP | Site Engineer | N/A
2.2 | Grassing with Type 1 and Type 2 seed |  | Each sowing event | Seed mix, sowing rate, and fertilising meet specification | Sec720.10 | Visual inspection | Photographic evidence | IP | Site Engineer | N/A
2.3 | Landscape maintenance |  | Ongoing during defect liability period | Accepted maintenance program, joint inspections carried out and plant performance is in accordance with Sec720.11 | Sec720.11 | Routine inspections; performance verification | Maintenance program; quarterly joint inspections | IP, WP | Site Engineer | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent