## 1145-C200-FUL-QAC-ITP-0001
|  |  | Inspection and Test Plan - Bridge Deck Waterproofing | [7 empty] | Document DOT35734 - ITP 022
Client: Department of Transport & Planning |  |  |  | Construction Process: Bridge Deck Waterproofing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 691 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Bridge Deck |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Skenes Creek |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman Contractor | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Material Conformity |  | Prior to Commencing Work | Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent. | VicRoads Spec.691.04 | Document review | Signed ITP | HP | Site Engineer / Superintendent |  |  | N/A
1.2 | Work Method Statement, ITPs, Test Plans |  | Prior to Commencing Work | The Contractor shall not proceed with the trial system application or the permanent waterproofing membrane system installation works until the WMS and ITPs have been reviewed and approved by the Superintendent. | VicRoads Spec.691.25 | Document review | Signed ITP | HP | Site Engineer / Superintendent |  |  | N/A
2 | Construction Works
2.1 | Trial Application |  | Prior to full scale waterproofing works | The Contractor shall not proceed with the full scale waterproofing works until the trial waterproofing membrane application has been carried out and the outcomes reviewed and approved by the Superintendent. | VicRoads Spec.691.16 | Visual Inspection | Signed ITP | HP | Site Engineer / Superintendent |  |  | N/A
2.2 | Application |  | During application | No spray application of liquid applied membrane shall be carried out within ten (10) metres of buildings, footpaths, roadways, pedestrians or vehicles without protective measures or methods being used which shall be submitted to the Superintendent for approval, a minimum of two working days in advance of the proposed works. | VicRoads Spec.691.26 | Visual Inspection | Signed ITP | HP | Site Engineer / Superintendent |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent