## ITP-003
|  |  | Inspection and Test Plan - Bridge Expansion Joints | [7 empty] | Document # ITP-020
Client: Department of Transport & Planning |  |  |  | Construction Process: Construction of Bridge Expansion Joints |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 660 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Pedestrian Bridge |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Skenes Creek, Great Ocean Road |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Engineer/ Works Supervisor | N/A |  | N/A
1.2 | Materials |  | Prior to commencing any activity | The Contractor shall submit proposals for joints and their installation (including items (b) to (f) listed below) to the Superintendent for review within four weeks of acceptance of tender The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations | Design Drawings, VR Section 660 | Visual inspection | ITP Signed | HP | Engineer/ Works Supervisor / Superintendent |  |  | N/A
1.3 | Alternative Designs |  | Prior to commencing any activity | If an alternative bridge expansion joint is proposed it shall be designed in accordance with Bridge Technical Note 1999 002 Design of deck joints for road bridges, in conjunction with the requirements of the AS 5100, the Australian Standard for bridge design. The Contractor shall submit proposals for joints and their installation (including items (b) to (f) listed in 660.03) to the Superintendent for review within four weeks of acceptance of tender. | VR Section 660.03 | Document Review | ITP Signed | HP* | Engineer/ Works Supervisor | N/A |  | N/A
2 | Construction Works
2.1 | Joint Installation |  | Prior to install | Expansion joint gaps shall be designed and dimensioned for installation at a mean temperature of 20C. In the event that the ambient temperature differs from 20C by more than 5C, it may be necessary to vary the joint gap. The Contractor shall seek a direction from the Superintendent and shall vary the joint-gap if required | VR Section 660 | Temperature reading taken | ITP Signed | HP* | Site Engineer/ Superintendent | N/A |  | N/A
2.2 | Installation Tolerances |  | Each Lot | The following tolerances shall apply to joint installation: (a) joint gap +-3 mm (b) deviation from plan alignment 5 mm maximum over the total length of the joint (c) the top surface of the joint shall be level with the adjacent road surface with a tolerance of 0 to -2 mm when measured with a 2.5 m straight edge at 90º to the joint | VR Section 660.04 | Visual Inspection / measurement taken | ITP Signed | HP* | Project Engineer/ Supervisor | N/A |  | N/A
2.3 | Pre-pour inspection |  | Each Lot | Prior to casting deck concrete, the Contractor shall ensure that there is no conflict between the joint anchors, the deck reinforcement and any embedment. Where conflict does occur, the Contractor shall submit proposals for resolving the conflict to the Superintendent. Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer. | VR Section 660.04 | Visual Inspection | ITP Signed, ITC Complete | HP* | Project Engineer/ Supervisor | N/A |  | N/A
2.4 | Post Concreting Inspection |  | Each Lot | After concreting and prior to installation of the joint seal, the vertical face of the concrete under the full length of the joint shall be inspected for the presence of voids and other imperfections. If voids are discovered, the Contractor shall remove the affected section of the joint to enable a full inspection of the concrete and shall submit proposals for repair to the Superintendent. Following completion of the joint assembly and tensioning of all anchor bolts, the full length of the joint shall be tested by tapping with a hammer. Should any part of the joint exhibit a hollow-ring or movement, the affected length shall be removed and re-bedded and all bolts replaced and re-tensioned. If the concrete under the joint is found to have voids or other imperfections or any of the anchor bolts are not properly restrained, the Contractor shall submit proposals for repair to the Superintendent. | VR Section 660.04 | Visual Inspection | ITP Signed | HP* | Project Engineer/ Supervisor / Contractor | N/A
2.5 | Tensioining Anchor Bolts |  | Each Lot | Not later than two weeks prior to installation of the bridge joint, the Contractor shall submit proposals for tightening of anchor bolts to the Superintendent. The Contractor shall supply a copy of the torque-wrench calibration certificate to the Superintendent on request. Anchor bolt tensioning records shall be maintained by the Contractor and supplied to the Superintendent on completion of installation. If the required tension cannot be achieved, the Contractor shall submit proposals to the Superintendent for rectification of the defect. | VR Section 660.04 | Data Record | ITP Signed, Record of Data | HP | Project Engineer/ Supervisor / Superintendent
2.6 | Compression Seals, Inserts and membranes |  | Each Lot | Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint including footpaths and barriers. If seals are bonded to the nosing, the surface shall be prepared and primed and the adhesives placed in accordance with the supplier’s recommendations. Completed joints shall be watertight. | VR Section 660.04 | Visual Inspection | ITP Signed | HP* | Project Engineer/ Supervisor / Superintendent | N/A
2.7 | Trafficking of Joints During Construction |  | Each Lot | If the joint or any of its component parts is damaged during construction, the Contractor shall repair the damage to the satisfaction of the Superintendent or replace the joint. | VR Section 660.04 | Visual Inspection | ITP Signed | HP* | Project Engineer/ Supervisor | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent