## ITP-003
|  |  | Inspection and Test Plan - Fabrication of Super-T Beam | [7 empty] | Document # ITP-021
Client: Department of Transport & Planning |  |  |  | Construction Process: Fabrication of Super-T Beam |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Skenes Creek Bridge Strengthening & Associated Works |  |  |  | Specifications: VicRoads Standard Specification – Section 622 |  | Name: | Jonathan Rau | Name: | Jarrod Rodrigues |  | Name: | Greg Grima
Contract No: DOT35734 |  |  |  | Structure / Component: Pedestrian Bridge |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Skenes Creek, Great Ocean Road |  | Date : | 2025-09-09 | Date : | 2025-09-10 |  | Date : | 2025-09-11
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings. | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Engineer/ Works Supervisor | N/A |  | N/A
1.2 | Materials |  | Prior to commencing any activity | Ensure correct concrete mix being used in accordance with design drawings and specifications. Approved Mix: V75V26AL Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. The Contractor shall submit the following for the material in each coil of wire or strand: • test certificates for tensile testing • load-extension graphs together with: • the manufacturer's certificate of compliance of the tendon material with the Australian Standard • a stress-relaxation test certificate for material taken from the same production facility and of the same type of material as that proposed for use in the works (stress relaxation-test certificates for similar tendons produced within the calendar year prior to the proposed use will be accepted) to the Superintendent at least seven days prior to the delivery of the coil or lot to its place of use. | Design Drawings, VR Section 620 | Document Review | ITP Signed, Test Certificates, Material Data Sheets. | HP* | Engineer/ Works Supervisor | N/A |  | N/A
1.3 | Calibration of Prestressing Equipment |  | Prior to commencing any activity | The Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range. | VR Section 622.06 | Document Review | ITP Signed, Calibration Certificates | HP* | Engineer/ Works Supervisor | N/A |  | N/A
1.4 | Submission of proposed method of transfer of prestress |  | Prior to commencing any activity | Ensure submission of the details of the proposed method of transfer of prestress to the Superintendent for review. | VR Section 622.08 | Document Review | ITP Signed | HP | Engineer/ Superintendent |  |  | N/A
1.5 | Notification of stressing operations |  | Prior to commencing any activity | The Superintendent shall be given seven days notice of stressing operations. All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer. | VR Section 622.06 | Document Review | ITP Signed | HP | Engineer/ Superintendent |  |  | N/A
2 | Construction Works
2.1 | Forms |  | Each Lot | Forms shall be manufacutred from steel, except where otherwise approved by the Superintendent. The formwork shall be constucted to as to produce a product in accordance with the design drawings, and with the surface finish and tolerances specified in Section 610. Casting bed to be inspected by designated Precast Concrete Surveillance Officer. | Design Drawings , VR Section 620, 610. | Visual inspection | ITP Signed | HP* | Project Engineer | N/A |  | N/A
2.2 | Stressing operations |  | Each Lot | All stressing operations shall take place in the presence of the designated Precast Concrete Surveillance Officer. | VR Section 622.06 | Visual Inspection | ITP Signed | HP* | Project Engineer/ Supervisor | N/A |  | N/A
2.3 | Pre-pour inspection |  | Each Lot | Ensure the completion of the Inspection Test Checklist (ITC) by the designated Precast Concrete Surveillance Officer. | VR Section 622.06 | Visual Inspection | ITP Signed, ITC Complete | HP* | Project Engineer/ Supervisor | N/A |  | N/A
2.4 | Data to be recorded |  | Each Lot | Ensure the following data is recorded and forwarded to the Superintendent prior to delivery of the pre-stressed units to the site: • ID No. of each unit • ID No. of prestressing equipment • Calibration certificates for prestressing equipment • ID No. for each tendon • Sag take-up force: • Elongation at take-up force: • Obtained elongation at completion of tensioning: • Obtained tendon force at completion of tensioning: • Elongation after release of jack: • Tendon pull-in: • Compressive strength of concrete at time of transfer of prestress: • Steam curing charts • Hog measure following transfer of prestress: | VR Section 622.09 | Data Record | ITP Signed, Record of Data | HP | Project Engineer/ Supervisor / Superintendent
2.5 | Projecting reinforcement |  | Each Lot | Ensure projecting reinforcement is in accordance with that shown on the design drawings and is in good condition. | VR Section 620.03 | Visual inspection | ITP Signed | HP* | Project Engineer/ Superintendent | N/A |  | N/A
2.6 | Marking |  | Each Lot | Ensure the identification number, date of casting, the manufacturuers name or registered mark and the maximum mass shall be marked on every precast unit. | VR Section 620.06 | Visual inspection | ITP Signed / Certificate of Compliance - Formwork Inspection | HP* | Project Engineer | N/A |  | N/A
2.7 | Handling & Storage |  | Each Lot | The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit. | VR Section 620.07 | Visual inspection | ITP Signed | HP* | Project Engineer/ Superintendent | N/A |  | N/A
2.8 | Transporting |  | Each Lot | Units shall not be transported from the precast yard until specified 28 day concrete compressive strength has been achieved, and not before 7 days after casting. No beam shall be transported and erected if it has a bow in excess of 1 in 400 of the length or 75mm whichever is the lesser. Should the bow at any time exceed the maximum allowable limit steps shall be taken to ensure the safety of the unit throughout the journey. | VR Section 610.14 | Visual inspection | ITP Signed, Concrete Test Reports | HP* | Project Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent