## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Stripping Topsoil Clearing and Grubbing | itp |  |  |  |  | ITP-001 - Stripping Topsoil Clearing and Grubbing
section | 1 - Preliminary Works
checkpoint | 1.1 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Ground Penetration Permit (GPP) issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current GPP signed and specific for the area where works will be executed. Services in the work area are identified
label | REFERENCE DOCUMENTS: Vicraods Spec.700.1, GPP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Extent of Clearing and Grubbing
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
label | REFERENCE DOCUMENTS: Project Spec. 176.I1 & Vicroads Spec.201
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Extent of Clearing and Grubbing reviewed by Superintendent
label | HP
label | RESPONSIBILITY: Site Engineer/Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Extent of Clearing and Grubbing
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: The Contractor shall obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
label | REFERENCE DOCUMENTS: Vicroads Spec.720.07
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Copy of issued permits
label | HP
label | RESPONSIBILITY: Site Engineer/Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Identification of Cultural Heritage sites and areas of Cultural Significance
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Immediately stop work and notify the Superintendent if any Cultural Heritage is discovered or identified during construction.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | REFERENCE DOCUMENTS: Relevant EMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Cultural Heritage approval (when required), Signed ITP
label | HP*, AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Stripping of topsoil and grubbing of vegetation
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | ○ In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | REFERENCE DOCUMENTS: VicRoads Specification 201.05
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Removal of abandoned services
label | FREQUENCY: Prior to commencing this work
label | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done.
label | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | ○ Decommissioned services to be disposed of in a suitable manner.
label | ○ Decommissioned pits have been broken back to 0.3 metres below subgrade level.
label | ○ Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%
label | REFERENCE DOCUMENTS: VicRoads Specification 201.05
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Clearing of Trees and Vegetation
label | FREQUENCY: During clearing works
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified and approved limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed by a suitably qualified arborist to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | REFERENCE DOCUMENTS: VicRoads Specification 201.04
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Disposal of vegetation
label | FREQUENCY: At completion of works
label | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from the site.
label | ○ Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | ○ Disposal of noxious weeds shall be in acordance with the CaLP permit
label | REFERENCE DOCUMENTS: VicRoads Spec. 201.07, CaLP Permit
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-002 - Pavement Excavation & Subgrade Prep | itp |  |  |  |  | ITP-002 - Pavement Excavation & Subgrade Prep
section | 1 - Preliminaries
checkpoint | 1.1 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, Site Induction
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Coordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Excavation Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Excavation
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | ○ The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl.204.03
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Site Excavation
label | FREQUENCY: Prior to (and during) Excavation of any new areas
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.06(c)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area reviewed by Superintendent and Contractor, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Ground water
label | FREQUENCY: Prior to Construction of Subbase Layer
label | ACCEPTANCE CRITERIA: Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.06(h)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior to Construction of Subbase Layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ The Contractor shall submit details of any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces to the Superintendent for review.
label | ○ No adjustment to the Contract Sum will be considered for the treatment of a rock subgrade, or for the construction of the regulating layer in lieu of capping or selected material, or for any modifications to the subsurface drainage.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Proof Roll - Cut Floor
label | FREQUENCY: Prior to Construction of Subbase Layer
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
label | ○ Superintendent to be present during all test rolling.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | ○ No fill or subbase materials are to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | ○ Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | ○ Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.12, Cl.173.03, Cl. 204.10(b), Cl. 204.07(d), Cl.204.11
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area visually reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Survey Pickup
label | FREQUENCY: Prior to Construction of Subbase Layer
label | ACCEPTANCE CRITERIA: Ensure the Cut Floor Level is recorded by survey
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Survey As-Built
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.7 - Re-Use of insitu material
label | FREQUENCY: Prior to Placing fill
label | ACCEPTANCE CRITERIA: If exacavated material is to be reused as Type A or B material, the Superintendent and the Contractor shall inspect the material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
label | ○ Type B Material shall meet the following requirements:
label | — CBR ≥ 1.5%
label | — Swell < 2.5%.
label | ○ Attach: Test Certificates
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 204.04, Cl. 204.06
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results, Material Category agreed with Superintendent
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-003 - Unbound Flexible Pavement Construction | itp |  |  |  |  | ITP-003 - Unbound Flexible Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most up-to-date revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and Drawings Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: VicRoads Spec. 812.03
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Mix Design Approval
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented before commencing work, that is: EMP, ECP, QMP, SWMS.
label | REFERENCE DOCUMENTS: IFC Drawings EMP, ECP, ERA, QMP, SWMS.
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints.
label | ○ Transverse joints shall be offset from one layer to next by not less than 2 metres
label | ○ Transverse joints shall be offset from one layer to the next by not less than 2 m.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a, b & c)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints.
label | ○ longitudinal joints shall be offset from one layer to the next by not less than 150 mm.
label | ○ longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a, d & e)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser.
label | ○ For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii & iv) Table 304.111
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Layer Thickness
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150mm and the maximum thickness of any subbase layer shall not exceed 200mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.09
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: Proof roll each layer
label | ACCEPTANCE CRITERIA: The Contractor shall provide for the Superintendent to be present during all test rolling.
label | ○ No visible deformation or spinging in presence of Superintendent's representative.
label | ○ Proof rolling plant to comply with requirements of Cl. 173.03.
label | ○ The placement of the Upper Base Layer shall not proceed until the Superintendent is satisifed with the release of this Hold Point.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173, Cl.304.09
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP/ WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Specification Table 204.161
label | ○ VicRoads Specification Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Modified Compactive Effort
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B.
label | ○ For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Permeability Testing
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec
label | ○ Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
label | REFERENCE DOCUMENTS: Project Specification Cl.3040.05(a) Table 3040.051
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Post-compaction Plasticity Index
label | FREQUENCY: After compaction
label | ACCEPTANCE CRITERIA: Post- compaction Plasticity Index must comply with the requirement of table 3040.053. Calss 3: 0 < PI < 10.
label | REFERENCE DOCUMENTS: Project Specification Cl.3040.05(a) Table 3040.053
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Post- compaction Grading
label | FREQUENCY: After compaction
label | ACCEPTANCE CRITERIA: The post compaction grading shall comply with the requirements of table 304.101
label | REFERENCE DOCUMENTS: VicRoads Specification Cl. 304.10 Table 304.101
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.7 - Survey Level
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Scale A:
label | — Minimum number of measurements per lot: 80 For Upper
label | — Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm
label | — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm.
label | — Base: Mean ± 5 with a maximum Standard Deviation of 8mm.
label | REFERENCE DOCUMENTS: VicRoads Specification Table 304.061, Table 304.062
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-004 - Underground Stormwater Drainage | itp |  |  |  |  | ITP-004 - Underground Stormwater Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most up-to-date set of drawings.
label | REFERENCE DOCUMENTS: IFC Drawings, Drawing Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, TMP, OHSCP, SWMS.
label | REFERENCE DOCUMENTS: QMP, EMP, ECP, TMP, OHSP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Pit & Pipe Compliance
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: A complying test Certificate shall be provided to the Superintendent at least 5 days prior to installation, certifying that pit access covers have been tested and certified by a NATA accredited laboratory as complying with the requirements of AS 3996 and DTP.
label | ○ Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058.
label | ○ Drainage Pits are supplied in accordance with 705.07.
label | REFERENCE DOCUMENTS: VicRoads Spec 705.04, 701.04, 701.05, 705.07
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP, IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Drainage Bedding Material
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Bedding Materials comply with Table 701.081 and 701.082.
label | ○ Material Approved by client.
label | REFERENCE DOCUMENTS: Table 701.081, Table 701.082
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Drainage Backfill Material
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082
label | ○ Material Approved by client.
label | REFERENCE DOCUMENTS: Table 701.081, Table 701.082
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Material Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Material inspection to be completed for all precast pits, pipes, beaching and culverts.
label | REFERENCE DOCUMENTS: Order Acceptance Form
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
checkpoint | 1.7 - Ground Penetration Permit (GPP) issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
section | 2 - Installation of Drainage
checkpoint | 2.1 - Confirm position of culverts
label | FREQUENCY: Prior to commencing drainage line
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts and stormwater drainage, confirm the position with the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.10 IFC Drawing
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Design and survey setout postion confirmed with Superintendent.
label | HP
label | RESPONSIBILITY: Engineer / Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation
label | FREQUENCY: Each trench
label | ACCEPTANCE CRITERIA: Ensure trench is excavated to prepare culvert foundation and specified depth of bedding.
label | ○ Pipe culverts: the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm.
label | ○ Pits: Clearance from external faces of the pit to each face of the excavation to be not less than 400mm
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.15 Table 701.151, Cl. 705.05(b)
label | INSPECTION/TEST METHOD: Site Inspection, Measurements of trench
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each trench
label | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be:
label | — minimum 100mm for pipes of D< 1500mm
label | — minimum 200mm for pipes with D ≥ 1500 mm
label | ○ 'D' is the nominal pipe diameter or culvert width.
label | ○ Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | ○ Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height.
label | ○ Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.16, Cl. 701.20(a)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Report
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.4 - Laying of Pipes
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream)
label | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | ○ Where applicable, the top of the pipe as marked shall be within five degrees of the vertical axis of the culvert.
label | ○ Spacing of multiple rows of culverts to reflect Table 701.171.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.17(b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.5 - Jointing
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Rubber Ring Joints (RRJs) jointed with rubber rings which have been kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
label | ○ RRJs assembled and prepared in accordance with the manufacturer’s recommendations.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.18
label | INSPECTION/TEST METHOD: Document review/ Site Inspection
label | RECORD OF CONFORMITY: Manufacturer’s recommendations, ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.6 - Survey
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The location of each run of underground drainage has been verified by a survey pickup prior to backfill and form the as constructed survey.
label | Tolerances that apply:
label | (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm
label | (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm
label | (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade.
label | (d) Departure from design grade of pipe runs +/-10mm in 10m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.701.10
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey Report
label | SCP
label | RESPONSIBILITY: Engineer / Surveyor
date | Date Completed:
checkpoint | 2.7 - Backfilling
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Culvert Under Area to be Paved:
label | — Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | — Where the trench is excavated from below design subgrade level the trench is filled with selected backfill material.
label | ○ Culvert Under Area not to be Paved:
label | — The trench is backfilled with selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.19(a)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Construction of Rock Apron at Concrete Headwalls
label | FREQUENCY: Each Headwall
label | ACCEPTANCE CRITERIA: Rock for Type 1 beaching shall consist of field or quarry rock.
label | ○ All rocks shall have a mass of between 20 and 70 kg and at least 60% by number shall be over 40 kg. Rocks shall be of such size that the layer of beaching is not less than 225 mm thick.
label | ○ Rock apron to be installed as per design drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec. 703
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing and Inspection
checkpoint | 3.1 - Inspection of Drainage Lines (CCTV)
label | FREQUENCY: Each culvert prior to construction of pavement layers
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisaiton using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.30
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Inspection Report, ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Repairs to Damaged Pipes
label | FREQUENCY: As Required
label | ACCEPTANCE CRITERIA: The Contractor shall submit details of proposed rectification treatments including manufacturer's product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | ○ No repairs shall be undertaken without the Superintendent's approval of the repair materials and procedures.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.31
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Latest IFC Drawing, ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Bedding Compaction Requirements
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding assessed for compaction and /or moisture in lots.
label | ○ Bedding compacted to refusal with handheld mechanical equipment with a mean moisture ratio of 92%.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.20 (a)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction and moisture Test Records, ITP signed
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.4 - Backfill Compaction and Moisture requirements
label | FREQUENCY: 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls)
label | ○ Min. 20% of all lots for each culvert shall be tested.
label | ACCEPTANCE CRITERIA: Backfill assessed for compaction and or moisture in lots.
label | ○ Backfill material which will have a nominal size after compaction of 40mm or < less compacted to a mean value of density ratio of not less than 97%.
label | ○ Backfill material which has a swell equal to or greater > than 2.5% maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: VicRoads Spec. 701.20 (b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compaction and moisture Test Records, ITP signed
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.5 - Flushing System
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Each culvert flushed clean from end to end on completion and maintained in proper working order.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 701.28
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-005 - Subsurface Drainage | itp |  |  |  |  | ITP-005 - Subsurface Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, EMP, ECP, ERA, SWMS
label | REFERENCE DOCUMENTS: QMP, EMP, ECP, ERA, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Submission of Quality Procedures
label | FREQUENCY: Prior to works commencing
label | ACCEPTANCE CRITERIA: Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete. The method of compaction shall be in accordance with the Contractor's quality procedures
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
label | ○ No Fines Concrete: No fines concrete shall consist of Type GP cement, water and coarse aggregate. The quantity of cement used shall be 4.0% by volume. Type GP Cement, water and coarse aggregate shall comply with the requirement of Section 703.
label | ○ Geotextiles: Shall comply with Cl 702.06.
label | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: Constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: VicRoads Spec 702.04, 702.05, 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey and Set Out
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Subsurface drains, whether pipe or geocomposite systems, shall be constructed true to line, level and depth, as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
label | ○ The base of the trench shall be inspected by the Superintendent prior to placing bedding in completed excavations.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (c )
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
label | ○ No-fines concrete is to be placed and compacted within one hour of mixing and is to be compacted in accordance with the approved quality procedure.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.6 - Compaction of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.9
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: VicRoads Spec 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.9 - CCTV
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec 702.09(i)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-006 - General Concrete Paving | itp |  |  |  |  | ITP-006 - General Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | REFERENCE DOCUMENTS: 610.07(b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Mix design approval
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: If Required
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | REFERENCE DOCUMENTS: 703.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
label | — Pavement Type 5 Footpath: 100mm layer of 20mm Class 3 Crushed Rock
label | — Pavement Type 6 Concrete Median: 100mm layer of 20mm Class 3 Crushed Rock
label | — Pavement Type 7 Concrete Path: 100mm layer of 40mm Class 3 Crushed Rock
label | REFERENCE DOCUMENTS: Cl 703.21 Design Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: 703.12, AS 3610
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All steel reinforcement used shall be:
label | — Pavement Type 5 Footpath: SL72 Steel Mesh
label | — Pavement Type 6 Concrete Median: SL72 Steel Mesh
label | — Pavement Type 7 Concrete Path: SL82 Steel Mesh
label | ○ Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
label | REFERENCE DOCUMENTS: AS/NZS 4671
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Concrete Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete shall be thoroughly compacted via continuous tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken intial set, a properly formed construction joint must be used.
label | REFERENCE DOCUMENTS: Cl 703.08
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.7 - Surface Finish
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanenelty hidden surfaces in accordance with AS3610/
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Expansion joints shall be placed at intervals not exceeding 10 m, on either side of vehicle crossings, at junctions with existing footpaths and shared use paths, at junctions with bridges and around all abutting structures such as pits, utility services, power poles, kerbs and other such features.
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-007 - Hot Mix Asphalt | itp |  |  |  |  | ITP-007 - Hot Mix Asphalt
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Designs
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The Contractor shall submit the details of the trackless tack coat or tack coat application system proposed to be used in the works.
label | ○ All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport and Planning as ‘General’, unless otherwise approved by the Department of Transport and Planning. The registration for all mixes incorporated into the works shall be current at the time of their use. The Contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.08, Cl.407.09
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval, ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.14, AS2150 10.1, AS2150 10.3, Completed ITP-008/009
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | ○ If specified temperatures are unachievable, prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer reading
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.17 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | ○ Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the design rates of application to those provided under clause 408.13(a).
label | (Sprayed Bituminous Surfacings only)
label | ○ Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the design rates of application to those provided under clause 408.13(a).
label | REFERENCE DOCUMENTS: VicRoads Spec 407.18, 408.04
label | INSPECTION/TEST METHOD: Visual Inspection, Written Confirmation
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.16 Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.3 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: VicRoads Spec 407.20 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | ○ Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(i), 407.29
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP, HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: VicRoads Spec. 407.23 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: VicRoads Spec 407.23 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | — 94.0% or greater Accept lot
label | — 91.0% to 93.9% Lot may be accepted at reduced rate
label | ○ For layers ≥50mm, if characteristic thickness is:
label | — 96.0% or greater Accept lot
label | — 91.0% to 95.9% Lot may be accepted at reduced rate
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.232
label | INSPECTION/TEST METHOD: String Sheet
label | RECORD OF CONFORMITY: Survey Conformance
label | SCP
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-008 - Drilling and Setting of Dowel Bars | itp |  |  |  |  | ITP-008 - Drilling and Setting of Dowel Bars
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the complete set of the correct and most current drawings.
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | REFERENCE DOCUMENTS: Health and Safety Coordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current EMP & ECP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, ECP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Ground Penetration Permit (GPP) issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current GPP signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: GPP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Set Out
label | FREQUENCY: Prior to Drilling
label | ACCEPTANCE CRITERIA: GPR Scan concrete deck to locate the upper bent of the existing shear ligatures of the existing RC beam. The scan shall mark also the deck reinforcement on top of concrete deck.
label | ○ Spacing of dowel bars can be adjusted by 25mm from specificied locations in the drawings to avoid cutting existing bars.
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION/TEST METHOD: Document Review & Site Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Drilling of Pilot Hole
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Drill an initial pilot hole 10mm nominal diameter at specified location from beam end. If reinforcement encountered, stop drilling immediately and attempt another pilot hole approximately 25mm longitudinally and laterally away from the first pilot hole in parallel direction to the existing beam. If reinforcement is still encountered, use the same offsets in the opposite direction until a clear hole is obtained.
label | ○ A succesful pilot hole is obtained when a 150mm drill hole does not enounter reinforcement. Once a successful pilot hole is obtained, drill hole to required depth and diameter shown on the drawings and use for the first dowel bar.
label | REFERENCE DOCUMENTS: Design IFC Drawings, Dowel Hole Drilling Procedure
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Drilling of Dowel Holes
label | FREQUENCY:
label | ACCEPTANCE CRITERIA: Locate subsequent drill holes in the same longitudinal alignment as first dowel bar. If reinforcement is encountered, repeat procedure stated in item 2.2.
label | ○ Use percussion drills only for dowel hole. Coring is strictly prohibited.
label | REFERENCE DOCUMENTS: Design IFC Drawings, Dowel Hole Drilling Procedure
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Cleaning of Holes
label | FREQUENCY:
label | ACCEPTANCE CRITERIA: Ensure all holes are cleaned in accordance with the manufacturer's installation instructions. This must include the following as a minimum:
label | ○ Air flush twice at the specified pressure.
label | ○ Brush clean twice.
label | ○ Air flush twice at the specified pressure.
label | ○ Fingertip test the hole surface for dust, and if dust is still present, brush clean and air-flush until all dust is removed. Ensure hole is clean and free of debris, dust particles, oils and other contaminants over its full depth.
label | REFERENCE DOCUMENTS: VicRoads Spec. 680.08 Manufacturer's Specification
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 2.2 - Trial Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to proceeding with the installation of all dowels bars, the trial system installation shall be witnessed by the superintendent and the outcomes reviewed and approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. 680
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.3 - Installation of Dowels Bars
label | FREQUENCY: Prior to commencing this work
label | ACCEPTANCE CRITERIA: Ensure materials being used are in accordance with standard specifications and design drawings.
label | ○ Installation to be undertaken in accordance with manufacturer's specifications.
label | ○ Seal all unused drill holes prior to constructiing deck concrete by filling with 'Hilti' HIT-RE 500 as per manufacturer's specifications.
label | REFERENCE DOCUMENTS: Manufacturer's Specification, Design IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-009 - Bored Cast-In-Place Piles (Temp Casing) | itp |  |  |  |  | ITP-009 - Bored Cast-In-Place Piles (Temp Casing)
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS, CMS, ECP, CASS MP.
label | REFERENCE DOCUMENTS: QMP, TMP, SWMS, CMS, ECP, CASS MP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.3 - Excavation Permit Issued
label | FREQUENCY: 4 weeks prior to commencement
label | ACCEPTANCE CRITERIA: The Contractor shall submit for review by the Superintendent a quality procedure / work method statement for the construction of the piles not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Sec.610.18 Quality Procedure
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Excavation Permit Issued
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for to the area where works will be execxuted.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS.
label | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
label | ○ Ensure that materials on-site are sufficient for the completion of works.
label | REFERENCE DOCUMENTS: Design Drawings, VicRoads Standard Section 610 & 611
label | INSPECTION/TEST METHOD: Visual Inspection/ Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Indentification of Services
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure any underground service locations have been identified and marker on-site. Ensure any required approvals/permits have been received by service authorities prior to commencing works.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Concrete Blinding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Data
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Set Out of Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Data
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.4 - Protection of Adjacent Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained the strength of 15 Mpa.
label | REFERENCE DOCUMENTS: VR Section 608.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Geotechnical Supervision
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The construction of the bored piles shall be carried out in the presence of a geotechnical engineer with appropriate experience to confirm that the founding materials at the piling locations are of a strength to satisfy the design assumptions. The geotechnical engineer engaged by the contractor shall be independent of the piling sub-contractor.
label | REFERENCE DOCUMENTS: Design Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Inspection of Pile Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | REFERENCE DOCUMENTS: VicRoads Section 606.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Geotechnical Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Casting Piles
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Section 606.06 (a)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Casting Under Water
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete placed under water shall be self compacting concrete (SCC) in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c).
label | ○ The outlet of the tremie pipe or pump discharge hose shall not be lifted from the bottom of the hole until the hole has been filled with a minimum of 2m depth of concrete. Thereafter, concreting shall be kept a minimum of 2m below the top surface of the concrete at all times and the Contractor shall continuously monitor and ensure that the 2m depth of embedment is to be maintained at all time.
label | REFERENCE DOCUMENTS: VicRoads Section 606.06 (b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 2.9 - Placement of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall not be placed in bored piles, under water or in a dry bore until the propose method of placement of concrete has been approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Section 610.18
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Quality Control Testing
checkpoint | 3.1 - Concrete Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All testing shall be undertaken by a prequalified consultant in accordance with the VicRoads scheme for prequalification and approval of the Superintendent. The consultant shall be independent of the piling contractor. The contractor shall provide details of the pile testing consultant to the Superintendent for review at least 2 weeks prior to the testing.
label | REFERENCE DOCUMENTS: VR Section 610.16
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Pile Integrity Testing
label | FREQUENCY: First six piles followed by every third pile thereafter.
label | ACCEPTANCE CRITERIA: All testing shall be undertaken by a prequalified consultant in accordance with the VicRoads scheme for prequalification and approval of the Superintendent. The consultant shall be independent of the piling contractor.
label | ○ Raw data of pile integrity testing shall be provided to the Superintendent within 48 hours of request of the Superintendent,
label | REFERENCE DOCUMENTS: VR Section 606.07
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Concrete Cracking
label | FREQUENCY: Ad Hoc
label | ACCEPTANCE CRITERIA: The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
label | REFERENCE DOCUMENTS: VR Section 610.24
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Superintendent / Technical Specialist
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-010 - Construction of Structural Concrete | itp |  |  |  |  | ITP-010 - Construction of Structural Concrete
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct, complete and most uptodate revision of the design drawings.
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. This shall include full details of the proposed methods of curing.
label | ○ Manufacturers and suppliers of steel reinforcement materials must be in posession of a current certificate of approval, issued by the ACRS. All reinforcement must be covered by the long-term quality level of AS/NZS 4671
label | ○ Reinforcement shall be checked upon delivery and placed on timbers adjacent to site fixing.
label | ○ Ensure that materials on-site are sufficient for the completion of works.
label | REFERENCE DOCUMENTS: Design Drawings, VicRoads Spec. 610 & 611
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Material Data Sheets.
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Submission of Preliminary Documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review the following:
label | — Full details of the proposed hot or cold weather concreting procedure, not less than two weeks prior to placement of concrete if required.
label | — Detailed WMS, ITPs, & Checklists for all concrete construction works not less than 4 weeks prior to the placement of concrete.
label | — Full details of the proposed methods of curing, as part of the concrete mix design submission, not less than 4 weeks prior to placement of concrete.
label | REFERENCE DOCUMENTS: VR Specificaiton 610.17, 610.18 & 610.23
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Submitted Documentation
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Formwork Requirement & Design
label | FREQUENCY: Prior to construction of formwork (if required)
label | ACCEPTANCE CRITERIA: The requirement for formwork design shall be in accordance with VicRoads Sepcification 614 Table 614.041.
label | ○ Where formwork is required, the proof engineering certificate of compliance shall be forwarded to the Superintendent as least two days prior to the construction of any formwork.
label | REFERENCE DOCUMENTS: VR Specificaiton 610.17, 610.18 & 610.23
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: ITP Signed, Submitted Documentation
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Survey & Set Out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | REFERENCE DOCUMENTS: Design Drawings & Survey Data
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Placement of Steel Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure steel reinforcement complies with the relevant specification and design drawings.
label | ○ Reinforcement placement shall be coordinated with formwork erection such that is can be placed to the correct size, location, diameter, number and spacing as shown on the drawings.
label | ○ If required, re-bending of steel reinforcement shall not commence until the procedure has been reviewed and approved by the Superintendent, and shall be witnessed by the Superintendent's representative.
label | ○ Splices in reinforcement shall be made only in the position shown on the drawings or as otherwise approved by the superintendent. Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commmence until the welding procedure has been qualified and reviewed by the Superintendent.
label | ○ Ensure reinforcement to be embedded shall be free of mortar, oil, dirt, rust, grease, paint, tar or any other contaminants.
label | ○ Ensure 70mm cover on all steel reinforcement unless noted otherwise on the design drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec. 611
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork, including supporting systems, shall be constructed in a fashion that ensures the specified quality of concrete finish is achieved. Forms shall be clean and free of majore surface defects.
label | ○ Formwork shall be constructed and shall be sufficient stiffness to tolerate the rate of concrete placement and high frequency vibration, and shall be of uniform stiffness to avoid causing varying vibration aplitudes over the formwork surfaces during compaction of concrete.
label | ○ Formwork shall not be placed in locations where steel reinforcement and other fixtures cannot be inspected and/or will be left open until inspections have been completed.
label | ○ The application of any load shall not proceed until the signed Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewd and accepted by the the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. 614
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed / Certificate of Compliance - Formwork Inspection
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Placement of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that the forms, reinforcement, any stressing materials and embedments has been checked against the specifciation and design drawings by the Superintendent.
label | ○ All foreign material has been completely removed from the forms.
label | ○ Air and concrete temperatures shall be recorded. Concrete shall only be placed under the following conditions:
label | — Air temperature 5 to 35 deg C.
label | — Concrete temperature 10 to 30 deg C.
textbox | Measured Air Temperature:
textbox | Measured Concrete Temperature:
label | ○ Concrete shall be placed from a height not exceeding 2m. Concrete pumping shall be used where access is restricted. Prior to the commencement of placing concrete by pumping, the initial discharge of concrete shall be pumped to waste until a consistent workable mix is discharged.
label | ○ In continuous concrete pours the maximum time lag between truck loads on site shall not exceed 25 minutes.
label | REFERENCE DOCUMENTS: VicRoads Spec. 608.07
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Traceability of Concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete batches (truckloads) used in the works shall be traceable from the batch plant to its general location in the structure by a unique lot number.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.14
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed, Concrete Delivery Dockets
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Removal of Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in VicRoads Table 610.251 have elapsed, after completion of the placing of concrete.
label | ○ If drilling into newly constructed concrete members, the drilling procedure and drill locations shall be submitted for approval by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.25
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure the method and period of curing is in accordance with specifications agreed with the client.
label | ○ The contractor shall ensure that records of temperature monitoring during the curing period are available for review by the Superintendent.
textbox | Measured Curing Temperature:
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.23
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Dimensional Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Dimensional tolerances shall be checked against the requirements in accordance with specications agreed with the client.
label | ○ The concrete shall be inspected for quality of finish and compliance with the surface class requirements.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.47
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Cracking of Concrete
label | FREQUENCY: Ad Hoc
label | ACCEPTANCE CRITERIA: The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.24
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman / Superintendent / Technical Specialist
date | Date Completed:
section | 3 - Loading & Testing
checkpoint | 3.1 - Early Loading & Trafficking
label | FREQUENCY: Each Lot (as required)
label | ACCEPTANCE CRITERIA: Early loading and trafficking of bridge decks, concrete deck overlays and approach slabs shall not proceed until:
label | (i) the Contractor’s early loading and trafficking quality procedure and inspection and test plan(s) have been reviewed by the Superintendent
label | (ii) the evidence that the minimum periods stated in this clause have been satisfied and maturity testing, temperature monitoring and compressive strength test results have been reviewed by the Superintendent.
label | ○ Lane closures and and speed restrictions shall not be removed until PPV measurements, matuirty testing, temperature monitoring and compressive strength test results have been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.36
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Concrete Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be sampled and tested in accordance with AS 1012.
label | ○ The minimum number of test samples shall be in accordance with Table 610.161 in the VicRoads Standard.
label | REFERENCE DOCUMENTS: VicRoads Spec. 610.16
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Concrete Test Results
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP